GiveWell Progress and Priorities as of 7/13/2010

Summary

- Research maintenance and systemization: We have completed an extensive internal review of our research, given substantial responsibilities to non-founder employees, and identified strong volunteers who can conduct further internal reviews.

- Research vetting and credibility: we have gotten several supportive quotes and expect several more soon; we haven't yet moved forward on external vetting because we wanted to complete our internal review first, but are now moving forward and expect some output from external vetting by giving season.

- Research on new causes: we expect to complete work on U.S. equality of opportunity and microfinance by giving season.  We have had several "false starts" on disaster relief and disease research funding.  Overall, we are falling slightly short of our earlier projections in this area.

- Packaging/marketing/outreach: we have put substantial time into speaking engagements, conferences, and talks with GuideStar and other potential partners.

- Development of general charity evaluation frameworks

Research maintenance and systemization

Goal as of 2/2010: no specific goal outlined.

Progress since 2/2010:

- Completed extensive internal review (checking each claim against support given) of our 2010 research report.  This was a significant time investment.

- Systemized process of this internal review; created assignments for volunteers.  We have had two volunteers doing significant work along these lines.

- Natalie Stone has taken responsibility for annual updates on our recommended charities and for exploring new charities.  All recommended charities and several potential recommended charities have reviews in progress, but none have had their update completed yet.

- Natalie Stone and Simon Knutsson both have long-term potential.

Plan and priority:

- Natalie Stone to finish annual updates of recommended charities by 11/1/2010.

- Natalie Stone to continue investigating potential recommended charities, as a medium priority.

- Further internal review work to be conducted by volunteers.

Research vetting and credibility

Goal as of 2/2010: "subject our existing research to strong, critical scrutiny from people with substantial relevant experience and credentials."  We also sought to consolidate the case for our research's credibility (this was filed under marketing but I am now filing it here).

Progress since 2/2010:

- We decided to conduct our extensive internal review before actively pursuing critical scrutiny from people with substantial relevant experience and credentials.

- However, we have had preliminary conversations with 4 such people, 3 of whom have agreed that they should be able to complete some vetting when we are ready, and 1 of whom (the best-credentialed of the four) said it was a possibility but depends on his schedule.

- At this point we have created a variety of "vetting assignments," ranging from narrow to broad evaluations of our work.

  - We have sent one fairly broad assignment (evaluating our basic criteria and heuristics) to Laura Freschi (http://dri.fas.nyu.edu/object/laura_freschi.html), who has said she should be able to complete it within a month.

  - We have sent a narrower assignment (reviewing our work on HIV/AIDS) to Matt Bonds (http://www.hsph.harvard.edu/research/matthew-bonds/) and have not yet heard back.

  - For our broadest assignment (the "Celebrity Jeopardy" assignment, choosing a charity to give to within a pre-specified period of time) we are planning a dry run with a volunteer, after which we will send it to an academic who has agreed to complete it

- We have collected quotes on GiveWell from 6 relatively well-credentialed people (2 of these quotes we simply pulled from existing online works; the others were provided to us on request); we are working/waiting on 4 more; and 1 person has declined our request on the basis of not wanting to burn bridges with large NGOs.

Plan and priority:

At this point the bottleneck is others, not us. We are moving incrementally; as we see how vetting assignments go, we will modify them and potentially invite more people to complete them.

We expect to have at least 2 reviews of substantial portions of our research, along with resolutions on everyone we've asked for quotes, well before giving season.

## Research on new causes

Goal as of 2/2010: complete research on U.S. equality of opportunity and further sub-causes within international aid by 9/1/2010.  Work on disease research funding as well, with no specific goal in mind.

Progress since 2/2010:

- Went through academic research on U.S. equality of opportunity programs; identified and contacted promising charities running promising programs; collected evidence for key points in this report.

- Several rounds of using heuristics to identify promising microfinance organizations, contacting microfinance organizations and evaluating them.

- Still in early stages with disaster relief and disease research.  We have had many conversations with people in relevant fields, and several "false starts" in terms of finding the appropriate criteria and process.

Plan and priority:

- We are on track to publish U.S. equality of opportunity research and microfinance research by giving season.  (As of 2/2010, we had hoped to publish by 9/1/2010; we think this is possible but optimistic at this point.)

- We are unsure whether we will have anything to publish regarding disaster relief and disease research.  We will not be researching orphans and vulnerable children this year (it was on the agenda as of 2/2010).

- U.S. research is Simon Knutsson's top priority; microfinance research is Natalie Stone's; the co-Founders are working on disease research and disaster relief only as medium priorities.

## Packaging/marketing/outreach

# Goal as of 2/2010: focus only on "low-hanging fruit" in this area.

Progress since 2/2010:

- At least one substantial blog post per week.

- Partnership with GuideStar via TakeAction portal

- Appearances at several conferences/meetings:

  - Elie spoke at the HBS Social Enterprise Forum.

  - Holden spoke at the Jewish Funders' Network conference.

  - Both Holden and Elie attended the 3-day Markets for Good meeting, hosted by GlobalGiving, in June 2010.

  - Two more speaking engagements are planned in 2010.

Plan and priority:

Working with potential partners is a high priority whenever it comes up.  We intend to continue producing at least one substantive blog post per week.  Otherwise, this area is low priority.

## Development of general charity evaluation frameworks

This section was not on our radar as of 2/2010, but due to our conversations with potential partners we have spent some time developing general frameworks for evaluating charities.

One, which we are calling the "General Charity Evaluation Framework," is a completely general set of 10 questions, to be applied to any charity.  This has been developed in collaboration with Ken Berger of Charity Navigator and Tris Lumley of New Philanthropy Capital.  We are currently planning to run it by a few more parties before publishing it publicly and advocating its adoption by groups including GuideStar, Charity Navigator and Jumo, with the hope being that charities receive "transparency scores" for answering the 10 questions (and once they've done so, GiveWell is in a better position to evaluate them).

The other, which we have called the "Do-It-Yourself Project" (DIY) for now, is a set of questions by cause, intended more for donors than for charities/evaluators. We will shortly be publishing our first draft of DIY, and hope that Charity Navigator, GuideStar and Jumo will consider adapting it as an informational tool for donors; we may also use it on our own site for visitors interested in causes we haven't covered.

## Other

- Holden completed a 2-week trip to Africa, and all of GiveWell is planning a 3-month trip to India, to deepen our understanding of developing-world interventions.

- We have acquired the GiveWell trademark and givewell.org domain name

- We are in the final stages of our FY 2009 audit.