## Data from Concern Universal
NET DISTRIBUTION FOR NTCHEU DISTRICT
Financial Report as at February 2012, provided by Concern Universal to GiveWell
|  |  | Actual Expenditure |  |  | Bal. of Budget
Main Budget Heading | Budget | Budget | In-country | In-country | Bal of Budget | as at Feb 2012 | Budget notes for Givewell
| (MK) | (€) | (MK) | (€@230.23) | (MK) | (€)
Warehouse hire- Ntcheu | 50000 | 222.2222 | 4000 | 17.3739 | 46000 | 204.8483
ADC briefing meetings | 600000 | 2666.6667 | 0 | 0 | 600000 | 2666.6667 | combined with HSA and VHC meetings so cost saving incurred
HSA and VHC briefing meetings | 1000000 | 4444.4444 | 345200 | 1499.3702 | 654800 | 2945.0742 | meetings cheaper than anticipated- fewer allowances required
Briefing meeting with District Executive Committee members | 50000 | 222.2222 | 6077.5 | 26.3975 | 43922.5 | 195.8247 | combined with another scheduled DEC meeting to save costs
Household registration | 795600 | 3536 | 780320 | 3389.3063 | 15280 | 146.6937
Data entry | 120000 | 533.3333 | 311300 | 1352.1261 | -191300 | -818.7928 | additional cost incurred due to hiring of 8 temporary data entry clerks rather than 4
Data verification | 382500 | 1700 | 1852460 | 8046.1278 | -1469960 | -6346.1278 | took longer than anticipated, involved more meetings and also required use of more data entry clerks than had been anticipated to re-enter verified data
Printing registers | 100000 | 444.4444 | 0 | 0 | 100000 | 444.4444 | done using existing paper and resources so no additional costs incurred
Binding registers | 468000 | 2080 | 99500 | 432.1765 | 368500 | 1647.8235 | as above
Other stationery | 150000 | 666.6667 | 30360.57 | 131.8706 | 119639.43 | 534.7961
CU staff costs | 350000 | 1555.5556 | 1120740 | 4867.9147 | -770740 | -3312.3591 | work took longer than anticipated so more staff costs incurred
Transport support costs | 2490000 | 11066.6667 | 1135260 | 4930.9821 | 1354740 | 6135.6846 | cost of fuel and maintenance- this line had been overbudgeted
Sub total | 6556100 | 29138.2222 | 5685218.07 | 24693.6458 | 870881.93 | 4444.5764
Distribution phase
Transport for net distribution | 5000000 | 22222.2222 | 4550122 | 19763.3758 | 449878 | 2458.8465 | cost savings through increased use of three tonne truck rather than landcruisers which meant fewer trips were made
CU vehicle cost- wear & tear | 400000 | 1777.7778 | 601582.52 | 2612.9632 | -201582.52 | -835.1854
Fuel for SHSA for distribution | 200000 | 888.8889 | 52500 | 228.0328 | 147500 | 660.8561
Refreshments for VHC and village leaders during distribution | 1072800 | 4768 | 99550 | FALSE | 973250 | 4768 | significant savings against this line as not seen as an essential cost
Allowances for HSA during distribution | 397800 | 1768 | 1137300 | 4939.8428 | -739500 | -3171.8428 | distribution took longer than anticipated so allowances higher- also this line was underbudgeted
CU staff costs (4 teams- 5 CU staff x 40 days) | 1750000 | 7777.7778 | 2484784.34 | 10792.6176 | -734784.34 | -3014.8398 | work took longer than anticipated- higher staff costs
Sub total | 8820600 | 39202.6667 | 8925838.86 | 38336.8321 | -105238.86 | 865.8345
Actual costs incurred by CU but not charged to the net distribution (for Givewell use)
admin salaries (10% of Finance and Admin Manager and Country Director's time for 4 months) | 680000 | 2956.5217
Ntcheu office overheads (25% of total overheads for 4 months) | 250000 | 1086.9565
salaries of borehole drilling crew (4 staff x 1 month) | 240000 | 1043.4783
TOTAL CU COSTS | 1170000 | 5086.9565
Costs incurred by government and not charged to the net distribution
HSA salaries (431 HSAs + 8 HSA supervisors (there were a total of 14 HSA supervisors byt 6 played a more active role in the project and their costs are captured in the next budget line) each spending an average of 10 FT working days during registration, verification and distribution- average HSA salary per working day is estimated at €3.91- actual amount varies dependent on qualifications and length of tenure- figure is basic salary only and doesn't include allowances) | 3953845 | 17190.6304
Senior HSA and District staff salaries (those 10 staff engaged in ongoing work throughout distribution- total 40 days FT) | 1150000 | 5000
TOTAL GOVERNMENT COSTS | 5103845 | 22190.6304
Post distribution follow-up (6 months)
Stationery | 26000 | 115.5556 |  |  | 26000 | 115.5556
Training HSAs on PD monitoring and data collection | 397800 | 1768 |  | 0 | 397800 | 1768
Data collection for PD monitoring | 795600 | 3536 |  | 0 | 795600 | 3536
Data entry | 60000 | 266.6667 |  |  | 60000 | 266.6667
Reports writing -for all clusters | 200000 | 888.8889 |  | 0 | 200000 | 888.8889
Sub total | 1479400 | 6575.1111 | 0 | 0 | 1479400 | 6575.1111
Post distribution follow-up (18 months)
Stationery | 26000 | 115.5556 | 1250 | 5.4294 | 24750 | 110.1262
Training HSAs on PD monitoring and data collection | 397800 | 1768 |  | 0 | 397800 | 1768
Data collection for PD monitoring | 795600 | 3536 |  | 0 | 795600 | 3536
Data entry | 60000 | 266.6667 |  | 0 | 60000 | 266.6667
Reports writing -for all clusters | 200000 | 888.8889 |  | 0 | 200000 | 888.8889
Sub total | 1479400 | 6575.1111 | 1250 | 5.4294 | 1478150 | 6569.6818
Post distribution follow-up (30 & 42 months)
Stationery | 50000 | 222.2222 |  | 0 | 50000 | 222.2222
Data collection for PD monitoring (30 and 42 months only) | 1591200 | 7072 |  | 0 | 1591200 | 7072
Data entry | 120000 | 533.3333 |  | 0 | 120000 | 533.3333
Reports writing -for all clusters | 1961200 | 8716.4444 |  | 0 | 1961200 | 8716.4444
Sub total | 3722400 | 16544 | 0 | 0 | 3722400 | 16544
Grand total (Year 1) without fixed costs | 16856100 | 74916 | 14611056.93 | 63030.4779 | 2245043.07 | 11885.5221
74916
73.2874
0.32572
471589
40% of all hospital admissions in Ntcheu District.
Grand total (including follow-ups at 6, 18, 30 & 42 months) | 22057900 | 98035.1111 | 21292256.93 | 92724.7001 | 7445593.07 | 34999.2038
98035.1111
95.9039
0.42624

## Rec (hidden)
Exchange Rates: | (MK) | Rate | (€)
Funds received from the Irish Aid (Oct 11) | 17248247.8 | 230.2345 | 74916
Less: Expenditure (Qtr 1) Jan 2012 | 14611056.93 | 230.23 | 63462.8716
Total/Average | 2637190.87 | 230.2594 | 11453.1284
Actual Rate versus Budget Rate:
Actual Rate (Year 1)
Oct to Jan 12 | 14611056.93 | 230.23 | 63462.8716
Subtotal | 14611056.93 |  | 63462.8716
Total |  |  | 63462.8716
Budgeted Rate (Year 1)
Oct to Jan 12 | 14611056.93 | 225 | 64938.03
Total |  |  | 64938.03
Exchange Rate Gain / (Loss) - Year 1 |  |  | 1475.1584
Note on A15: user:

## GiveWell calculations
|  |  | Source | Notes
Numbers of nets:
Nets distributed at end of March/beginning of April 2012 | 16574 |  | "Additional costs of the 16,574 distribution are MK 350,000 fuel, running costs and allowances and MK 80,000 salary costs." Robin Todd, email to GiveWell, April 3, 2012.
Total that will be distributed at the end of the Malawi campaign | 268294 |  | "The total number of LLINs required to cover Ntcheu Town is 25,549, making the total required for Ntcheu District 268,294. As we have already received 251,720 nets from AMF this means that we will require an additional 16,574 LLINs to complete universal distribution in Ntcheu District." Email from Rob Mather to GiveWell, March 8, 2012.
Additional costs for 16,574 nets distributed at end of March/beginning of April
Shipping | 4483 |  | "The shipping costs for the additional nets was US$4,483." Robin Todd, email to GiveWell, April 3, 2012.
Distribution costs | 2453.6226 |  | "Additional costs of the 16,574 distribution are MK 350,000 fuel, running costs and allowances and MK 80,000 salary costs." Robin Todd, email to GiveWell, April 3, 2012. | As noted below (cell E85), we have used the Euro costs to calculate costs in USD. Because we received these additional distribution costs in Malawi kwatcha, we converted to Euro using the conversion rate given by Concern Universal in cell E7 of the "Data from Concern Universal" tab and then converted to USD.
Organizational costs | 0 |  | "The fixed costs should be the same as I worked them out for a length of time which included distribution of the extra nets. Actual amount spent should be the same as I have estimated because there has been no difference in salaries or rent/utilities since I made these original calculations." Robin Todd, email to GiveWell, April 3, 2012.
| Without extra costs for 16,574 nets distributed at the end of March/beginning of April | With extra costs for 16,574 nets distributed at the end of March/beginning of April
Net shipping costs | 71039 | 75522 | "Shipping costs are not included in the budget as we didn’t charge these to Irish Aid but instead covered them from our own resources. Total shipping costs for the 250,000 nets came to US$71,039" Email to GiveWell from Robin Todd, March 30, 2012
Concern Universal distribution and pre/post-distribution costs | 129929.074 | 132382.6966 | -
Costs incurred by the government | 31144.5544 | 31144.5544 | -
Concern Universal organizational costs | 7139.5445 | 7139.5445 | -
Total Concern Universal & government costs | 239252.1729 | 246188.7955
Total Concern Universal/government cost per net |  | 0.91761

## What has changed since Nov 2011
| November 2011 estimates (estimated costs) |  | April 2012 update (actual costs) |  | Change between estimated and actual costs |  | Source | Comment
Category | Total costs | Cost per net | Total costs | Cost per net | Difference in total costs | Difference in cost per net
Shipping costs | 45000 | 0.18 | 75522 | 0.28149 | 30522 | 0.10149 | November 2011 estimate was reported to us by Rob Mather in "Net Cost for GiveWell" where the total cost for Concern Universal in Malawi was quoted at $170K, including shipping costs of $45K. For the source of the April 2012 estimate, see "GiveWell Calculations," this spreadsheet. | Estimated vs actual (includes higher than estimated shipping for the original set of nets, plus extra shipping for ~16k extra nets)
Concern Universal distribution and pre/post-distribution | 125000 | 0.5 | 132382.6966 | 0.49342 | 7382.6966 | -0.006576 | November 2011 estimate was reported to us by Rob Mather in "Net Cost for GiveWell" where the total cost for Concern Universal in Malawi was quoted at $170K, including shipping costs of $45K. For the source of the April 2012 estimate, see "GiveWell Calculations," this spreadsheet. | Estimated vs actual
Organizational costs covered by Concern Universal | 0 | 0 | 7139.5445 | 0.026611 | 7139.5445 | 0.026611 | "GiveWell calculations" tab | These were costs that GiveWell did not originally include because we did not know about them.
Costs paid by the government (health surveillance assistant salaries) | 0 | 0 | 31144.5544 | 0.11608 | 31144.5544 | 0.11608 | "GiveWell Calculations" tab | These were costs that GiveWell did not originally include because we did not know about them.
Total nets | 250000 |  | 268294 |  |  |  |  | Note that the original number of nets was 250K because this was the planned number as reported to GiveWell by AMF.
Total | 170000 | 0.68 | 215044.2411 | 0.91761 | 76188.7955 | 0.23761

## FX rates
Exchange rates from http://www.oanda.com/currency/historical-rates/
| USD / EUR | USD / MWK
Period Average | 0.7612 | 163.876
Period High | 0.7755 | 165.275
Period Low | 0.7563 | 162.499
2012-04-01 | 0.7592 | 165.144
2012-03-01 | 0.7567 | 165.275
2012-02-01 | 0.7563 | 163.888
2012-01-01 | 0.7755 | 162.499
2011-12-01 | 0.7584 | 162.572