## Summary-Dowa Non-net Costs
Dowa District - Non-Net Costs - Budget and Actual
X-Rate (USD: MWK) MWK = Malawi Kwatcha | 1. May 2014 - Current |  | 400 |  |  | 3. Feb 2015 - Forward |  | 420 | Estimated Pre-D costs finalising date
| 2. May 2014 - Forward |  | 420 |  |  | 4. Sep 2015 - Forward |  | 420 | Estimated PDCU-6 costs finalising date
Nets Required | Budgeted LLINs |  | 396900 |  |  | Actual LLINs
% increase
Eventual increase
| AGREED BUDGET |  |  |  |  | ACTUAL
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15)
|  |  |  | per net |  |  |  | CU borne | AMF borne |  |  | per net | Actual | Actual | Actual
| Budget | X-Rate | Budget | Budget |  | Actual | Date | Actual | Actual | X-Rate | Actual | Actual | vs Budget | vs Budget | vs Budget
| (MK) | Applied | (USD) | (USD) |  | (MK) | Final | (MK) | (MK) | Applied | (USD) | (USD) | (MK) | (USD) | (USD), %
1. SHIPPING
All Shipping costs and clearing charges | 36844000 | 400 | 92110 | 0.23207
Shipping Sub total | 36844000 |  | 92110 | 0.23207 | 25.02%
2. PRE-DISTRIBUTION PHASE
1. Full Pre-Distribution Registration Survey (PDRS)
1. Briefing (of health teams)
1.1 District Executive Committee
District Executive Committee Members (DEC) | 93500 | 400 | 233.75 | 0.00058894
CU Staff | 3400 | 400 | 8.5 | 2.1416e-05
Drivers (Dr) | 1700 | 400 | 4.25 | 1.0708e-05
Refreshments | 23200 | 400 | 58 | 0.00014613
Fuel | 42670 | 400 | 106.675 | 0.00026877
Sub total | 164470 |  | 411.175 | 0.001036 | 0.1117%
1.2 ADC and VHC
Area Development Committee (ADC) | 0 | 400 | 0 | 0
Village Health Committee Representatives (VHC) | 0 | 400 | 0 | 0
District Health Staff (DHS) | 76500 | 400 | 191.25 | 0.00048186
CU Staff | 30600 | 400 | 76.5 | 0.00019274
Drivers (Dr) | 15300 | 400 | 38.25 | 9.6372e-05
Refreshments | 172800 | 400 | 432 | 0.0010884
Fuel | 230418 | 400 | 576.045 | 0.0014514
Sub total | 525618 |  | 1314.045 | 0.0033108 | 0.357%
1.3 HSAs
Health Surveilance Assistants (HAS) | 749700 | 400 | 1874.25 | 0.0047222
District Health Staff (DHS) | 68000 | 400 | 170 | 0.00042832
CU Staff | 27200 | 400 | 68 | 0.00017133
Drivers (Dr) | 13600 | 400 | 34 | 8.5664e-05
Refreshments | 202000 | 400 | 505 | 0.0012724
Fuel | 341360 | 400 | 853.4 | 0.0021502
Sub total | 1401860 |  | 3504.65 | 0.0088301 | 0.9521%
Briefing Sub total | 2091948 |  | 5229.87 | 0.013177 | 1.421%
2. Data Collection
i) Personnel
Data Collectors (DC) | 3748500 | 400 | 9371.25 | 0.023611
Supervisors (Sp) | 574200 | 400 | 1435.5 | 0.0036168
Drivers (Dr) | 3400 | 400 | 8.5 | 2.1416e-05
Fuel | 213250 | 400 | 533.125 | 0.0013432
Personnel Sub Total | 4539350 |  | 11348.375 | 0.028593 | 3.083%
ii) Stationary
Paper | 300000 | 400 | 750 | 0.0018896
Pencils | 25000 | 400 | 62.5 | 0.00015747
Pencil Sharpener | 7500 | 400 | 18.75 | 4.7241e-05
Pens | 75000 | 400 | 187.5 | 0.00047241
Clear bags | 325000 | 400 | 812.5 | 0.0020471
Ink pads | 10000 | 400 | 25 | 6.2988e-05
Ink | 4000 | 400 | 10 | 2.5195e-05
Toner | 800000 | 400 | 2000 | 0.0050391
Ark Lever Files | 35000 | 400 | 87.5 | 0.00022046
Stationary Sub Total | 1581500 |  | 3953.75 | 0.0099616 | 1.074%
iii) Other costs
Printing Registers | 1500000 | 400 | 3750 | 0.0094482
Binding Registers | 3354000 | 400 | 8385 | 0.021126
Photocopy Forms (Either/or) | 360000 | 400 | 900 | 0.0022676
Mobile phone airtime | 220000 | 400 | 550 | 0.0013857
Other Costs Sub Total | 5434000 |  | 13585 | 0.034228 | 3.691%
Data Collection Sub total | 11554850 |  | 28887.125 | 0.072782 | 7.848%
3. Data Entry (including error checking and revisions post verification)
Data Officer | 450000 | 400 | 1125 | 0.0028345
Data Entry Clerks | 2100000 | 400 | 5250 | 0.013228
Data entry Sub Total | 2550000 |  | 6375 | 0.016062 | 1.732%
4. Data Verification
Temporary field officers for data verification | 175000 | 400 | 437.5 | 0.0011023
Management Sub Total | 175000 |  | 437.5 | 0.0011023
5. Managemnt of the PDRS
Project Coordinator | 2200000 | 400 | 5500 | 0.013857
Project Manager | 3850000 | 400 | 9625 | 0.02425
Field coordinator | 770000 | 400 | 1925 | 0.0048501
Field officers | 1837500 | 400 | 4593.75 | 0.011574
Driver | 1100000 | 400 | 2750 | 0.0069287
Settlement allowance | 1233000 | 400 | 3082.5 | 0.0077664
Management Sub Total | 10990500 |  | 27476.25 | 0.069227 | 7.465%
6. Warehouse hire
Warehouse Hire | 625000 | 400 | 1562.5 | 0.0039368
Security Guards | 600000 | 400 | 1500 | 0.0037793
Warehouse hire Sub Total | 1225000 |  | 3062.5 | 0.007716 | 0.832%
7. Transport support costs
Car hire | 2520000 | 400 | 6300 | 0.015873
Fuel | 1344105 | 400 | 3360.2625 | 0.0084663
Wear & tear | 1260000 | 400 | 3150 | 0.0079365
Transport support cost Sub Total | 5124105 |  | 12810.2625 | 0.032276 | 3.48%
Full Pre-Distribution Registration Survey (PDRS) Sub Total | 33711403 |  | 84278.5075 | 0.21234 | 22.9%
3. DISTRIBUTION PHASE
1. Briefing (of health teams)
i) District Executive Committee
District Executive Committee Members (DEC) | 93500 | 400 | 233.75 | 0.00058894
CU Staff | 3400 | 400 | 8.5 | 2.1416e-05
Drivers (Dr) | 1700 | 400 | 4.25 | 1.0708e-05
Refreshments | 23200 | 400 | 58 | 0.00014613
Fuel | 42670 | 400 | 106.675 | 0.00026877
Sub total | 164470 |  | 411.175 | 0.001036 | 0.1117%
ii) ADC and VHC
Area Development Committee (ADC) | 0 | 400 | 0 | 0
Village Health Committee Representatives (VHC) | 0 | 400 | 0 | 0
District Health Staff (DHS) | 76500 | 400 | 191.25 | 0.00048186
CU Staff | 30600 | 400 | 76.5 | 0.00019274
Drivers (Dr) | 15300 | 400 | 38.25 | 9.6372e-05
Refreshments | 172800 | 400 | 432 | 0.0010884
Fuel | 230418 | 400 | 576.045 | 0.0014514
Sub total | 525618 |  | 1314.045 | 0.0033108 | 0.357%
iii) HSAs
Health Surveilance Assistants (HAS) | 749700 | 400 | 1874.25 | 0.0047222
District Health Staff (DHS) | 68000 | 400 | 170 | 0.00042832
CU Staff | 27200 | 400 | 68 | 0.00017133
Drivers (Dr) | 13600 | 400 | 34 | 8.5664e-05
Refreshments | 202000 | 400 | 505 | 0.0012724
Fuel | 341360 | 400 | 853.4 | 0.0021502
Sub total | 1401860 |  | 3504.65 | 0.0088301 | 0.9521%
Briefing Sub total | 2091948 |  | 5229.87 | 0.013177 | 1.421%
2. Distribution of nets
i) Personnel
Health surveilance assistants (HSA) | 749700 | 400 | 1874.25 | 0.0047222
Supervisors (Sp) | 957000 | 400 | 2392.5 | 0.006028
Drivers (Dr) | 229500 | 400 | 573.75 | 0.0014456
Fuel | 4606200 | 400 | 11515.5 | 0.029014
Personnel Sub Total | 6542400 |  | 16356 | 0.041209 | 4.443%
ii) Stationary
Paper | 300000 | 400 | 750 | 0.0018896
Pencils | 1100 | 400 | 2.75 | 6.9287e-06
Pens | 75000 | 400 | 187.5 | 0.00047241
Clear bags | 6500 | 400 | 16.25 | 4.0942e-05
Ink pads | 20000 | 400 | 50 | 0.00012598
Ink | 4000 | 400 | 10 | 2.5195e-05
Toner | 1600000 | 400 | 4000 | 0.010078
Ark Lever Files | 35000 | 400 | 87.5 | 0.00022046
Stationary Sub Total | 2041600 |  | 5104 | 0.01286 | 1.387%
iii) Other costs
Photocopy Forms (Either/or) | 360000 | 400 | 900 | 0.0022676
Printing Registers | 750000 | 400 | 1875 | 0.0047241
Binding Registers | 3354000 | 400 | 8385 | 0.021126
Refreshments for VHC and village leaders during distribution | 1200000 | 400 | 3000 | 0.0075586
Fuel for SHSA during distribution | 600512 | 400 | 1501.28 | 0.0037825
Mobile phone airtime | 300000 | 400 | 750 | 0.0018896
Other Costs Sub Total | 6564512 |  | 16411.28 | 0.041349 | 4.459%
Distribution of nets Sub total | 15148512 |  | 37871.28 | 0.095418 | 10.29%
3. Data Entry (including error checking)
Data Officer | 450000 | 400 | 1125 | 0.0028345
Data Entry Clerks | 1050000 | 400 | 2625 | 0.0066138
Data entry Sub Total | 1500000 |  | 3750 | 0.0094482 | 1.019%
4. Managemnt of the Distribution
Project Coordinator | 1320000 | 400 | 3300 | 0.0083144
Project Manager | 2310000 | 400 | 5775 | 0.01455
Field coordinator | 660000 | 400 | 1650 | 0.0041572
Field officers | 1575000 | 400 | 3937.5 | 0.0099206
Temporary field officers for data verification and distribution | 1575000 | 400 | 3937.5 | 0.0099206
Driver | 660000 | 400 | 1650 | 0.0041572
Management Sub Total | 8100000 |  | 20250 | 0.05102 | 5.501%
5. Warehouse hire
Warehouse Hire | 500000 | 400 | 1250 | 0.0031494
Security Guards | 800000 | 400 | 2000 | 0.0050391
Insurance | 800000 | 400 | 2000 | 0.0050391
Warehouse hire Sub Total | 2100000 |  | 5250 | 0.013228 | 1.426%
6.Transport support costs
Car hire | 2160000 | 400 | 5400 | 0.013605
Fuel | 2304180 | 400 | 5760.45 | 0.014514
Wear & tear | 2880000 | 400 | 7200 | 0.018141
Transport support cost Sub Total | 7344180 |  | 18360.45 | 0.04626 | 4.988%
Distribution Subtotal | 36284640 |  | 90711.6 | 0.22855 | 24.64%
4. POST-DISTRIBUTION PHASE
SECTION 1
1. Briefing (of health teams)
Data Collectors (DC) | 70000 | 420 | 166.6667 | 0.00041992
Supervisors (Sp) | 17400 | 420 | 41.4286 | 0.00010438
CU Staff | 3400 | 420 | 8.0952 | 2.0396e-05
Drivers (Dr) | 7000 | 420 | 16.6667 | 4.1992e-05
Refreshments | 6400 | 420 | 15.2381 | 3.8393e-05
Fuel | 42670 | 420 | 101.5952 | 0.00025597
Briefing Sub total | 146870 |  | 349.6905 | 0.00088105 | 0.095%
2. Data Collection
i) Personnel
Data Collectors (DC) | 1540000 | 420 | 3666.6667 | 0.0092383
Supervisors (Sp) | 382800 | 420 | 911.4286 | 0.0022964
HAS's Supervisors (HAS Sp) | 37400 | 420 | 89.0476 | 0.00022436
Drivers (Dr) | 308000 | 420 | 733.3333 | 0.0018477
Refreshments | 149600 | 420 | 356.1905 | 0.00089743
Fuel | 750992 | 420 | 1788.0762 | 0.0045051
Personnel Sub Total | 3168792 |  | 7544.7429 | 0.019009 | 2.05%
ii) Stationary
Paper | 165000 | 420 | 392.8571 | 0.00098981
Pencils | 550 | 420 | 1.3095 | 3.2994e-06
Pencil Sharpener | 1650 | 420 | 3.9286 | 9.8981e-06
Pens | 1650 | 420 | 3.9286 | 9.8981e-06
Clear bags | 7150 | 420 | 17.0238 | 4.2892e-05
Ink pads | 11000 | 420 | 26.1905 | 6.5988e-05
Ink | 4400 | 420 | 10.4762 | 2.6395e-05
Toner | 80000 | 420 | 190.4762 | 0.00047991
Ark Lever Files | 700 | 420 | 1.6667 | 4.1992e-06
Stationary Sub Total | 272100 |  | 647.8571 | 0.0016323 | 0.176%
iii) Other costs
Photocopy Forms (Either/or) | 825000 | 420 | 1964.2857 | 0.0049491
Mobile phone airtime | 88000 | 420 | 209.5238 | 0.0005279
Other Costs Sub Total | 913000 |  | 2173.8095 | 0.005477 | 0.5906%
Data Collection Sub total | 4353892 |  | 10366.4095 | 0.026118 | 2.816%
3. Data Entry
Data Officer | 150000 | 420 | 357.1429 | 0.00089983
Data Entry Clerks | 420000 | 420 | 1000 | 0.0025195
Data entry Sub Total | 570000 |  | 1357.1429 | 0.0034194 | 0.3687%
4. Managemnt of the PDCU (for the duration of a single PDCU)
Project Coordinator | 220000 | 420 | 523.8095 | 0.0013198
Project Manager | 770000 | 420 | 1833.3333 | 0.0046191
Driver | 175000 | 420 | 416.6667 | 0.0010498
Management Sub Total | 1165000 |  | 2773.8095 | 0.0069887 | 0.7536%
SINGLE PDCU TOTAL | 6235762 |  | 14847.0524 | 0.037408
SECTION 2 - Number of PDCUs and Cost increases over three year period
PDCU-6 | 6235762 | 420 | 14847.0524 | 0.037408
PDCU-12 | 6547550.1 | 420 | 15589.405 | 0.039278
Year 1 Sub Total | 12783312.1 |  | 30436.4574 | 0.076685 | 8.269%
PDCU-18 | 6874927.605 | 420 | 16368.8753 | 0.041242
PDCU-24 | 7218673.9853 | 420 | 17187.319 | 0.043304
Year 2 Sub Total | 14093601.5903 |  | 33556.1943 | 0.084546 | 9.116%
PDCU-30 | 7579607.6845 | 420 | 18046.685 | 0.045469
PDCU-36 | 7958588.0687 | 420 | 18949.0192 | 0.047743
Year 3 Sub Total | 15538195.7533 |  | 36995.7042 | 0.093212 | 10.05%
MULTI-YEAR PDCU TOTAL | 42415109.4435 |  | 100988.3558 | 0.25444 | 27.44%
SECTION TOTALS
1. SHIPPING | 36844000 |  | 92110 | 0.23207 | 25.02%
2. PRE-DISTRIBUTION PHASE | 33711403 |  | 84278.5075 | 0.21234 | 22.9%
3. DISTRIBUTION PHASE | 36284640 |  | 90711.6 | 0.22855 | 24.64%
4. POST-DISTRIBUTION PHASE | 42415109.4435 |  | 100988.3558 | 0.25444 | 27.44%
PROJECT TOTAL | 149255152.4435 |  | 368088.4633 | 0.92741 | 100%

## Dowa-CostDriverInput
Malawi - Dowa District - Distribution Budgeting - With Cost Drivers
[9 empty] | # Nets | 396900
# HHs:
Post-Distribution: # nets surveyed:
[9 empty] | US$:MKW X-rate: | 400 | (as at 30Apr14)
Budget item | Cost driver 1 | Number | Cost driver 2 | Number | Cost driver 3 | Number | Unit cost (MKW) |  | Total cost (MKW) | Total Cost (US$) | US$/HH | % | Notes
1. SHIPPING
All Shipping costs and clearing charges | [8 empty] | 36844000 | 92110 | 0.23207 | 25.02%
Shipping Sub total | [8 empty] | 36844000 | 92110 | 0.23207 | 25.02%
2. PRE-DISTRIBUTION PHASE
1. Full Pre-Distribution Registration Survey (PDRS)
(change/add individual cost lines as necessary with appropriate cost drivers)
1. Briefing (of health teams)
1.1 District Executive Committee
District Executive Committee Members (DEC) | # people | 55 | # days | 1 |  |  | 1700 | 4.25 | 93500 | 233.75 | 0.00058894 | 0.0635% | X DEC @ Y cost x Z days each
CU Staff | # people | 2 | # days | 1 |  |  | 1700 | 4.25 | 3400 | 8.5 | 2.1416e-05 | 0.002309% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 1 |  |  | 1700 | 4.25 | 1700 | 4.25 | 1.0708e-05 | 0.001155% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 58 |  |  |  |  | 400 | 1 | 23200 | 58 | 0.00014613 | 0.01576% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 1 | 853.4 | 2.1335 | 42670 | 106.675 | 0.00026877 | 0.02898% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 164470 | 411.175 | 0.001036 | 0.1117%
1.2 ADC and VHC
Area Development Committee (ADC) | # people | 80 | # days | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | X people @ Y cost x Z days each
Village Health Committee Representatives (VHC) | # people | 280 | # days | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | X people @ Y cost x Z days each
District Health Staff (DHS) | # people | 5 | # days | 9 |  |  | 1700 | 4.25 | 76500 | 191.25 | 0.00048186 | 0.05196% | X people @ Y cost x Z days each
CU Staff | # people | 2 | # days | 9 |  |  | 1700 | 4.25 | 30600 | 76.5 | 0.00019274 | 0.02078% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 9 |  |  | 1700 | 4.25 | 15300 | 38.25 | 9.6372e-05 | 0.01039% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 432 |  |  |  |  | 400 | 1 | 172800 | 432 | 0.0010884 | 0.1174% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 30 | # days | 9 | 853.4 | 2.1335 | 230418 | 576.045 | 0.0014514 | 0.1565% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 525618 | 1314.045 | 0.0033108 | 0.357%
1.3 HSAs
Health Surveilance Assistants (HSA) | # people | 441 | # days | 1 |  |  | 1700 | 4.25 | 749700 | 1874.25 | 0.0047222 | 0.5092% | X HSAs @ Y cost x Z days each
District Health Staff (DHS) | # people | 5 | # days | 8 |  |  | 1700 | 4.25 | 68000 | 170 | 0.00042832 | 0.04618% | X DHS @ Y cost x Z days each
CU Staff | # people | 2 | # days | 8 |  |  | 1700 | 4.25 | 27200 | 68 | 0.00017133 | 0.01847% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 8 |  |  | 1700 | 4.25 | 13600 | 34 | 8.5664e-05 | 0.009237% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 505 |  |  |  |  | 400 | 1 | 202000 | 505 | 0.0012724 | 0.1372% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 8 | 853.4 | 2.1335 | 341360 | 853.4 | 0.0021502 | 0.2318% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 1401860 | 3504.65 | 0.0088301 | 0.9521%
Briefing Sub total | [8 empty] | 2091948 | 5229.87 | 0.013177 | 1.421%
2. Data Collection
i) Personnel
Data Collectors (DC) | # people | 441 | # days | 5 |  |  | 1700 | 4.25 | 3748500 | 9371.25 | 0.023611 | 2.546% | X DCs @ Y cost x Z days each
Supervisors (Sp) | # people | 22 | # days | 3 |  |  | 8700 | 21.75 | 574200 | 1435.5 | 0.0036168 | 0.39% | X HZSs @ Y cost x Z days each
Drivers (Dr) | # people | 1 | # days | 2 |  |  | 1700 | 4.25 | 3400 | 8.5 | 2.1416e-05 | 0.002309% | X Drivers @ Y for Z days each
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 5 | 853 | 2.1325 | 213250 | 533.125 | 0.0013432 | 0.1448% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Personnel Sub Total | [8 empty] | 4539350 | 11348.375 | 0.028593 | 3.083%
ii) Stationary
Paper | # items | 100 |  |  |  |  | 3000 | 7.5 | 300000 | 750 | 0.0018896 | 0.2038% | # items x Y cost per item (based on number of HZ, HA etc)
Pencils | # items | 500 |  |  |  |  | 50 | 0.125 | 25000 | 62.5 | 0.00015747 | 0.01698% | # items x Y cost per item (based on number of HZ, HA etc)
Pencil Sharpener | # items | 50 |  |  |  |  | 150 | 0.375 | 7500 | 18.75 | 4.7241e-05 | 0.005094% | # items x Y cost per item (based on number of HZ, HA etc)
Pens | # items | 500 |  |  |  |  | 150 | 0.375 | 75000 | 187.5 | 0.00047241 | 0.05094% | # items x Y cost per item (based on number of HZ, HA etc)
Clear bags | # items | 500 |  |  |  |  | 650 | 1.625 | 325000 | 812.5 | 0.0020471 | 0.2207% | # items x Y cost per item (based on number of HZ, HA etc)
Ink pads | # items | 10 |  |  |  |  | 1000 | 2.5 | 10000 | 25 | 6.2988e-05 | 0.006792% | # items x Y cost per item (based on number of HZ, HA etc)
Ink | # items | 10 |  |  |  |  | 400 | 1 | 4000 | 10 | 2.5195e-05 | 0.002717% | # items x Y cost per item (based on number of HZ, HA etc)
Toner | # items | 10 |  |  |  |  | 80000 | 200 | 800000 | 2000 | 0.0050391 | 0.5433% | # items x Y cost per item (based on number of HZ, HA etc)
Ark Lever Files | # items | 50 |  |  |  |  | 700 | 1.75 | 35000 | 87.5 | 0.00022046 | 0.02377% | # items x Y cost per item (based on number of HZ, HA etc)
Stationary Sub Total | [8 empty] | 1581500 | 3953.75 | 0.0099616 | 1.074%
iii) Other costs
Printing Registers | # pages | 50000 |  |  |  |  | 30 | 0.075 | 1500000 | 3750 | 0.0094482 | 1.019% | X pages @ Y cost per form
Binding Registers | # registers | 6708 |  |  |  |  | 500 | 1.25 | 3354000 | 8385 | 0.021126 | 2.278% | X pages @ Y cost per form
Photocopy Forms (Either/or) | # pages | 12000 |  |  |  |  | 30 | 0.075 | 360000 | 900 | 0.0022676 | 0.2445% | X pages @ Y cost per form
Mobile phone airtime | # people | 4 | # months | 5 |  |  | 11000 | 27.5 | 220000 | 550 | 0.0013857 | 0.1494% | X pages @ Y cost per form
Other Costs Sub Total | [8 empty] | 5434000 | 13585 | 0.034228 | 3.691%
Data Collection Sub total | [8 empty] | 11554850 | 28887.125 | 0.072782 | 7.848%
3. Data Entry (including error checking and revisions post verification)
Data Officer | # people | 1 | # days | 45 |  |  | 10000 | 25 | 450000 | 1125 | 0.0028345 | 0.3056% | X data entry people @ Y cost x Z days each
Data Entry Clerks | # people | 10 | # days | 30 |  |  | 7000 | 17.5 | 2100000 | 5250 | 0.013228 | 1.426% | X data entry people @ Y cost x Z days each
Data entry Sub Total | [8 empty] | 2550000 | 6375 | 0.016062 | 1.732%
4. Data Verification
Temporary field officers for data verification | # people | 10 | # days | 5 |  |  | 3500 | 8.75 | 175000 | 437.5 | 0.0011023 | 0.1189%
Management Sub Total | [8 empty] | 175000 | 437.5 | 0.0011023 | 0.1189%
5. Managemnt of the PDRS
Project Coordinator | # people | 1 | # months | 5 |  |  | 440000 | 1100 | 2200000 | 5500 | 0.013857 | 1.494%
Project Manager | # people | 1 | # months | 5 |  |  | 770000 | 1925 | 3850000 | 9625 | 0.02425 | 2.615%
Field coordinator | # people | 1 | # months | 3.5 |  |  | 220000 | 550 | 770000 | 1925 | 0.0048501 | 0.523%
Field officers | # people | 3 | # months | 3.5 |  |  | 175000 | 437.5 | 1837500 | 4593.75 | 0.011574 | 1.248%
Driver | # people | 1 | # months | 5 |  |  | 220000 | 550 | 1100000 | 2750 | 0.0069287 | 0.7471%
Settlement allowance | # people | 6 | # months | 1 |  |  | 205500 | 513.75 | 1233000 | 3082.5 | 0.0077664 | 0.8374%
Management Sub Total | [8 empty] | 10990500 | 27476.25 | 0.069227 | 7.465%
6. Warehouse hire
Warehouse Hire | # months | 2.5 |  |  |  |  | 250000 | 625 | 625000 | 1562.5 | 0.0039368 | 0.4245% | X data entry people @ Y cost x Z days each
Security Guards | # people | 4 | # months | 1.5 |  |  | 100000 | 250 | 600000 | 1500 | 0.0037793 | 0.4075% | X data entry people @ Y cost x Z days each
Warehouse hire Sub Total | [8 empty] | 1225000 | 3062.5 | 0.007716 | 0.832%
7. Transport support costs
Car hire | # vehicles | 1 | # days | 105 |  |  | 24000 | 60 | 2520000 | 6300 | 0.015873 | 1.712%
Fuel | # vehicles | 1 | # litres of fuel | 15 | # days | 105 | 853.4 | 2.1335 | 1344105 | 3360.2625 | 0.0084663 | 0.9129%
Wear & tear | # vehicles | 2 | # Kms | 120 | # days | 105 | 50 | 0.125 | 1260000 | 3150 | 0.0079365 | 0.8558%
Transport support cost Sub Total | [8 empty] | 5124105 | 12810.2625 | 0.032276 | 3.48%
Full Pre-Distribution Registration Survey (PDRS) Sub Total | [8 empty] | 33711403 | 84278.5075 | 0.21234 | 22.9%
3. DISTRIBUTION PHASE
1. Briefing (of health teams)
i) District Executive Committee
District Executive Committee Members (DEC) | # people | 55 | # days | 1 |  |  | 1700 | 4.25 | 93500 | 233.75 | 0.00058894 | 0.0635% | X DEC @ Y cost x Z days each
CU Staff | # people | 2 | # days | 1 |  |  | 1700 | 4.25 | 3400 | 8.5 | 2.1416e-05 | 0.002309% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 1 |  |  | 1700 | 4.25 | 1700 | 4.25 | 1.0708e-05 | 0.001155% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 58 |  |  |  |  | 400 | 1 | 23200 | 58 | 0.00014613 | 0.01576% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 1 | 853.4 | 2.1335 | 42670 | 106.675 | 0.00026877 | 0.02898% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 164470 | 411.175 | 0.001036 | 0.1117%
ii) ADC and VHC
Area Development Committee (ADC) | # people | 80 | # days | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | X people @ Y cost x Z days each
Village Health Committee Representatives (VHC) | # people | 280 | # days | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | X people @ Y cost x Z days each
District Health Staff (DHS) | # people | 5 | # days | 9 |  |  | 1700 | 4.25 | 76500 | 191.25 | 0.00048186 | 0.05196% | X people @ Y cost x Z days each
CU Staff | # people | 2 | # days | 9 |  |  | 1700 | 4.25 | 30600 | 76.5 | 0.00019274 | 0.02078% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 9 |  |  | 1700 | 4.25 | 15300 | 38.25 | 9.6372e-05 | 0.01039% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 432 |  |  |  |  | 400 | 1 | 172800 | 432 | 0.0010884 | 0.1174% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 30 | # days | 9 | 853.4 | 2.1335 | 230418 | 576.045 | 0.0014514 | 0.1565% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 525618 | 1314.045 | 0.0033108 | 0.357%
iii) HSAs
Health Surveilance Assistants (HSA) | # people | 441 | # days | 1 |  |  | 1700 | 4.25 | 749700 | 1874.25 | 0.0047222 | 0.5092% | X HSAs @ Y cost x Z days each
District Health Staff (DHS) | # people | 5 | # days | 8 |  |  | 1700 | 4.25 | 68000 | 170 | 0.00042832 | 0.04618% | X DHS @ Y cost x Z days each
CU Staff | # people | 2 | # days | 8 |  |  | 1700 | 4.25 | 27200 | 68 | 0.00017133 | 0.01847% | X CU Staff @ Y cost for Z days each
Drivers (Dr) | # people | 1 | # days | 8 |  |  | 1700 | 4.25 | 13600 | 34 | 8.5664e-05 | 0.009237% | X Dr x Y days x Z cost per person
Refreshments | # refreshments | 505 |  |  |  |  | 400 | 1 | 202000 | 505 | 0.0012724 | 0.1372% | X refreshments @Y cost
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 8 | 853.4 | 2.1335 | 341360 | 853.4 | 0.0021502 | 0.2318% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Sub total | [8 empty] | 1401860 | 3504.65 | 0.0088301 | 0.9521%
Briefing Sub total | [8 empty] | 2091948 | 5229.87 | 0.013177 | 1.421%
2. Distribution of nets
i) Personnel
Health surveilance assistants (HSA) | # people | 441 | # days | 1 |  |  | 1700 | 4.25 | 749700 | 1874.25 | 0.0047222 | 0.5092% | X DCs @ Y cost x Z days each
Supervisors (Sp) - Senior HSAs | # people | 22 | # days | 5 |  |  | 8700 | 21.75 | 957000 | 2392.5 | 0.006028 | 0.65% | X HZSs @ Y cost x Z days each
Drivers (Dr) | # people | 3 | # days | 45 |  |  | 1700 | 4.25 | 229500 | 573.75 | 0.0014456 | 0.1559% | X Drivers @ Y for Z days each
Fuel | # vehicles | 3 | # litres of fuel | 40 | # days | 45 | 853 | 2.1325 | 4606200 | 11515.5 | 0.029014 | 3.128% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Personnel Sub Total | [8 empty] | 6542400 | 16356 | 0.041209 | 4.443%
ii) Stationary
Paper | # items | 100 |  |  |  |  | 3000 | 7.5 | 300000 | 750 | 0.0018896 | 0.2038% | # items x Y cost per item (based on number of HZ, HA etc)
Pencils | # items | 22 |  |  |  |  | 50 | 0.125 | 1100 | 2.75 | 6.9287e-06 | 0.0007471% | # items x Y cost per item (based on number of HZ, HA etc)
Pens | # items | 500 |  |  |  |  | 150 | 0.375 | 75000 | 187.5 | 0.00047241 | 0.05094% | # items x Y cost per item (based on number of HZ, HA etc)
Clear bags | # items | 10 |  |  |  |  | 650 | 1.625 | 6500 | 16.25 | 4.0942e-05 | 0.004415% | # items x Y cost per item (based on number of HZ, HA etc)
Ink pads | # items | 20 |  |  |  |  | 1000 | 2.5 | 20000 | 50 | 0.00012598 | 0.01358% | # items x Y cost per item (based on number of HZ, HA etc)
Ink | # items | 10 |  |  |  |  | 400 | 1 | 4000 | 10 | 2.5195e-05 | 0.002717% | # items x Y cost per item (based on number of HZ, HA etc)
Toner | # items | 20 |  |  |  |  | 80000 | 200 | 1600000 | 4000 | 0.010078 | 1.087% | # items x Y cost per item (based on number of HZ, HA etc)
Ark Lever Files | # items | 50 |  |  |  |  | 700 | 1.75 | 35000 | 87.5 | 0.00022046 | 0.02377% | # items x Y cost per item (based on number of HZ, HA etc)
Stationary Sub Total | [8 empty] | 2041600 | 5104 | 0.01286 | 1.387%
iii) Other costs
Photocopy Forms (Either/or) | # pages | 12000 |  |  |  |  | 30 | 0.075 | 360000 | 900 | 0.0022676 | 0.2445% | X pages @ Y cost per form
Printing Registers | # pages | 25000 |  |  |  |  | 30 | 0.075 | 750000 | 1875 | 0.0047241 | 0.5094% | X pages @ Y cost per form
Binding Registers | # registers | 6708 |  |  |  |  | 500 | 1.25 | 3354000 | 8385 | 0.021126 | 2.278% | X pages @ Y cost per form
Refreshments for VHC and village leaders during distribution | # items | 3000 |  |  |  |  | 400 | 1 | 1200000 | 3000 | 0.0075586 | 0.815% | # items x Y cost per item (based on number of HZ, HA etc)
Fuel for SHSA during distribution | # SHSAs | 22 | # litres of fuel | 8 | # days | 4 | 853 | 2.1325 | 600512 | 1501.28 | 0.0037825 | 0.4079% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Mobile phone airtime | # people | 5 | # months | 3 |  |  | 20000 | 50 | 300000 | 750 | 0.0018896 | 0.2038% | X pages @ Y cost per form
Other Costs Sub Total | [8 empty] | 6564512 | 16411.28 | 0.041349 | 4.459%
Distribution of nets Sub total | [8 empty] | 15148512 | 37871.28 | 0.095418 | 10.29%
3. Data Entry (including error checking)
Data Officer | # people | 1 | # days | 45 |  |  | 10000 | 25 | 450000 | 1125 | 0.0028345 | 0.3056% | X data entry people @ Y cost x Z days each
Data Entry Clerks | # people | 10 | # days | 30 |  |  | 3500 | 8.75 | 1050000 | 2625 | 0.0066138 | 0.7131% | X data entry people @ Y cost x Z days each
Data entry Sub Total | [8 empty] | 1500000 | 3750 | 0.0094482 | 1.019%
4. Management of the Distribution
Project Coordinator | # people | 1 | # months | 3 |  |  | 440000 | 1100 | 1320000 | 3300 | 0.0083144 | 0.8965%
Project Manager | # people | 1 | # months | 3 |  |  | 770000 | 1925 | 2310000 | 5775 | 0.01455 | 1.569%
Field coordinator | # people | 1 | # months | 3 |  |  | 220000 | 550 | 660000 | 1650 | 0.0041572 | 0.4483%
Field officers | # people | 3 | # months | 3 |  |  | 175000 | 437.5 | 1575000 | 3937.5 | 0.0099206 | 1.07%
Temporary field officers for data verification and distribution | # people | 10 | # days | 45 |  |  | 3500 | 8.75 | 1575000 | 3937.5 | 0.0099206 | 1.07%
Driver | # people | 1 | # months | 3 |  |  | 220000 | 550 | 660000 | 1650 | 0.0041572 | 0.4483%
Management Sub Total | [8 empty] | 8100000 | 20250 | 0.05102 | 5.501%
5. Warehouse hire
Warehouse Hire | # months | 2 |  |  |  |  | 250000 | 625 | 500000 | 1250 | 0.0031494 | 0.3396% | X data entry people @ Y cost x Z days each
Security Guards | # people | 4 | # months | 2 |  |  | 100000 | 250 | 800000 | 2000 | 0.0050391 | 0.5433% | X data entry people @ Y cost x Z days each
Insurance |  |  | # months | 2 |  |  | 400000 | 1000 | 800000 | 2000 | 0.0050391 | 0.5433% | X data entry people @ Y cost x Z days each
Warehouse hire Sub Total | [8 empty] | 2100000 | 5250 | 0.013228 | 1.426%
6.Transport support costs
Car hire | # vehicles | 2 | # days | 45 |  |  | 24000 | 60 | 2160000 | 5400 | 0.013605 | 1.467% | X vehicles @ Y cost x Z days each
Fuel | # vehicles | 2 | # litres of fuel | 30 | # days | 45 | 853.4 | 2.1335 | 2304180 | 5760.45 | 0.014514 | 1.565% | X vehicles x W litres @ Y cost x Z days each
Wear & tear | # vehicles | 4 | # Kms | 320 | # days | 45 | 50 | 0.125 | 2880000 | 7200 | 0.018141 | 1.956% | X vehicles x W kms @ Y cost x Z days each
Transport support cost Sub Total | [8 empty] | 7344180 | 18360.45 | 0.04626 | 4.988%
Distribution Subtotal | [8 empty] | 36284640 | 90711.6 | 0.22855 | 24.64%
4. POST-DISTRIBUTION PHASE
Guidance
1. Section 1 is for costs for one PDCU including all direct 'daily' management of the PDCU
2. Section 1 is where any PDCU administrative overhead should be added
3. Section 2 is where the number of PDCUs in the 3 year time period should be indicated
4. Please change and add cost items as necessary in this column (B)
5. Please ensure cost drivers are entered for each cost line item
6. All costs for an activity should be entered under that activity
- For example, stationary cost for the 'Briefing' activity should be entered under 'Briefing' | [8 empty] | US$:MKW X-rate: | 420
SECTION 1
1. Briefing (of health teams)
Data Collectors (DC) | # people | 10 | # days | 1 |  |  | 7000 | 17.5 | 70000 | 166.6667 | 0.00041992 | 0.04528% | X DCs @ Y cost x Z days each
Supervisors (Sp) | # people | 2 | # days | 1 |  |  | 8700 | 21.75 | 17400 | 41.4286 | 0.00010438 | 0.01126% | X HASs @ Y cost x Z days each
CU Staff | # people | 2 | # days | 1 |  |  | 1700 | 4.25 | 3400 | 8.0952 | 2.0396e-05 | 0.002199% | X Drivers @ Y cost for Z days each
Drivers (Dr) | # drivers | 1 | # days | 1 |  |  | 7000 | 17.5 | 7000 | 16.6667 | 4.1992e-05 | 0.004528% | X Drivers @ Y cost for Z days each
Refreshments | # refreshments | 16 | # days | 1 |  |  | 400 | 1 | 6400 | 15.2381 | 3.8393e-05 | 0.00414% | X People x Y days x Z cost per person
Fuel | # vehicles | 1 | # litres of fuel | 50 | # days | 1 | 853.4 | 2.1335 | 42670 | 101.5952 | 0.00025597 | 0.0276% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Briefing Sub total | [8 empty] | 146870 | 349.6905 | 0.00088105 | 0.095%
2. Data Collection
i) Personnel
Data Collectors (DC) | # people | 10 | # days | 22 |  |  | 7000 | 17.5 | 1540000 | 3666.6667 | 0.0092383 | 0.9961% | X DCs @ Y cost x Z days each
Supervisors (Sp) | # people | 2 | # days | 22 |  |  | 8700 | 21.75 | 382800 | 911.4286 | 0.0022964 | 0.2476% | X HZSs @ Y cost x Z days each
HAS's Supervisors (HAS Sp) | # people | 1 | # days | 22 |  |  | 1700 | 4.25 | 37400 | 89.0476 | 0.00022436 | 0.02419% | X HZSs @ Y cost x Z days each
Drivers (Dr) | #drivers | 2 | # days | 22 |  |  | 7000 | 17.5 | 308000 | 733.3333 | 0.0018477 | 0.1992% | X Drivers @ Y for Z days each
Refreshments | # refreshments | 17 | # days | 22 |  |  | 400 | 1 | 149600 | 356.1905 | 0.00089743 | 0.09677% | X People x Y days x Z cost per person
Fuel | # vehicles | 2 | # litres of fuel | 20 | # days | 22 | 853.4 | 2.1335 | 750992 | 1788.0762 | 0.0045051 | 0.4858% | Average fueling for for X vehicles (=people) @ (Y litres x Z/litres diesel) x W days
Personnel Sub Total | [8 empty] | 3168792 | 7544.7429 | 0.019009 | 2.05%
ii) Stationary
Paper | # items | 55 |  |  |  |  | 3000 | 7.5 | 165000 | 392.8571 | 0.00098981 | 0.1067% | # items x Y cost per item (based on number of HZ, HA etc)
Pencils | # items | 11 |  |  |  |  | 50 | 0.125 | 550 | 1.3095 | 3.2994e-06 | 0.0003558% | # items x Y cost per item (based on number of HZ, HA etc)
Pencil Sharpener | # items | 11 |  |  |  |  | 150 | 0.375 | 1650 | 3.9286 | 9.8981e-06 | 0.001067% | # items x Y cost per item (based on number of HZ, HA etc)
Pens | # items | 11 |  |  |  |  | 150 | 0.375 | 1650 | 3.9286 | 9.8981e-06 | 0.001067% | # items x Y cost per item (based on number of HZ, HA etc)
Clear bags | # items | 11 |  |  |  |  | 650 | 1.625 | 7150 | 17.0238 | 4.2892e-05 | 0.004625% | # items x Y cost per item (based on number of HZ, HA etc)
Ink pads | # items | 11 |  |  |  |  | 1000 | 2.5 | 11000 | 26.1905 | 6.5988e-05 | 0.007115% | # items x Y cost per item (based on number of HZ, HA etc)
Ink | # items | 11 |  |  |  |  | 400 | 1 | 4400 | 10.4762 | 2.6395e-05 | 0.002846% | # items x Y cost per item (based on number of HZ, HA etc)
Toner | # items | 1 |  |  |  |  | 80000 | 200 | 80000 | 190.4762 | 0.00047991 | 0.05175% | # items x Y cost per item (based on number of HZ, HA etc)
Ark Lever Files | # items | 1 |  |  |  |  | 700 | 1.75 | 700 | 1.6667 | 4.1992e-06 | 0.0004528% | # items x Y cost per item (based on number of HZ, HA etc)
Stationary Sub Total | [8 empty] | 272100 | 647.8571 | 0.0016323 | 0.176%
iii) Other costs
Photocopy Forms (Either/or) | # pages | 27500 | # pages | 1 |  |  | 30 | 0.075 | 825000 | 1964.2857 | 0.0049491 | 0.5336% | X pages @ Y cost per form
Mobile phone airtime | # people | 4 | # units/day | 1 | # days | 22 | 1000 | 2.5 | 88000 | 209.5238 | 0.0005279 | 0.05692% | X pages @ Y cost per form
Other Costs Sub Total | [8 empty] | 913000 | 2173.8095 | 0.005477 | 0.5906%
Data Collection Sub total | [8 empty] | 4353892 | 10366.4095 | 0.026118 | 2.816%
3. Data Entry
Data Officer | # people | 1 | # days | 15 |  |  | 10000 | 25 | 150000 | 357.1429 | 0.00089983 | 0.09703% | X data entry people @ Y cost x Z days each
Data Entry Clerks | # people | 4 | # days | 15 |  |  | 7000 | 17.5 | 420000 | 1000 | 0.0025195 | 0.2717% | X data entry people @ Y cost x Z days each
Data entry Sub Total | [8 empty] | 570000 | 1357.1429 | 0.0025195 | 0.3687%
4. Managemnt of the PDCU (for the duration of a single PDCU)
Project Coordinator | # people | 1 | # months | 0.5 |  |  | 440000 | 1100 | 220000 | 523.8095 | 0.0013198 | 0.1423%
Project Manager | # people | 1 | # months | 1 |  |  | 770000 | 1925 | 770000 | 1833.3333 | 0.0046191 | 0.4981%
Driver | # people | 1 | # months | 1 |  |  | 175000 | 437.5 | 175000 | 416.6667 | 0.0010498 | 0.1132%
Management Sub Total | [8 empty] | 1165000 | 2773.8095 | 0.0069887 | 0.7536%
SINGLE PDCU TOTAL | [8 empty] | 6235762 | 14847.0524 | 0.036508 | 4.034%
SECTION 2 - Number of PDCUs and Cost increases over three year period
Frequency of PDCUs (every x months) |  | 6
Number of PDCUs in 3 year period |  | 6
Estimated percentage increase in costs from one PDCU to another |  | 5%
PDCU-6 | [8 empty] | 6235762 | 14847.0524 | 0.037408 | 4.034%
PDCU-12 | [8 empty] | 6547550.1 | 15589.405 | 0.039278 | 4.235%
Year 1 Sub Total | [8 empty] | 12783312.1 | 30436.4574 | 0.076685 | 8.269%
PDCU-18 | [8 empty] | 6874927.605 | 16368.8752 | 0.041242 | 4.447%
PDCU-24 | [8 empty] | 7218673.9853 | 17187.319 | 0.043304 | 4.669%
Year 2 Sub Total | [8 empty] | 14093601.5903 | 33556.1943 | 0.084546 | 9.116%
PDCU-30 | [8 empty] | 7579607.6845 | 18046.685 | 0.045469 | 4.903%
PDCU-36 | [8 empty] | 7958588.0687 | 18949.0192 | 0.047743 | 5.148%
Year 3 Sub Total | [8 empty] | 15538195.7533 | 36995.7042 | 0.093212 | 10.05%
MULTI-YEAR PDCU TOTAL | [8 empty] | 42415109.4435 | 100988.3558 | 0.25444 | 27.44%
SECTION TOTALS
1. SHIPPING | [8 empty] | 36844000 | 92110 | 0.23207 | 25.02%
2. PRE-DISTRIBUTION PHASE | [8 empty] | 33711403 | 84278.5075 | 0.21234 | 22.9%
3. DISTRIBUTION PHASE | [8 empty] | 36284640 | 90711.6 | 0.22855 | 24.64%
4. POST-DISTRIBUTION PHASE | [8 empty] | 42415109.4435 | 100988.3558 | 0.25444 | 27.44%
PROJECT TOTAL | [8 empty] | 149255152.4435 | 368088.4633 | 0.92741 | 100%
Budget item | Cost driver 1 | Number | Cost driver 2 | Number | Cost driver 3 | Number | Unit cost (CF) |  | Total cost (MKW) | Total Cost (US$) | US$/net | % | Notes

## Data Sources
Useful sources of information
Exchange rates
http://www.xe.com/currencycharts/?from=USD&to=MWK&view=2Y
http://www.exchangerates.org.uk/USD-MWK-exchange-rate-history.html
http://www.natbank.co.mw/index.php/2013-01-10-09-18-18/foreign-exchange-rates-nbm
Inflation rates
http://www.rbm.mw/inflation_rates_detailed.aspx
http://www.nsomalawi.mw/index.php/latest-publications/consumer-price-indices.html
http://www.factfish.com/statistic-country/malawi/inflation+rate
http://www.tradingeconomics.com/malawi/inflation-cpi

## Project Timeline
DOWA PRE-DISTRIBUTION REGISTRATION SURVEY AND DISTRIBUTION PLAN
No. | ACTIVITY | 2014-10-14 |  |  |  | 2014-11-14 |  |  |  | 2014-12-14 |  |  |  |  | 2015-01-15 |  |  |  | 2015-02-15 |  |  |  | 2015-03-15 |  |  |  | 2015-04-15
|  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24
1 | Staff selection & orientation | bar: 2014-10-14 20
2 | DEC briefing meeting
3 | ADC/VHC & HSA briefing meetings | bar: 2014-11-14 3
4 | Data collection/registration
5 | Data entry & verification | bar: 2014-12-14 8 to 2014-12-14 15
6 | Additional Data Collection/Entry/Verification | bar: 2014-12-14 15
7 | Nets Arrival & Distribution Preparation | bar: 2014-12-14 8
8 | PDRS report writing | bar: 2015-01-15 12
9 | Distribution planning meetings
10 | Pilot Distribution | bar: 2015-01-15 12
11 | Distribution | bar: 2015-02-15 13
12 | Data entry & verification | bar: 2015-02-15 13
13 | Mop-Up Distribution
14 | Distribution report writing