## READ THIS FIRST!!
Periodic Report and Cash Request Form
The Periodic Update and Cash Request Form is the END Fund's central periodic reporting format, including three primary components: 1) The Narrative Report, 2) The items requested in the CHECK LIST below (review and complete) 3) And each of the following tabs in this workbook (1 through 5)
The purpose of this form is to provide the essential information for the END Fund to evaluate the program's achievements and cash needs to inform effective grant monitoring and control.
During the grant implementation period, the END Fund can disburse funds to the Implementing Partner (IP) based on demonstrated program achievement and financial requirements for the following period of implementation.
The IP should submit this form within 30 calendar days from the closing date of the relevent period(s) covered by this report, on or before the date the report due due stated in the Partnership Agreement.
All necessary supporting documents should be provided with this form. Please refer to the CHECK LIST tab for a document list.
Please assure that the Cash Request Authorization page is signed and dated by the authorized representative of the Implementing Organization. This page can be printed in PDF format and sent to the END Fund along with the entire completed workbooks in Excel format.
Please communicate with your END Fund contact if you have any questions.
CHECK LIST of documents to be submitted along with these worksheets:
SELECT BELOW TO INCLUDE
END Fund Requested | IP Included Attached
|  | Management | Comments:
Yes | Select | Organization Chart
Yes | Select | Bios of New Personnel
No | Select | Agreement(s) with Sub-Grantees
No | Select | Document Relevant to Special Grant Conditions
No | Select | Evidence and documentation required to fulfil PA conditionalities
No | Select | Updated List of in-country partners.
|  | Monitoring and Evaluation: | Comments:
No | Select | Maps indicating program locations
Yes | Select | Any mapping, survey or assessment reports due | MDA Coverage Reports
Yes | Select | Any external reports that support data quality
|  | Financial: | Comments:
No | Select | Signed and Dated Cash Request Authorization
Yes | Select | Statement of sources and uses of funds (cash flow statement)
No | Select | Updated budget
Yes | Select | Budgets including any justifications for adjustments
No | Select | Cash Reconcilation with Sub-Grantees
Yes | Select | Bank reconciliation
No | Select | Any audit report due, finacials, management letters, etc
No | Select | Any audit report due from a sub-grantee
Work plans:
Yes | Select | Include a Gantt Chart or chronogram for the next reporting timeframe
|  | Communications: (Reference: Annex D of the Partnership Agreement) | Comments:
Yes | Select | Human Interest Stories
Yes | Select | Photos of workshops, trainings, launches, testing, drug administrations, etc.
Yes | Select | Copies of publlications, press releases, educational materials

## 1. Program Outcomes & Impact
On-going Periodic Update and Cash Request
GENERAL GRANT INFORMATION
Country and Grant number: |  | Angola
Diseases: |  | Integrated
Implementing Partner: |  | Mentor-Initiative
Program Start Date: |  | 2013-04-01
Currency: |  | USD
PERIODIC UPDATE
Progress Update - Reporting Period: |  | Cycle: | Periodic | Number: | P7
Progress Update - Period Covered: |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 7
CASH REQUEST
Cash Request - Disbursement Period: |  | Cycle: | Select | Number:
Cash Request - Period Covered: |  | Beginning Date: |  | End Date:
Cash Request - Number:
Section 1: Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  | Baseline |  | Year of Target | Intended Target | Report Due Date | Actual Result | Data Source of Results | Comments on results on Impact/Outcome indicators and data sources, and any other comments
(if applicable)
[5 empty] | Value | Year
Impact | STH Prevalence Rate |  |  |  | H: 12%; U:59%; Z: 23% | 2014 | Y2 | - | - | - | STH mapping done in the 3 provinces | Mapping was completed this year and the results have been used as baseline. Targets can only be set if a second mapping is completed
Impact | Schistosomiasis Prevalence Rate |  |  |  | H: 23%; U:14%; Z: 18% | 2014 | Y2 | - | - | - | Shisto mapping done in the 3 provinces | Mapping was completed this year and the results have been used as baseline. Targets can only be set if a second mapping is completed
Impact | LF Prevalence Rate |  |  |  | TBD | 2015 | Y2 | TBD | - | - | LF mapping pending | LF mapping was not conducted as expected in line with NTD National Program recomendation. It is expected to take place in 2015 in a joint mapping funded by WHO
Outcome | Timely completion of national NTD workplans and guidelines. Angola participates in international NTD control activities. |  |  |  | - | 2014 | Y2 | - | P8 | - | National Plan of activities | The National NTD Strategic Plan 2013-2018 review workshop was held during P7, including budget discussions, no operational and budget plan 2015 has been discussed. (The annual NTD Plan 2015 has been sent to the partners in January 2015). No NTD guidelines have been elaborated or dissiminated by the Ministry of Health, Mentor has drafted guidelines on secundary and adverse effects from treatment with Praziquantel. Angola has been represented at the international NTD Conference JAF in Addis Abeba, Ethiopia, December 2014..
Outcome | Passive NTD treatment data is reported and effective enough for comparison against baseline mapping information |  |  |  | - | 2014 | Y2 | - | P8 | - | Quarterly Epidemiological NTD Report | The new NTD data collection tools started to be used during P7. The main database tools used until now were the training and meeting databases, the MDA database and the HF supervision database. In Huambo no HF have been supervised during P7, in Uíge, reflects 19 health facilities supervised during P7. However, since we just recently started conducting supervisions the values are far from being representative to the province.
Outcome | % coverage enrolled SAC through school based MDA |  |  |  | H: 71%; U:63%; Z: 77% | 2015 | Y3 | 85% | P9 | - | Results from the ALB MDA | Based on the mapping results, the MDA ALB treatment schedule for Huambo, Uíge and Zaire till 2017 has been elaborated and shared with the national and provincial health authorities.
Outcome | % coverage of community based MDA |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | So far no community campaigns have been implemented, it is proposed to do a pilot project in 2015 in some municipalities in Uíge because of the high prevalence of STH and the availability of a NTD community based intervention structure.
Outcome | % coverage of at risk population |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | The current target group is children age 5-15, however also other population groups are considered as at risk for STH infections. Reaching the other populations at risk requires other intervention strategies alongside school-based interventions.
Outcome | % coverage enrolled SAC through school based MDA |  |  |  | H:75; U: 73%; Z:87 | 2014 | Y3 | 85% | P7 | - | Results from the PZQ MDA | MDA PZQ conducted on the mid of P7 (October/November 2014) in the 3 provinces. Detailed results available through the MDA database.
Outcome | % coverage of community based MDA |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | So far no community campaigns have been implemented, it is proposed to do a pilot project during 2015 in the municipalities Songo in Uíge because of the high prevalence of SCH and the availability of a NTD community based intervention structure.
Outcome | % coverage of at risk population |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | The current target group is children age 5-15, however also other population groups are considered as at risk for SCH infections. Reaching the other populations at risk requires other intervention strategies alongside school-based interventions.
Outcome | % coverage of community based MDA |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | Prevalence of LF in Huambo, Uíge and Zaire is unknown, no mapping data available yet, however it is expected that LF mapping will be done as part of the Coordinated mapping together with STH/SCH as from March 2015. In case of LF prevalence, consequently community based MDA interventions to be developped and implemented.
Outcome | % coverage of at risk population |  |  |  | 0 | 2014 | Y3 | TBD | - | - |  | The entire population at risk of LF transmission (ineligible population for treatment: pregnant women, lactating women in the first week after birth, children <90 cm in height (approximately equivalent to 15 kg/body weight), and the severely ill). Adequate intervention strategies to be developped and implemented to reach high treatment coverage.
Outcome | % Trained in Program Activities |  |  |  | 4830 | 2014 | Y2 | 85% | P7 | - | Attendance Spreadsheets filled | 2 teachers perschool in the 3 Provinces and that training will reach 85% of those teachers. # of schools based on MENTOR assessment in every municipality
Outcome | % School Coverage |  |  |  | H: 1065; U: 1097; Z:253; T: 2415 | 2014 | Y2 | 50% | P8 | - | MENTOR M&E System + KAP Report + WASHE Report | # of schools based on MENTOR assessment in every municipality. KAP study to be conducted during P8 (February 2015).

## 2. Program Progress Outputs
On-going Periodic Update and Cash Request
PERIODIC UPDATE
Progress Update - Reporting Period: |  |  | Cycle: | Periodic | Number: | P7
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  | 7
Note: All programmatic indicators contained in the current Program Assessment Framework should be listed, regardless of whether there are targets/results for the period covered by the Periodic Update or whether the targets have been met in previous periods.
B. Programmatic Indicators
Objective No. | * Indicator No. | Indicator Description |  |  |  | Tied To | Targets cumulative? | Baseline (if applicable) |  | Intended Target Year to date | Actual Result Year to date | % achievement (Please calculate as appropriate) | Reasons for programmatic deviation from intended target and deviations from the related workplan activities
[8 empty] | Value | Year
1 | 1.1.1 | Number of NTD stakeholder meetings in Uige, Huambo and Zaire Provinces (1 per province/month plus quarterly national) |  |  |  | Current grant | Y- over entire grant | All stake holder meetings | PY1 | H:9 U:9 Z:9 National: 3 | H:9 U:9 Z:9 National: 3 | 100% | Huambo: Regular activity planning meetings held, with various participating stakeholders from DPS, DPE and Mentor. Uige: Regular meetings were held at Provincial Level to prepare the monthly activity plans and the Oct/Nov PZQ MDA. During all meetings the Mentor Project Coordinator, the Mentor NTD project manager and the Provincial Health Directorate NTD representative were present. Of note that much more encounters took place to discuss activities but those on an informal manner, and as such these are not included in the report. Zaire: regular meetings held with other stakeholders of which a majority are informal undocumented encounters. Good communication lines established with partners.
1 | 1.1.2 | Number of Rational and feasible NTD local annual work plans developed and agreed with stakeholders (1 per province plus one national) |  |  |  | Current grant | Y- over entire grant | All work plans completed | PY1 | 4 | P8 | 0% | Uige: The 2015 yearly activity plan was already prepared together with the NTD local authorities and Public Health department. However this was done in January 2015 and as such will be refered on the P8 Report.
1 | 1.1.2 | Percentage of logistical support requests fulfilled by the programme |  |  |  | Current grant | N-not cumulative | N/A | PY1 | N/A | N/A | 0% | As discussed with EF during the October 2014 visit, this target can be removed as it offers no information on the Program implementation
1 | 1.1.3 | Number of monthly meetings between MENTOR/MoH in Uige, Huambo and Zaire Provinces to analyze health facility (HF) NTD data (1 per province/month) |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | H:2 U:2 Z:2 | H:0; U: 2; Z:0 | 0% | Huambo: no meetings to analyze health faciliy data organised. Uige: Several formal and informal meetings took place to discuss both MDA data and data reviewed on HF during supervisions. Note that because of the human resources being all dedicated to the MDA the supervisions started in small scale in October (Before the MDA) and on a larger scale in December (After MDA) thus the data collected is still not representative of any municipality. The database was used for the first time and proved efficient both in data input and analysis, minor bugs were corrected. Zaire: No meetings were held to analyze health facilities data.
1 | 1.1.3 | Percentage of logistical support requests fulfilled by the programme |  |  |  | Current grant | N-not cumulative | N/A | PY1 | N/A | N/A | 0% | As discussed with EF we suggest a change in this indicator in order to reflect a more results-oriented approach. We suggest that indicator should be % of Municipalities submiting monthly NTD reports to provincial level and a target of 50%. That way, the effort should be to ensure a minimal number of municipalities submit these reports in a frequent and timely manner. Even knowing it is not a output indicator it would measure the effective support given by MENTOR when reports don't arrive on time.
1 | 1.1.4 | Number of Mentor/MoH/MoE and other stakeholders logistical meetings to manage the drug supply system (1 per province per month) |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | H:9 U:9 Z:9 | H:4; U: 5; Z:4 | 48.14% | Huambo: pre and post MDA meetings organised with various stakeholders Uige: Pre and post MDA meetings took place to ensure an accurate PZQ supply to the province. On the pre-MDA side, the PZQ was dispached late from the central deposits and only arrived on the last day of the training for area coordinators (22-Oct-2014) several emergency meetings had to be held in order to ensure the timely arrival and storage of the medication. During the post-MDA, meetings were held between the local authorities and Mentor to garantee the proper recovery of the unused PZQ from several municipalities and its storage in the provincial deposites (it was decided that the PZQ should be collected from the several municipalities during the MDA data collection). Zaire: Meetings on drugs management were organized before and after the MDA campaign.
2 | 2.1.1. | No. of HF or ANC based health workers trained thorugh on site technical coaching |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 586 | 430 | 73.38% | 180 Health workers trained in Y1 in Huambo and Uige provinces. In Y2, 135 Health Workers were trained in Zaire (in 5 municipalities) and 67 in Uige (48 had been trained in the P5). Uíge: it is planned the training of 99 health professionals for the P8 (33 in January, 33 in February and 33 in March). However, given the intent of conducting the KAP survey in February and a potential MDA campaign in March these activities might be affected. Zaire: A training session will be organized during P8 in the missing municipality.
2 | 2.1.2. | Number of NTD treatment guidelines developed and provided to HFs distributed to health workers during trainings |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 954 | 0 | 0% | Guidelines on secondary and adverse effects developed by MENTOR and shared with the National NTD coordination for approval. No other NTD Guidelines developed or proposed by the National Coordination.
| 2.1.3 | No of joint analysis of HF passive NTD patient data collection is conducted with specialist assistance |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | H:33 U:48 Z:18 | H:0; U: 0; Z:2 | 0% | Huambo: no data on HF collection and analysis conducted Uíge: Supervisions started on P7 to health facilities. No supervisions were made to the municipal departments of health Zaire: 2 Municipal departments of Health were supervised during this quarter.
2 | 2.1.4 | No. of IEC technical guideline sets/kits developed and provided to HFs |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 534 | H:0; U: 22; Z:0 | 0% | National Program gave authorization to reproduce a set of posters targeting NTDs to be delivered to HFs and Schools. These posters were produced and distributed to MENTOR bases. Huambo: posters will be distributed during P8 by the supervisors Uíge: Posters started to be delivered across the different HF during supervisions. It is planned to proceed with further distributions during trainings and school events in P8. Zaire: posters will be distributed during P8.
2 | 2.1.5 | Number of Joint MENTOR/MoH technical coaching visits to HFs assist with distribution/delivery of NTD supplies |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 410 | H:0; U: 19; Z:61 | 0% | Huambo: 2 Mentor NTD supervisors recruited, 1 NTD data clerk recruited and functioning, no technical coaching visits to HF during P7 Uíge: Supervisions started on P7 to 19 health facilities. Mentor NTD supervisors were trained in using the supervision guides and how to do a proper supervision. Then they went to do joint supervisions with MENTOR senior staff to understand the notion of constructive supervision and how to conduct one in the field. By the end of P7 the NTD supervisors were already fully capable of conducting supervisions on their own. As such, from that moment all the monthly and weekly plans consider HF spervision activities. The NTD data-clerk was also trained to input data on the supervision data-base and to check for any data-collection mistakes. Data-clection data base proved efficient, althouth minor bugs were corrected. Zaire: 61 health facilites were supervised in all 6 municipalities in joint NTD-malaria supervisions.
3 | 3.1.1 | Number of sampled schools visited to test children |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 593 | 575 | 96.96% | 97% of sampled schools were targeted. 12 schools in Huambo and 6 in Uige were not mapped due to logistical constraints.
3 | 3.1.2 | Number of sampled villages visited to test residents |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 99 | 0 | 0% | No villages sampled as per instruction from the National NTD Coordination. Tests arrived but the proposed mapping protocol has not been approved by the Ministry of Health.
3.1 | 3.1.3 | No. of enrolled school aged children (5-15) treated for STH in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | H:342.669; U:159.773:; Z:68.449 Total:570,891 | PY1 | H:503.672; U:284.093:; Z:85.479 Total:873.243 | H:342.669; U:159.773:; Z:68.449 Total:570,891 | H:68%; U:56%:; Z:80% Total:65% | Huambo: recommendation following the STH mapping for Y2 distribution of ALB is distribution in the municipalities Huambo and Longonjo but no distribution took place because no albendazole was available Uíge: Based on the mapping results, it is planned two ALB MDA campaigns the first is being aimed for March / April 2015 and the second for the third quarter of 2015. This will depend on the drug supply. Zaire: recommendation following the STH mapping for Y2 distribution of ALB in 4 municipalities did not take place because no drugs were available/ IMPORTANT NOTE: The percentages presented represent the achievment against the target and not geographical or therapeutic coverages. These results are from MDA done in November 2013. For Y2, MDA school campaign will target PZQ only given that Albendazole didn't arrive the country due to delays in placing the order from WHO. This target won't be met this Year but actual target numbers were calculated to reflect 85% coverage of the 2014 enrolled students (data collected by MENTOR at municipal level)
3.1 | 3.1.4 | No. of unenrolled school aged children (5-15) treated for STH in Huambo, Zaire, and Uige. |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | TBD | TBD | 0% | Albendazole didn't arrive to the country due to delays in placing the order with WHO. Calculations need to be done to accurately know the number of non enrolled SAC age 5-15, to set the targets for next Quarters. These numbers can be calculated from the National Census 2014 data, or from data of other health interventions, such as polio or measles vaccination campaigns or community networks.
3.1 | 3.1.5 | No. of communes reached through CDD MDA |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0% | Community mass drug distribution campaigns are not in NTD National Program Plans as drug donations limit distributions to Schools only. However, if LF proves to be endemic in some provinces, there will be a need to target the entire population and these campaigns could be integrated with other MDAs if permissions are received . It can be defined only once LF mapping is done.
3.1 | 3.1.6 | No. of pre-SAC that receive MDA in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0%
3.1 | 3.1.7 | No. of pregnant women that receive MDA in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0%
3.1 | 3.1.8 | No. of high risk adults (>15) that receive MDA in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0%
3.2 | 3.2.1 | No. of enrolled school aged children (5-15) treated for Schisto in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | H:356.765 ; U:214.529; Z:84,664 | PY2 | H:503.672; U:284.093:; Z:85.479 Total:873.243 | H:356.765; U:214.529; Z:84,664 | H:70,8; U:75.5% Z:99,0% | IMPORTANT NOTE: The percentages presented represent the achievement against the target and not geographical or therapeutic coverages. Huambo: MDA conducted early November, long data collection process because of exams and closure of schools, data collection and entry completed in January 2015 Uíge: The MDA lasted a period comprehended between the end of October and the begining of November. Towards the mid and late November data was collected from the various municipalities and inserted into the data-base. In the end, an MDA report detailing all the results, challenges, solutions and recommendations was produced and shared with our partners and donors. Zaire: Drugs administration and data collection were completed by the end of November. Data entry was done in December.
3.2 | 3.2.2 | No. of unenrolled school aged children (5-15) treated for Schisto in Huambo, Zaire, and Uige. |  |  |  | Current grant | Y- over entire grant | H:; U: 3288; Z: | PY1 | TBD | H:10790; U: 3288; Z:3,187 | TBD | Huambo: high number of treated non-enrolled children although no campaigns at community level has been done Uíge: A total of 3,288 non-enrolled SAC dewormed during the PZQ MDA. Higher values would be obtained if a stronger pre-campaign strategy was putted into place. Zaire: In total, 3,6% of children reached were unenrolled children.
3.2 | 3.2.3 | No. of communes reached through CDD MDA (Schisto) |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0% | PZQ Drug donations are not currently available for us to deliver at community level, only for school level distributions. . However, if some hotspots are identified it may be possible to target some communes with remaining tablets (and possibly other donations) of School MDA (given that tablets will expire soon). Possibility of targeting adults is under discussion.
3.2 | 3.2.4 | No. of high risk adults (>15) that receive MDA in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0%
3.3 | 3.3.1 | No. of communes reached through CDD MDA (LF) |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | TBD | 0 | - | Dependent of LF mapping
3.3 | 3.3.2 | No. of high risk adults (>15) that receive MDA in Huambo, Zaire and Uige |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | TBD | 0 | - | Dependent of LF mapping
3.4 | 3.4.1 | No. of government officials that receive training as part of cascade |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 100 | H:74; U:33; Z:12 | 0% | Huambo: 12 health techniciens, 12 social mobilisators, 13 school health supervisors, 37 area coordinators Uige: 2 persons per each municipality were trained, one representative of health and one representative of education per each municipality. In the municipality of Buengas, due to its remoteness and poor road infrastucture, 3 area coordinators were trained to get higher supervision coverage. Zaire: One health representative and one education representative were trained in each municipality.
3.4 | 3.4.2 | No. of teachers involved in MDA campaign planning and delivery in their schools |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 4830 | H:2191 ; U:2.174; Z:565 | 0% | Target was reduced to reflect the reality. It is not feasible to train 3 teachers/directors per school as initially planned. Therefore, 2 teachers are considered. Calculations were made on the basis of data collected by MENTOR at Municipal level. Total of Schools: H: 1065; U: 1097; Z: 253; Total: 2415. Uíge: According to the training forms filled in and the information gathered in the field it is estimated that 2,174 teachers/directors participated in the trainings. Zaire: Slightly more than 2 persons/school were trained as some municipalities tried to get 3 persons/school.
3.4 | 3.4.3 | No. of CDDs involved in MDA campaign planning and delivery |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | TBD | 0 | 100% | CDD will be trained if Community Campaigns move on. Total number of CDD needs to be defined according to the communes/villages endemic for LF and/or hotspots defined during mapping
3.4 | 3.4.4 | Number and type of non-program funded community campaigns to which MDA activities develop linkages (at least 2 per year per province) |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 0 | 0 | 0% | These IEC campaigns need to be revised as possible links with other programs might be hard to find. As a solution, we propose the development of a strong IEC component via radio messages targeting NTD prevention and MDA campaigns preparation (broadcast of messages to MDA preparation like the ones broadcasted for November campaign)
4.1 | 1 | No. of KAP Studies |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 3 | 0 | 0% | ToR for KAP developped and presented to National NTD Coordination. All KAP surveys are planned to be done during the P8 (February when schools open). WASH supervisors to be recruited in January. Uíge: Interviews are being conducted to hire the WASH supervisor. Given the size, road conditions and number of municipalities in Uíge we will resort to activists to help conducting the survey.
4.1 | 2 | Number of schools sampled for assessment report |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 30 | 575 | 1917% | In total, 575 schools across the 3 provinces have been/will be assessed for basic sanitation levels. WASH-related survey incorporated into school-based mapping of STH and schistosomiasis,
4.1 | 3 | Number of schools reached with WASH package IEC interventions |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 531 | 0 | 0% | Activities are planned for P8 and Mentor will be seeking to continue these activities during Y3. Target for the remaining periods needs to be reviewed as it may be impossible to reach the target set.
4.1 | 4 | Number of hygiene kits distributed to the schools |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 531 | 0 | 0% | Activities are planned for P8 and Mentor will be seeking to continue these activities during Y3.
4.1 | 5 | No. of reports submitted to government stakeholders |  |  |  | Current grant | Y- over entire grant | N/A | PY1 | 6 | 3 | 100% | Mapping report with WASH info relative to the schools mapped was given to Education and Health Authorities in the 3 Provinces. Results were presented to these Provincial authorities
* Indicator No. should correspond to the indicator number listed in the approved Program Assessment Framework of the grant (1.1, 1.2, etc.)
C. Analysis of data quality and reporting issues
(!) This section should contain (1) a summary of issues related to data quality and reporting on programmatic indicators, and any relevant issues which are not covered in 'Reasons for programmatic deviation', and (2) remedial actions that are underway or planned to address these issues.
Evaluation of the indicators to be done in February 2015. A data-base was developed and is being used andhas proved efficient for data entry and data alaysis. Huambo: 2 supervisors and a data clerk recruited, WASH supervisor to be recruited in January 2015, In Uíge, appart from the WASH suppervisor, all the remaining EF staff was hired and trained. Zaire: all staff recruited.

## 3A. Financial Data Summary
On-going Periodic Report and Cash Request
PERIODIC UPDATE
Progress Update - Reporting Period: |  |  | Cycle: | Periodic | Number: | P7
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  | 7
Currency: |  |  | USD
Section 4: Total Implementing Partner Cash Outflow Summary
A. SUMMARY BUDGET BREAKDOWN BY EXPENDITURE CATEGORY
No. | Category | P7 |  | PY2 To Date |  | Comments
|  | Budgeted | Actual | Budgeted | Actual
1 | Human Resources | 198753.4 | 176247.26 | 701371.73 | 388628.52 | (1) Underspending for the quarter continues to be explained by the long delays in deploment of international staff (challenging recruitment and excessively long visa application processes) and as a consequence also delayed recruitment of local teams as not all activities could start as planned (e.g. WASH). (2) Since mid 2014 payments for goods and services in Angola are no longer allowed in USD. Staff salaries were converted to AOA as of October at a negotiated rate with the staff of 105AOA/USD. This has increased the existing staff salary expenditures against budget by 2%.
2 | Technical Assistance | 2640 | 2783.98 | 64034.6 | 61814.26
3 | Training | 64245 | 41473.19 | 211775.78 | 99172.24 | Focus of P7 was on MDA and ensuing follow-up which led to delays in organizing regular trainings
4 | Health Products and Health Equipment | 0 | 0 | 3471.92 | 3471.92
5 | Medicines and Pharmaceutical Products | 0 | 0 | 205733.1 | 0 | No medicines and Pharmaceutical Products have been procured with EF funds to date.
6 | Procurement and Supply Management Costs | 76701 | 8775.24 | 85626.25 | 11560.51 | Warehouses for drugs and other equipments have been removed from the budget as not required. The MENTOR offices will provide the space needed for stocking items.
7 | Infrastructure and other Equipment | 68850 | 1094.99 | 287710.87 | 224718.05 | The Angola goverment increased taxes for "luxury cars" by more than 40%, so cars were procured from Gibraltar, realizing savings between 20-25% of total budget during P6. Purchase of the Luanda car, and other equipment (printers and last generators) will be concluded in P8 .
8 | Communications Materials | 38700 | 7782.92 | 59700.15 | 8905.72 | Most materials are related to hygiene/WASH. WASH coordinator arrived in Jan 2015 so expenditures will incur in P8
9 | Monitoring and Evaluation | 13134.71 | 11892.92 | 36208.03 | 16483.86 | No major deviations to report for P7
10 | Living or other Support to Beneficiary Population(s) | 83250 | 0 | 83250 | 0 | No meals distributed during MDA. Hygiene kits are part of WASH, activities to start in P8
11 | Planning and Administration | 134582.9375 | 106940.21 | 278067.8025 | 198954.86 | Savings are due to increasing cost sharing opportunities with other grants. Some of the unspent balances in rent payments will need to be used in P8.
12 | Overheads | 68085.7048 | 35699.071 | 201695.0403 | 101370.994 | Indirect Costs Contribution
13 | Other | 0 | 0 | 0 | 0
TOTAL |  | 748942.7523 | 392689.781 | 2218645.2728 | 1115080.934
B. SUMMARY BUDGET BREAKDOWN BY PROGRAM ACTIVITY
No. | NTD Macro Category | P7 |  | PY2 To Date |  | Comments
|  | Budgeted | Actual | Budgeted | Actual
1 | NTD Capacity Building | 91750 | 66945.91 | 180188.6 | 88068.85 | Luanda based NTD liaison left in early December which led to a delay in some Cap Dev activities. Other trainings postponed due to MDA and follow-up work. Several trainings moves to P8.
2 | Training and Workshops | 99044.6 | 51670.74 | 301616.72 | 128968.58 | Training room rental not required as provided by DPS. Some P7 trainings postponed to P8 given focus on MDA and follow-up activities in P7 and delays in recruitment of coordinators and supervisor/trainer teams
3 | Support to Health Facilities | 94760.9 | 72925.44 | 306346.33 | 227013.62 | M&E officer recruited and obtained visa, but canceled last minute so scheduled expenditures for P7 were not made
4 | IEC/ACSM | 34160 | 7042.82 | 51048.85 | 10570.19 | Majority of spendings expected to occur in P8 in conjunction with WASH activities (see under WASH category)
5 | NTD Mapping | 0 | 5297.44 | 129324.05 | 135777.7 | Overall comment: Costs of mapping teams working on the field and cars available for the activities were largely understimated. In Zaire province we paid hotel accomodation to the mapping team. In other provinces a fix amount was paid to each person, and they took their responsability for their accomodation. This new policy help to reduce the expenses. In the other hand, the lack of cooperation in some cases of the DPS by providing the provincial cars, forced Mentor to rent cars for the period of the mapping activities. For P7: Final mapping related invoices were paid in December.
6 | Assessments and Surveys | 2741.21 | 1356.37 | 8626.69 | 1906.05 | P7 underspending based on revised budget. M&E officer recruited and obtained visa, but canceled last minute so scheduled expenditures for P7 were not made
7 | Mass Drug Administration | 166423.2 | 51166.63 | 566839.99 | 160908.02 | Underspending explained by the fact that no drugs were purchased for community distribution as MoH has not agreed to this yet.
8 | WASH | 125877.1375 | 42018.09 | 238114.4925 | 93161.86 | WASH coordinator recruited in P7 but only arrived in Jan 2015 due to long visa process. WASH activities will therefore take off in P8
9 | Supervision | 12281 | 17423.67 | 40449.97 | 29666.51 | Supervision teams largely put in place in P7, expenditures in line with revised budget
10 | Program Management and Administration | 53819 | 41143.6 | 194394.71 | 137668.56 | Expenditures largely in line with revised budget. Some equipment purchases to take place in P8. Savings made on rent payments due to cost share with other grants - some more rent payments are due in P8.
11 | Indirect Cost Contribution | 68085.7048 | 35699.071 | 201695.04 | 101370.994
12 | Medicines (Mapping, MDA, etc.)
13 | Distribution Costs (MDA)
14 | Supervision
15 | Program Management and Administration
TOTAL |  | 748942.7523 | 392689.781 | 2218645.4425 | 1115080.934
C. SUMMARY BUDGET BREAKDOWN BY IMPLEMENTING PARTNER
No. | Type and Name of Implementer | Current Period |  | Program Year To Date |  | Comments
|  | Budgeted | Actual | Budgeted | Actual
1 | The MENTOR Initiative | 748942.7523 | 392689.781 | 2218645.4425 | 1115080.934
2 | Sub-Grantee
3 | Sub-Grantee
TOTAL |  | 748942.7523 | 392689.781 | 2218645.4425 | 1115080.934
Note on A28: Author: Totals for in each of Sections A, B, and C should equal the same amounts.

## 3B. Total Cash Outflow
On-going Periodic Report and Cash Request
PERIODIC UPDATE
Progress Update - Reporting Period: |  | Cycle: | Periodic | Number: | P7
Progress Update - Period Covered: |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31 |  | A Statement of Sources and Uses of Funds is to be provided by the Implementing Partner to the END Fund
Progress Update - Number: |  | 7
Currency: |  | USD
Section 4: Total Implementing Partner Cash Outflow Summary
Budget Summary by Expense Category | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason(s) for Variance |  | Cumulative Budget through this Reporting Period | Cumulative Actual Cash Outflow through this Reporting Period | Variance | Reason(s) for Variance
1. Total IP cash outflow vs. budget | 748942.7523 | 392689.781 | 356252.9713 |  |  | 2218645.2728 | 1115080.934 | 1103564.3388
1a. IP's total expenditures | 748942.7523 | 392689.781 | 356252.9713 |  |  | 2218645.2728 | 1115080.934 | 1103564.3388
1b. Disbursements to Sub-Grantees (if applicable) |  |  | 0 |  |  |  |  | 0
Budget Summary by Program Activities | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason(s) for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason(s) for Variance
2. Total IP cash outflow vs. budget | 748942.7523 | 392689.781 | 356252.9713 |  |  | 2218645.4425 | 1115080.934 | 1103564.5085
2a. IP's total expendiures | 748942.7523 | 392689.781 | 356252.9713 |  |  | 2218645.4425 | 1115080.934 | 1103564.5085
2b. Disbursements to Sub-Grantees (if applicable) |  |  | 0 |  |  |  |  | 0

## 4A. Cash Reconcilation
On-going Periodic Report and Cash Request
REQUEST PERIOD
Progress Update - Reporting Period: |  | Cycle: | Periodic | Number: | P7 | A Statement of Sources and Uses of Funds is to be provided by the Implementing Partner to the END Fund
Progress Update - Period Covered: |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 7
Currency: |  | USD
Section 5: Financial Reconciliation and Cash Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 8 from Cash Reconciliation section of the period covered by the previous Periodic Update):
777774.0058
Add: | 2. Cash received by the IP from the END Fund during the period covered by this periodic update: | [5 empty] | 553750
3. Interest received on bank account
| 4. Any sources of income, (if applicable, e.g. disposal of fixed assets, tax refunds) | [6 empty] | 553750
Less: | 5. Total cash outflow during period covered by Progress Update (value entered in Section 4 "Total Cash Outflow": | [5 empty] | 392689.781
6. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign)
| 7. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) | [6 empty] | 392689.781
8. Cash Balance: End of period covered by Periodic Update: | [7 empty] | 938834.2248
Explanation of reconciliation adjustments (line 7)
! An explanation must be provided if there have been any adjustments.
Not gain/losses or reconciliation adjustment have been rerpoted during this quarter

## 4B. Cash Request
On-going Periodic Report and Cash Request
REQUEST PERIOD
Country and Grant number: |  |  | Angola
Progress Update - Reporting Period: |  |  | Cycle: | Periodic | Number: | P7
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  |  | 7
Currency: |  | USD
Section 5: Financial Reconciliation and Cash Request
B: REQUEST FOR FUNDS
Total forecasted net cash expenditures by the Implementing Partner for the period immediately following the period covered by the Periodic Report:
1. Period beginning date: |  |  |  | end date: |  |  | approved budget amount: | 634676 | forecasted amount: | 260000
2a. Cash buffer period (by default) | [10 empty] | Implementing Partner Total Forecast
(cash "buffer") beginning date: |  |  |  | end date: |  |  | approved budget amount: | 986393.44 | forecasted amount: | 986393.44
1246393.44
Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. | [5 empty] | _ Period beginning date: From 1 January to 31st March 2015 _ Cash buffer period: As instructed by EF we cash buffer will cover 6 months, from 1 April2015 to 30 September 2015. _ YR3 Budget approved $1,972,787 so approved budget amount for this perdio is $986,393.44 _ Forecast amount for period 1 April to 31 September 2015 is not an accurate projection due the budget revision for YR3 will take place during February 2015.
NB. Consider the following items when providing the analysis.
- Expected timing of payments for any significant budgetary items,
- Impact of existing cash balance with Sub Grantees
- Current confirmed commitments to be paid during the cash request period
- Current/expected unit prices compared to those in the budget
- Change in quantities compared to budget
- Exchange rates and inflation
- Linkage between budget absorption and programmatic performance to-date.
! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the next implementation period
3. Cash Balance: End of period covered by Periodic Update (number 8 from IP Cash Reconciliation sheet): | [9 empty] | 938834.2248
| Less: | [9 empty] | 938834.2248
6. IP's Disbursement Request to the END Fund for the period immediately following the period covered by the Periodic Update, plus additional period (cash buffer): | [10 empty] | 307559.2152
7. Does the IP's Cash Request include funds for health product procurement? | [5 empty] | No
8. Exchange Rate (used to translate local currency into grant currency) | [5 empty] | Name of local currency, date and source of the exchange rate, and other comments (if appropriate)
| - used to convert Opening Cash Balance |  |  | 98.329 |  | October Exchange Rate AOA/USD
| - used to convert Closing Cash Balance |  |  | 99.489 |  | November Exchange Rate AOA/USD
| - used to convert Total Cash Outflow for the Periodic Update Period |  |  | 101.45 |  | December Exchange Rate AOA/USD

## 5. Cash Request Authorization
On-going Periodic Update and Cash Request
GENERAL GRANT INFORMATION
Country and Grant number: |  | Angola
Diseases: |  | Integrated
Implementing Partner: |  | Mentor-Initiative |  |  |  | Please print, sign and date this form.
Program Start Date: |  | 41365
Currency: |  | USD
PERIODIC UPDATE
Progress Update - Reporting Period: |  | Cycle: | Periodic |  | P7
Progress Update - Period Covered: |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31
Progress Update - Number: |  | 7
CASH REQUEST
Cash Request - Disbursement Period: |  | Cycle: | Select | Number:
Cash Request - Period Covered: |  | Beginning Date: |  | End Date:
Cash Request - Number:
Section 7: Cash Request and Authorization
A: CASH REQUEST
On behalf of the IP, the undersigned hereby requests the END Fund to disburse funds under the above referenced Partnership Agreement as follows:
1. Cash amount requested from the END Fund in grant currency |  |  |  | 307559.2152
2. Amount requested in words: |  | three hundred and seven thousand five hundred fifty-nine
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Periodic Update and Cash Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 12 of the Partnership Agreement.
Signed on behalf of the Implementing Organization: (signature of Authorized Designated Representative) |  |  | The MENTOR Initiative
Name: | German Martinez Pacheco
Title: | Senior Grants Manager
Date: | 2015-01-30

## 6. EF Review (hidden)
On-going Periodic Update and Cash Request
GENERAL GRANT INFORMATION
Country and Grant number: |  |  | Angola
Diseases: |  |  | Integrated
Implementing Partner: |  |  | Mentor-Initiative
Program Start Date: |  |  | 41365
Currency: |  |  | USD
PERIODIC UPDATE | [6 empty] | CASH REQUEST
Progress Update - Reporting Period: |  |  | Cycle: | Periodic |  | P7 | Cash Request - Disbursement Period: |  |  | Cycle: | Select | Number:
Progress Update - Period Covered: |  |  | Beginning Date: | 2014-10-01 | End Date: | 2014-12-31 | Cash Request - Period Covered: |  |  | Beginning Date: |  | End Date:
Progress Update - Number: |  |  | 7 |  |  |  | Cash Request - Number:
Section 8: EF Request Review Sheet
A: CUMULATIVE GRANT FUND RECONCILIATION
1. Current Partnership Agreement Revision: | [7 empty] | Total Grant Funds:
2. Less Funding Tranches
Sub-total: | Period of Cash Request (from PAF) |  |  |  | Date
1
2
3
4
5 | [11 empty] | 0
3. Current Fund Balance: | [11 empty] | 0
B: REQUEST SUMMARY AND REVIEW
4B) Total Cash Outflow |  | Budgeted | Actual | Variance |  | 5C) Cash Request | Budgeted | Forecasted | Variance
| Period | 748942.7523 | 392689.781 | 356252.9713 |  | Period | 634676 | 260000 | 374676 |  | Current IP Cash Balance |  | 938834.2248
| Cumulative | #NAME? | 1115080.934 | #NAME? |  | Buffer | 986393.44 | 986393.44 | 0 |  | Requested Cash Amount: |  | 307559.2152
1. APPROVED CASH AMOUNT: |  |  |  | NEW FUND BALANCE FOLLOWING APPROVAL: |  |  | 0
2. JUSTIFICATION:
C: AUTHORIZATION
END Fund Authorized Program Director:
Name: |  |  |  | Title: |  |  |  | Date: