## Outputs & outcomes Y3
MENTOR WORKPLAN Yr3
| Activity | Specific tasks | Year Targets | [7 empty] | Q1 | [6 empty] | Q2 | [6 empty] | Q3 | [6 empty] | Q4 | [6 empty] | Deliverables | Person/Entity in Charge | Comments
| Objective 1 - Ministry of Health has sustainable integrated NTD programme across 3 provinces and capacity to scale to national coverage |  | LDA | UIG | ZAI | HBO | BIE | KUANDO KUBANGO | KWANZA SUL | TOTAL | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBP | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS
Output #1 | A1.1 - Planning and Coordination Meetings at National and Provincial Level | 1- Set up regular dates for meetings in each Province with DTN Officials | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 60 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | Monthly Plans at Provincial and National Levels | PM NTDP | One meeting per month
|  | 2 - Organize and put in place meetings at least once a month | [37 empty] | PM NTDP
Output #2 | A1.2 - Provide Technical Support for National and Provincial levels to deliver workplans and to the implementation of the programme | 1 - Organize monthly meeting to write agreed joint workplans | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 60 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | Yearly Workplans Jan - Dec 2015 | PM NTDP NTDN | One meeting per month
| A1.3 - Provide logistical support to provincial and national NTD teams | 1 - Develop a needs assessment on logistical needs on each province | NA | NA | NA | NA | NA | NA | NA | NA | [28 empty] | NA |  | NA | bar: Q1 LDA to Q1 HBO; Q1 KS to Q2 HBO; Q2 KS to Q3 HBP; Q3 KS to Q4 HBO; Q4 KS
2 - Agree on the logistical support to be given by The MENTOR Initiative both at National and Provincial levels | bar: Q1 BIE to Q1 KK; Q2 BIE to Q2 KK; Q3 BIE to Q3 KK; Q4 BIE to Q4 KK
3 - Define a logistical support plan for the Quarter/Year
Output #3 | A1.4 - To organize regular meetings to accurately analyse the NTD burden data | 1 - Set up a regular meeting for data analysis in all provinces (reflected in the monthly plannings) | 12 | 12 | 8 | 8 | NA | NA | NA | 28 | 1 | 3 | 2 | 2 | NA | NA | NA | 1 | 3 | 2 | 2 | NA | NA | NA | 1 | 3 | 2 | 2 | NA | NA | NA | 1 | 3 | 2 | 2 | NA | NA | NA | Monthly NTD data table or graphic reflecting disease burden in the Province | PM NTDP | One meeting per month
|  | 2 - Design and use proper data collection and analysis tools | [37 empty] | PM NTDP NTDN
| A1.5 - Data report handing over in time | 1 - Set up a week/days in the month for this activity (reflected in the monthly planning). Should be near the deadline for monthly data collection | 12 | 12 | 12 | 12 | NA | NA | NA | 36 | 4 | 3 | 3 | 3 | NA | NA | NA | NA | 3 | 3 | 3 | NA | NA | NA | NA | 3 | 3 | 3 | NA | NA | NA | NA | 3 | 3 | 3 | NA | NA | NA | (DPS reports to National Programme Coordination) | PM/SUP/NTDP | Mentor supports the DPS in submitting monthly reports to the National Programme Coordination
2 - Conduct data collection trips in accordance to data supervisions to Municipal Health teams (A2.3)
Output #4 | A1.6 - Organize specific meetings targeting NTD drug supply for MDA and health facilities | 1 - Set up a regular monthly date with NTD, EM and MoE officials in each province (should be reflected in the monthly workplans) | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 36 | 3 | 3 | 3 | 3 |  |  | 1 | 3 | 3 | 3 | 3 |  |  | 1 | 3 | 3 | 3 | 3 |  |  | 1 | 3 | 3 | 3 | 3 |  |  | 1 | Stock balance disagregated by NTD drug/municipality with expiry dates | PM/NTDP/EM | One meeting per month
|  | 2 - Assess the current stocks and expiry dates in HF and municipal warehouses in each municipality | [37 empty] | PM/NTDP/EM | bar: Q1 BIE to Q1 KK; Q2 BIE to Q2 KK; Q3 BIE to Q3 KK; Q4 BIE to Q4 KK
|  | 3 - Create and update on a monthly basis a NTD stock control database inarticulation with NTD and EM programs in provinces | [36 empty] | Updated stock control spreadsheet | PM/NTDP/EM
| Objective 2 - Primary Health Care System (PHC) in provinces has competency and delivers systematic NTD control |  | LDA | UIG | ZAI | HBO | BIE | KUANDO KUBANGO | KWANZA SUL | TOTAL | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS
Output #1 | A2.1 - Organize training sessions of health workers on the prevention, management of NTD and WASHE | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan | NA | 297 | 194 | 242 | NA | NA | NA | 733 | NA | 78 | 66 | 0 | NA | NA | NA | NA | 76 | 20 |  | NA | NA | NA |  | 119 | 60 |  | NA | NA | NA |  | 24 | 48 |  | NA | NA | NA | Monthly workplan with trainings dates | PC/NTDP | Number of health units * 1 health professionals / Quitexe (Uige) 2 health professionals
2 - Inform Provincial and Municipal Authorities about the training dates (inform with letter)
|  | 3 - Prepare training logistics (training materials and catering) | [8 empty] | HBO: 196; LDA: NA; HBO: 46; LDA: NA; HBO: 0 | Attendance Spreadsheet filled | PM
4 - Deliver the training
|  | 5 - Write a Training Report | [36 empty] | Training Report | PM/NTDP
Output #2 | A.2.2 - Produce technical guidelines and training curriculum disseminate to health Facility | 1 - Produce technical guidelines and get NTD Program approval | 1 | 0 | 0 | 0 | NA | NA | NA | 0 |  | 0 | 0 | 0 | NA | NA | NA |  | 0 | 0 | 0 | NA | NA | NA |  | 0 | 0 | 0 | NA | NA | NA |  | 0 | 0 | 0 | NA | NA | NA | Technica guideline and training curriculum for Health Staff, to be developed By MoH | PC/NTDN | Technical guidelines and training curriculum for Health Staff trainings on NTD diagnose and treatment to be developed by the National NTD coordiantion. To be dissiminated and distributed to DPS and HF during Y4
|  | 2 - Print the approved guidelines | [36 empty] | Multiplication and distribution of techical guidelines and training curriculum | PM
|  | 3 - Deliver the guidelines to Health Workers | [37 empty] | PM
Output #3 | A2.3 - Perform joint technical supervisions with Provincial NTD coordinators to municipal health departments on NTD data collection and analysis | 1 - Define a clear NTD data management system |  | 64 | 0 | 0 | NA | NA | NA | 64 |  | 16 | 0 | 0 | NA | NA | NA |  | 16 | 0 | 0 | NA | NA | NA |  | 16 | 0 | 0 | NA | NA | NA |  | 16 | 0 | 0 | NA | NA | NA | Data collection tools; Defined dates for report submission (na aproved NTD data calendar), NTD epidemiological database | PC/NTDN | Only supervison of Municipal health authorities planned during Y3 in Uige, awaiting the technical guidelines and training curriculum for Health Staff by the MoH
|  | 2 - Train Provincial Supervisors on the data management system | [37 empty] | PM/SUP/NTDP
|  | 3 - Define a Supervision Guide for Municipal Health Teams | [36 empty] | Supervision guide | PC/NTDN
|  | 4 - Plan Monthly supervision visits to Municipal Health Teams | [36 empty] | Supervision dates (reflected in the Monthly Plan) | PM/NTDP
|  | 5 - Conduct Regular monthly supervisions to Municipal health teams | [36 empty] | Supervision Guides Filled and data analyzed | PM/SUP/NTDP
Output #4 | A2.4 -Produce and disseminate IEC materials | 1 - Produce IEC technical guidelines and get NTD Program approval . 1 Per HF |  | 145 | 48 | 121 | NA | NA | NA | 314 | UIG: 39; ZAI: 33; KS: NA; UIG: 38; ZAI: 10; KS: NA; UIG: 60; ZAI: 30; UIG: 12; ZAI: 22; KS: NA | Aproved IEC kits/guidelines/materials | PC/NTDN | Distribution of IEC materials for HF throught the WASHE trainging sessions in Huambo and Zaire / In Uige IEC materials provided through the NHS
|  | 2 - Print the approved guidelines | [8 empty] | HBO: 0; BIE: NA; KK: NA; HBO: 98; BIE: NA; KK: NA; HBO: 23; BIE: NA; KK: NA; KS: NA; HBO: 0; BIE: NA; KK: NA |  | PC/ML
|  | 3 - Deliver the guidelines | [36 empty] | IEC delivery form | PM/SUP/NTDP
Output #5 | A2.5 - Perform technical support supervisions and coaching on NTD case management, medicine stock and supply chain management and WASHE program implementation | 1 - Define a Supervision Guide for Health Units with NTDP National Program |  | 148 | 97 | 121 | NA | NA | NA | 366 |  | 24 | 26 | 0 | NA | NA | NA |  | 37 | 17 | 27 | NA | NA | NA |  | 54 | 15 | 81 | NA | NA | NA |  | 33 | 39 | 13 | NA | NA | NA | Health Unit Supervision Guide | PC/NTDN | 50% of health facilities supervised per year
|  | 2 - Train Provincial Supervisors on the use of Supervision Guide | [37 empty] | PM/SUP/NTDP
|  | 3 - Plan Monthly supervision visits to Health Units | [36 empty] | Clear dates for Supervision reflected in monthly plans | PM/NTDP
|  | 4 - Conduct Regular monthly supervisions to health units | [36 empty] | Filled Supervision guides | PM/SUP/NTDP
Objective 3 - The intensity of infection of schistosomiasis, lymphatic filariasis and intestinal worms (and potentially Onchocerciasis) in children, women and men reduced significantly from baseline. |  |  | LDA | UIG | ZAI | HBO | BIE | KUANDO KUBANGO | KWANZA SUL | TOTAL | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS
Output #1 | A 3.1 - Perform mapping studies for STH and Schistosomiasis in schools | 1 - Conclude mapping |  | NA | NA | NA |  |  |  | 0 | [29 empty] | PM/NTDP | Mapping not part of the Y3 activities | bar: UIG to HBO; UIG to HBO; UIG to HBO; UIG to HBO
|  | 2 - Produce mapping reports |  |  |  |  | NA | NA | NA | [29 empty] | 1 report per Province | JCF | bar: BIE to KS; BIE to KS; BIE to KS; BIE to KS
|  | 3 - Present mapping results at Provincial and National Level | [36 empty] | 1 Provincial meeting with Municipal authorities for results presentation | PC/PM/NTDP/NTDN
Output #2 | A 3.2 - Perform mapping studies for lymphatic filariasis in communities | 1 - Get LF tests from NTD National Program |  | NA | NA | NA |  |  |  | 0 | [29 empty] | PC/NTDN | Mapping not part of the Y3 activities | bar: UIG to HBO; UIG to HBO; UIG to HBO; UIG to HBO
|  | 2 - Train the teams for LF mapping in the field | [37 empty] | PC/JCF/NTDN
|  | 3 - Conduct mapping |  |  |  |  | NA | NA | NA | [30 empty] | PC/PM/SUP/NTDP | bar: BIE to KS; BIE to KS; BIE to KS; BIE to KS
|  | 3 - Produce mapping reports | [36 empty] | 1 report per Province | JCF
|  | 4 - Present results at provincial and National level | [36 empty] | 1 Provincial meeting with Municipal authorities for results presentation | PC/PM/NTDP/NTDN
Output #3.1.3&3.2.1 | A 3.3 - Conduct MDA in schools (includes Outputs 3.1.3 & 3.2.1) | 1 - Set a MDA calendar with all necessary procedures needed to be done in advance |  | 2 | 1 | 1 |  |  |  | 7 | UIG: 0.01; ZAI: 0; KS: 0; UIG: 1; ZAI: 1; KS: 0 | MDA calendar (national and provincial level) | PC/PM/NTDP/NTDN | School-based distribution campaigns of ALB and PZQ
|  | 2 - Collect data on the number of existing schools/classes and children |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 0 | 0 |  |  |  |  | 0 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | # Of schools/classes/Students per municipality | PM/NTDP/MoE
|  | 3 - Draft a distribution Plan of Medicines/Data collection tools for each Municipality | [36 empty] | Plan of Medicines distribution | PM/NTDP/EM
Output #3.1.4-3.1.7 & 3.2.2-3.2.4 & 3.3.1-3.3.2 | A 3.4 - Conduct MDA in communities (includes Outputs 3.1.4-3.1.7 & 3.2.2-3.2.4 & 3.3.1-3.3.2) | 1 - Set a MDA calendar with all necessary procedures needed to be done in advance |  | 1 | 0 | 0 | 0 | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | MDA calendar (national and provincial level) | PC/PM/NTDP/NTDN | Community-based distribution campaings of ALB, PZQ and IVM (5 municipalities in Uige)
|  | 2 - Collect data on the number of existing communes and population | [36 empty] | # Of communes/population per municipality | PM/NTDP
|  | 3 - Draft a distribution Plan of Medicines/Data collection tools for each Municipality | [36 empty] | Plan of Medicines distribution | PM/NTDP/EM
|  | 4 - Prepare MDA logistics (Copies/materials (Dose Poles)/funds (For trainings and Supervision) | [37 empty] | PC/NTDN/ML
Output #3.4.1 | A3.5 - Provide Annual basic NTD training to Provincial and municipal coordinators and education area coordinators | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan |  | 64 | 12 | 12 | 18 | 18 | 22 | 146 |  | 0 | 0 | 12 | 0 | 0 | 0 |  | 32 | 12 | 0 | 18 | 18 | 0 |  | 0 | 0 | 0 | 0 | 0 | 22 |  | 32 | 0 | 0 | 0 | 0 | 0 | Workplan with trainings dates | PC/NTDP | Trainings for MDA campaings for health officials per province
|  | 2 - Inform Provincial and Municipal Authorities about the training dates (inform with letter - MoH and MoE) | [37 empty] | PC
|  | 3 - Prepare training logistics (training materials and catering) | [37 empty] | PC/ML
|  | 4 - Deliver the training | [36 empty] | Attendance Spreadsheet filled | PM/SUP/NTDP
Output #3.4.2 | A3.6 - Provide annual basic NTD training to teachers and school directors of MDA supported schools | 1 - Plan with MDA provincial coordinators |  | 4332 | 516 | 2028 | TBD | TBD | TBD | 6876 |  | 0 | 0 | 2028 | 0 | 0 | 0 |  | 2166 | 516 | 0 | TBD | TBD | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD |  | 2166 | 0 | 0 | 0 | 0 | 0 | Attendance Spreadsheet filled | PM/PC/NTDP | Trainings for MDA campaings for education staff (teachers and/or school directors), per provinces.
|  | 2 - Supervise the deliverance of the trainings | [36 empty] | Training Report | PM/NTDP
Output #3.4.2 | A3.6 - Provide annual basic NTD training to Community Drug Distributors | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan |  | 797 | NA | NA | NA | TBD | NA | 797 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 797 | 0 | 0 | 0 | TBD | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Workplan with trainings dates | PC/NTDP | Trainings for community-based MDA campaign (5 municipalities in Uige)
|  | 2 - Select and register CDD in each municipality | [36 empty] | List with CDD names and contacts per municipality | PC/NTDP/PM/SUP/LA/COM
|  | 3 - Inform Provincial and Municipal Authorities about the training dates (inform with letter) | [37 empty] | PC
Objective 4 - WASHE is integrated into school curriculum and hand washing with soap increased significantly from baseline |  |  | LDA | UIG | ZAI | HBO | BIE | KUANDO KUBANGO | KWANZA SUL | TOTAL | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS | LDA | UIG | ZAI | HBO | BIE | KK | KS
Output #1 | A4.1 - Conduct a KAP study on NTD transmission and WASH Practices | 1 - Draft KAP Survey ToR |  | NA | NA | NA | NA | NA | NA | NA | [28 empty] | ToR for KAP survey | MHQ | KAP survey implemented during Y2 | bar: UIG to KS; UIG to KS; UIG to KS; UIG to KS
|  | 2 - Recruit a KAP survey consultant | [36 empty] | Consultant hired | MHQ
|  | 3 - KAP survey elaboration (Survey instruments & data collectors training) | [36 empty] | Data collection tools and survey design | KAPC
|  | 4 - Conduct the KAP survey | NA | [36 empty] | KAPC/PC/PM/SUP
|  | 5 - Deliver the KAP survey report | [36 empty] | KAP survey report | KAPC
|  | 6 - Present the survey reports at National and Provincial Levels (Output 4.1.5) | [36 empty] | 1 meeting/province | KAPC/PC/NTDP
Output #2 | A4.2 - Assess the condition and current Provision of WASHE facilities in schools in the operational area | 1 - Conduct the assessment (done with mapping) | NA | NA | NA | NA | NA | NA | NA | NA | [30 empty] | Part of NTD mapping and KAP survey | bar: UIG to KS; UIG to KS; UIG to KS; UIG to KS
|  | 2 - Finalize the report | [36 empty] | Report of WASH conditions in schools | PC/JCF
Output #3 | A4.3 - Undertake hygiene information, education and communication interventions in schools targeting priority NTD | 1 - Define WASHE strategy to implement in schools |  | 489 | 258 | 607 |  |  |  | 1354 | UIG: 75; ZAI: 65; HBO: 118; UIG: 99; ZAI: 27; HBO: 364; UIG: 237; ZAI: 109; HBO: 127; UIG: 78; ZAI: 57; HBO: 0 |  | WC | Training sessions for one health activitist per school , inlcuding distribution of IEC package for schools.
|  | 2 - Develop WASHE tools and strategies | NA |  |  |  | NA | NA | NA | [30 empty] | WC | bar: BIE to KS; BIE to KS; BIE to KS; BIE to KS
|  | 3 - Develop a WASHE workplan for the 3 Provinces | [36 empty] | Workplans | WC
|  | 4 - Put in place WASHE defined strategy | [37 empty] | WC
Output #4 | A4.4 -Distribute, replenish or replace hygiene kits to all schools annually when IEC interventions are carried out | 1 - Define Hygiene kits content | NA | 489 | 258 | 610 | NA | NA | NA | 1357 |  | 75 | 65 | 118 | NA | NA | NA |  | 99 | 27 | 365 | NA | NA | NA |  | 237 | 109 | 127 | NA | NA | NA |  | 78 | 57 | 0 | NA | NA | NA | List of items to be purchased | PC/WC/NTDN | Hygine kits to be distributed to all schools.
|  | 2 - Procure Kit elements | [37 empty] | WC/ML
|  | 3 - Pack the kits | [36 empty] | Packed kits in stock | WC/ML
|  | 4 - Draft a kit distribution plan according to priorities | [36 empty] | Distribution Plan | WC/PC/PM
|  | 5 - Put in place kit distribution | [37 empty] | PM/SUP/NTDT/MoE
Output #5 | A4.5 - Provide information from all WASH assessment reports to provincial Ministry of Education officials | 1 - Organize and implement official results presentation meetings to present results | NA | 4 | 4 | 4 | NA | NA | NA | 12 | [28 empty] | 1 meeting/province | PC/NTDP | DPS to provide activitie reports to DPE | bar: UIG to KS; UIG to KS; UIG to KS; UIG to KS
| A4.6 - Perform joint supervisions with DPS and DPE on the WASHE programme implementation in the schools of the targeted municipalities | 1 - Plan with supervisions of the schools and HFs in the targeted municipalities with DPS and DPE coordinators | NA | 148 | 97 | 121 | NA | NA | NA | 366 | NA | 24 | 26 | 0 | NA | NA | NA | NA | 37 | 17 | 27 | NA | NA | NA | NA | 54 | 15 | 81 | NA | NA | NA | NA | 33 | 39 | 13 | NA | NA | NA | Supervison reports per province | PM/NTDP /DPS/DPE | One joint supervision of one week on the WASHE programme implementation per municipality
2 - Supervise the implementation of the WASHE trainings, use of IEC and Hygiene kits
KEY
| PC - Program Coordinator | ML - MENTOR Logistics
| PM - Program manager | DC - Data Clercks
| SUP - Supervisors | LA - Local Authorities
| NTDP - NTD Provincial Programs | COM - Communities
| NTDN - NTD National Program | MHQ - MENTOR HQ
| MoE - Ministry of Education Officials | WC - WASHE Coordinator
EM - Essential Medicines program

## Activity calender Y3
| Activity calender Y3 |  | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | 2015-04-01 |  |  |  |  | 2015-05-01 |  |  |  | 2015-06-01 |  |  |  | 2015-07-01 |  |  |  |  | 2015-08-01 |  |  |  | 2015-09-01 |  |  |  | 2015-10-01 |  |  |  |  | 2015-11-01 |  |  |  | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01
|  | Location | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Objective 1 sustainable National NTD programme | A1.1 - Planning and Coordination Meetings at National and Provincial Level
A1.2 - Provide Tecnical Support for National and Provincial levels to deliver workplans and to the implementation of the programme
| A1.3 - Provide logistical support to provincial and national NTD teams | NA | bar: 2015-04-01 1
A1.4 - To organize regular meetings to accuratelly analyse the NTD burden data
A1.5 - Data report handing over in time | bar: 2015-04-01 2; 2015-05-01 2; 2015-06-01 2; 2015-07-01 2; 2015-08-01 2; 2015-09-01 2; 2015-10-01 2; 2015-11-01 2; 2015-12-01 2; 2016-01-01 2; 2016-02-01 2; 2016-03-01 2
A1.6 - Organize specific meetings targeting NTD drug supply for MDA and health facilities
Objective 2 Integration in PHC | A2.1 - Organize training sessions of health workers on the prevention, management of NTD and WASHE, in 50% of the municipalities per province. | Huambo | bar: 2015-07-01 1; 2015-08-01 1; 2015-09-01 1 to 2015-09-01 2; 2015-10-01 1; 2015-11-01 1
Uige | bar: 2015-04-01 1 to 2015-04-01 2; 2015-05-01 1; 2015-05-01 3; 2015-07-01 1 to 2015-07-01 2; 2015-08-01 2; 2015-08-01 4; 2015-10-01 3 to 2015-10-01 4; 2015-11-01 3 to 2015-12-01 2; 2016-03-01 1 to 2016-03-01 2
Zaire | bar: 2015-05-01 1; 2015-09-01 1 to 2015-09-01 2; 2016-01-01 1 to 2016-01-01 2
| A.2.2 - Produce technical guidelines and training curriculum and disseminate to Health Facilities | NA | bar: 2015-04-01 1
| A2.3 - Perform joint technical supervisions with Provincial NTD coordinators to municipal health departments on NTD data collection and analysis | Uige | bar: 2015-04-01 1; 2015-05-01 1; 2015-06-01 1; 2015-07-01 1; 2015-08-01 1; 2015-09-01 1; 2015-10-01 1; 2015-11-01 1; 2015-12-01 1; 2016-01-01 1; 2016-02-01 2; 2016-03-01 1
| A2.4 -Produce and disseminate IEC materials | Huambo | bar: 2015-07-01 1; 2015-08-01 1; 2015-09-01 1 to 2015-09-01 2; 2015-10-01 1; 2015-11-01 1
Uige | bar: 2015-04-01 1 to 2015-04-01 2; 2015-05-01 1; 2015-05-01 3; 2015-07-01 1 to 2015-07-01 2; 2015-08-01 2; 2015-08-01 4; 2015-10-01 3 to 2015-10-01 4; 2015-11-01 3 to 2015-12-01 2; 2016-03-01 1 to 2016-03-01 2
Zaire | bar: 2015-05-01 1; 2015-09-01 1 to 2015-09-01 2; 2016-01-01 1 to 2016-01-01 2
| A2.5 - Perform technical support supervisions and coaching on NTD case management, medicine stock and supply chain management | NA | bar: 2015-04-01 1
Objective 3 MDA | A 3.1 - Perform mapping studies for STH and Schistosomiasis in schools | NA | bar: 2015-04-01 1
| A 3.2 - Perform mapping studies for lymphatic filariasis in communities | NA | bar: 2015-04-01 1
| A 3.3 - Conduct MDA in schools (includes Outputs 3.1.3 & 3.2.1) | Huambo | bar: 2015-05-01 3 to 2015-05-01 4
Uige | bar: 2015-06-01 3 to 2015-06-01 4; 2016-02-01 3 to 2016-02-01 4
Zaire | bar: 2015-08-01 3 to 2015-08-01 4
Bie | bar: 2015-07-01 3 to 2015-07-01 5
K Cubango | bar: 2015-08-01 3 to 2015-08-01 4
Kwanza Sul | bar: 2015-09-01 3 to 2015-09-01 4
| A 3.4 - Conduct MDA in communities (includes Outputs 3.1.4-3.1.7 & 3.2.2-3.2.4 & 3.3.1-3.3.2) | Uige | bar: 2015-08-01 3 to 2015-08-01 4
K Cubango | bar: 2015-08-01 3 to 2015-08-01 4
| A3.5 - Provide Annual basic NTD training to Provincial and municipal coordinators and education area coordinators | Huambo | bar: 2015-05-01 1 to 2015-05-01 2; 2016-02-01 1 to 2016-02-01 2
Uige | bar: 2015-06-01 1 to 2015-06-01 2
Zaire | bar: 2015-08-01 1 to 2015-08-01 2
Bie | bar: 2015-07-01 1 to 2015-07-01 2
K Cubango | bar: 2015-08-01 1 to 2015-08-01 2
Kwanza Sul | bar: 2015-09-01 1 to 2015-09-01 2
| A3.6 - Provide annual basic NTD training to teachers and school directors of MDA supported schools | Huambo | bar: 2015-05-01 1 to 2015-05-01 2
Uige | bar: 2015-06-01 1 to 2015-06-01 2
Zaire | bar: 2015-08-01 1 to 2015-08-01 2
Bie | bar: 2015-07-01 1 to 2015-07-01 2
K Cubango | bar: 2015-08-01 1 to 2015-08-01 2
Kwanza Sul | bar: 2015-09-01 1 to 2015-09-01 2
| A3.6 - Provide annual basic NTD training to Community Drug Distributors | Uige | bar: 2015-08-01 1 to 2015-08-01 2; 2015-09-01 1 to 2015-09-01 2
K Cubango | bar: 2015-08-01 1 to 2015-08-01 2
Objective 4 WASHE | A4.1 - Conduct a KAP study on NTD transmission and WASH Practices | NA | bar: 2015-04-01 1
| A4.2 - Assess the condition and current Provision of WASHE facilities in schools in the operational area | NA | bar: 2015-04-01 1
| A4.3 - Undertake hygiene information, education and communication interventions in schools targeting priority NTD | Huambo | bar: 2015-06-01 3 to 2015-06-01 4; 2015-07-01 2 to 2015-07-01 3; 2015-08-01 2; 2015-09-01 3 to 2015-09-01 4; 2015-10-01 2; 2015-11-01 1
Uige | bar: 2015-04-01 4 to 2015-04-01 5; 2015-05-01 4; 2015-07-01 3 to 2015-07-01 4; 2015-08-01 1; 2015-08-01 3; 2015-10-01 1 to 2015-10-01 2; 2015-11-01 1 to 2015-11-01 3; 2015-12-01 3 to 2015-12-01 4; 2016-03-01 3 to 2016-03-01 4
Zaire | bar: 2015-05-01 2; 2015-09-01 3 to 2015-09-01 4; 2016-01-01 3 to 2016-01-01 4
| A4.4 -Distribute, replenish or replace hygiene kits to all schools annually when IEC interventions are carried out | Huambo | bar: 2015-06-01 3 to 2015-06-01 4; 2015-07-01 2 to 2015-07-01 3; 2015-08-01 2; 2015-09-01 3 to 2015-09-01 4; 2015-10-01 2; 2015-11-01 1
Uige | bar: 2015-04-01 4 to 2015-04-01 5; 2015-05-01 4; 2015-07-01 3 to 2015-07-01 4; 2015-08-01 1; 2015-08-01 3; 2015-10-01 1 to 2015-10-01 2; 2015-11-01 1 to 2015-11-01 3; 2015-12-01 3 to 2015-12-01 4; 2016-03-01 3 to 2016-03-01 4
Zaire | bar: 2015-05-01 2; 2015-09-01 3 to 2015-09-01 4; 2016-01-01 3 to 2016-01-01 4
| A4.5 - Provide information from all WASH assessment reports to provincial Ministry of Education officials | H-U-Z | bar: 2015-04-01 3; 2015-07-01 3; 2015-10-01 3; 2016-01-01 3
| A4.6 - Perform joint supervisions with DPS and DPS on the WASHE programme implementation in the schools and HFs of the targetted municpalities | Huambo | bar: 2015-08-01 3; 2015-10-01 3; 2015-11-01 3; 2015-12-01 2; 2016-01-01 1
Uige | bar: 2015-05-01 1; 2015-07-01 1; 2015-08-01 1; 2015-10-01 1; 2015-11-01 1; 2015-12-01 1; 2016-01-01 1; 2016-03-01 1
Zaire | bar: 2015-06-01 2; 2015-10-01 3; 2016-02-01 1

## Plano Huambo
PLANO WASHE PROGRAMA ET DMM HUAMBO Y3
Ano 1 2015-2016 (ENDfund Y3)
Huambo, Caala, Ucuma, Longonjo, Tchinjenge
| abril | maio | junho |  |  |  | julho |  |  |  | agosto |  |  |  | setembro |  |  |  | outobro |  |  |  | novembro |  |  |  | Dezembro |  |  |  | janeiro |  |  |  | fevereiro |  |  |  | marco
Principias actividades / municipio |  |  |  |  | Caala |  | Caala |  |  |  | Ucuma |  |  |  | Huambo |  |  |  | Tchinjenge |  |  |  | Longonjo
semana |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
formacao US DTN+ WASHE 2 dias | prep |  | 1: Preparação; Caala 1: 54; Ucuma 1: 28; Huambo 1: 57; Huambo 2: 57; Tchinjenge 1: 20; Longonjo 2: 26
formacao WASH +professores 3 dias |  |  | Caala 3: 59; Caala 4: 59; Caala 2: 59; Caala 3: 59; Ucuma 2: 60; Huambo 3: 93; Huambo 4: 94; Tchinjenge 2: 52; Longonjo 1: 75
distribucao kits Higiene escolas | bar: Caala 3 to Caala 4; Caala 2 to Caala 3; Ucuma 2; Huambo 3 to Huambo 4; Tchinjenge 2; Longonjo 1
distribucao IEC escolas+US | bar: Caala 3 to Caala 4; Caala 2 to Caala 3; Ucuma 2; Huambo 3 to Huambo 4; Tchinjenge 2; Longonjo 1
supervisao US + escolas |  |  | Ucuma 3: Caala; Tchinjenge 3: Ucuma; Longonjo 3: Hbo; Longonjo 2: Tchin; Longonjo 1: Long
Distribucao ALB+PZQ 6 municipios
Huambo, Longonjo, Ucuma, Caala, Tchinjenge, Tchicala Choloanga
Caala: 236 escolas / 27 US |  |  | 1: Formacoes 2015-2016; Ucuma 3: Total
Ucuma : 60 escolas / 14 US |  | Professores | 1: Caala; Caala 3: Ucuma; Caala 1: Hbo; Caala 3: Chinj; Ucuma 1: Long
Huambo: 187 escolas / 57 US |  |  | 1: 236; Caala 3: 60; Caala 1: 186; Caala 3: 52; Ucuma 1: 75; Ucuma 3: 609
Tchinjenge: 52 escolas / 10 US |  | Technicos de saude | 1: Caala; Caala 3: Ucuma; Caala 1: Hbo; Caala 3: Chinj; Ucuma 1: Long
Longonjo : 75 escolas / 13 US |  |  | 1: 54; Caala 3: 28; Caala 1: 114; Caala 3: 20; Ucuma 1: 26; Ucuma 3: 242
Total schools: 610
Total schools: 97
Ano 2 (END Fund year4)
Ecunha, Mungo, Cachiungo, Bailundo, Chicala Tchonogola, Londumbali.

## Plano Uige
PLANO WASHE PROGRAMA ET DMM UIGE Y3
Y3
Songo, Ambuila, Bembe, Quitexe, Negage, Sanza Pombo, Damba.
[6 empty] | Q1 | [11 empty] | Q2 | [11 empty] | Q3 | [11 empty] | Q4
| 2015-04-01 |  |  |  | 2015-05-01 |  |  |  | 2015-06-01 |  |  |  | 2015-07-01 |  |  |  | 2015-08-01 |  |  |  | 2015-09-01 |  |  |  | 2015-10-01 |  |  |  | 2015-11-01 |  |  |  | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01
| Songo |  |  |  | Ambuila |  |  |  | MDA |  |  |  | Bembe |  |  |  | Quitexe |  |  |  | MDA |  |  |  | Mucaba |  |  |  | Sanza Pombo |  |  |  | Damba | [7 empty] | MDA |  |  |  | Buenge
Semana | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Formação US DTN + WASH 2 dias | 24 | 24 |  |  | 15 |  | 15 | [5 empty] | 22 | 22 |  |  |  | 16 |  | 16 | [6 empty] | 15 | 14 |  |  | 24 | 24 | 21 | 21 | [10 empty] | 12 | 12
Formação WASH + Professores |  |  | 28 | 28 |  |  |  | 19 | [6 empty] | 21 | 23 | 27 |  | 28 | [5 empty] | 21 | 21 |  |  | 39 | 39 | 39 |  |  |  | 39 | 39 | [10 empty] | 39 | 39
Distribuição Kits Higiene Escolas
Distribuição IEC Escolas + US
Supervisão US + Escolas |  |  |  |  | Songo | [7 empty] | Ambuila |  |  |  | Bembe | [7 empty] | Quitexe |  |  |  | Mucuba |  |  |  | Pombo |  |  |  | Damba | [7 empty] | Buenge
FORMAÇÕES - 2015/2016
| Professores | [5 empty] | Songo |  | Ambuila |  | Bembe |  | Quitexe |  | Mucaba |  | Sanza Pombo |  | Damba |  | Buenge |  | Total
Songo: 56 Escolas / 24 US | [6 empty] | 56 |  | 19 |  | 44 |  | 55 |  | 42 |  | 117 |  | 78 |  | 78 |  | 489
Ambuila: 19 Escolas / 15 US | Técnicos de Saúde | [5 empty] | Songo |  | Ambuila |  | Bembe |  | Quitexe |  | Mucaba |  | Sanza Pombo |  | Damba |  | Buenge |  | Total
Bembe: 44 Escolas / 22 US | [6 empty] | 48 |  | 30 |  | 44 |  | 32 |  | 29 |  | 48 |  | 42 |  | 24 |  | 297
Quitexe: 55 Escolas / 16 US | Mentor
Mucaba: 42 Escolas / 15 US
S. Pombo: 117 Escolas / 23 US
Damba: 78 Escolas / 21 US
Buenge: 78 Escolas/12 US
Escolas: 489
US: 148

## Plano Zaire
PLANO WASHE PROGRAMA ET DMM ZAIRE Y3
Ano 1
| Abril-15 |  |  |  | Maio-15 |  |  |  | Juno-15 |  |  |  | 2015-07-01 |  |  |  | 2015-08-01 |  |  |  | 2015-09-01 |  |  |  | Outo-15 |  |  |  | 2015-11-01 |  |  |  | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | Fevr-16 |  |  |  | 2016-03-01
[5 empty] | MBC |  |  |  | Noqui | [7 empty] | MDA |  |  |  | N´zeto |  |  |  | Kuimba |  |  |  | Tomboco | [11 empty] | Soyo
Semana | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Formação US DTN + WASH 3 dias |  |  |  |  | 26 | 26 |  |  |  |  | 14 | [9 empty] | 10 | 10 |  |  | 15 | 15 |  |  |  |  | 15 | 15 | [8 empty] | 24 | 24
Formação WASH + Professores | [6 empty] | 17 | 16 |  |  |  | 32 | [10 empty] | 27 |  |  |  | 29 | 29 | 25 | 26 | [12 empty] | 28 | 29
Distribuição Kits Higiene Escolas
Distribuição IEC Escolas + US
Supervisão US + Escolas | [8 empty] | MBC |  |  |  | Nq | [10 empty] | Nz | [8 empty] | Kuimba |  |  |  | Tomboco | [7 empty] | Soyo
MDA ALB+PZQ (6 municipios)
[11 empty] | FORMAÇÕES - 2015 | [11 empty] | Total
[5 empty] | Professores | [5 empty] | Soyo |  | Noqui |  | Nzeto |  | Kuimba |  | Tomb. |  | MBC
N´zeto: 27 Escolas / 10 US | [10 empty] | 57 |  | 32 |  | 27 |  | 58 |  | 51 |  | 33 |  | 258
Kuimba: 58 Escolas / 15 US |  |  |  |  | Técnicos de Saúde | [5 empty] | Soyo |  | Noqui |  | Nzeto |  | Kuimba |  | Tomb. |  | MBC
Soyo: 57 Escolas / 24 US | [10 empty] | 48 |  | 14 |  | 20 |  | 30 |  | 30 |  | 52 |  | 194
Noqui: 32 Escolas / 7 US
Tomboco: 51 Escolas / 15 US
MBC: 33 Escolas / 26 US
Total schools: 258
Total schools: 97