## WORKPLAN UIGE 5YEARS
UIGE Work Plan Matrix April 2012 / March 2016
Y2012 |  |  |  |  | Y2013 |  |  |  |  | Y2014 |  |  |  |  | Y2015 |  |  |  |  | Y2016
Key Activities by QUARTERS | Q1 | Q2 | Q3 | Q4 | Key Activities by QUARTERS | Q1 | Q2 | Q3 | Q4 | Key Activities by QUARTERS | Q1 | Q2 | Q3 | Q4 | Key Activities by QUARTERS | Q1 | Q2 | Q3 | Q4 | Key Activities by QUARTERS | Q1 | Q2 | Q3 | Q4
1/ Strengthen and reinforce the technical capacity of MOH health staff in targeted facilities to effectively implement malaria control activities.
1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | x | x |  |  | 1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | x |  |  |  | 1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | x | x |  |  | 1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | x | x |  |  | 1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | x | x
2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | x | x | x | x | 2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | x | x | x | x | 2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | x | x | x | x | 2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | x | x | x | x | 2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | x | x | x | x
2/ Improve the operational capacity of laboratory services for malaria through quality assurance (QA).
1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | x | x |  |  | 1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | x |  |  |  | 1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | x |  |  |  | 1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | x |  |  |  | 1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | x
2) Complete assesment of the labs in the province | x |  |  |  | 2) Complete assesment of the labs in the province | x |  |  |  | 2) Complete assesment of the labs in the province | x |  |  |  | 2) Complete assesment of the labs in the province | x |  |  |  | 2) Complete assesment of the labs in the province | x
3) Provide quality control of microscopy at individual health facilities labs, twice | x | x | x | x | 3) Provide quality control of microscopy at individual health facilities labs, twice | x | x | x | x | 3) Provide quality control of microscopy at individual health facilities labs, twice | x | x | x | x | 3) Provide quality control of microscopy at individual health facilities labs, twice | x | x | x | x | 3) Provide quality control of microscopy at individual health facilities labs, twice | x | x | x | x
4) Provide 2-days on-the-job training for laboratory diagnosis | x | x | x | x | 4) Provide 2-days on-the-job training for laboratory diagnosis | x | x | x | x | 4) Provide 2-days on-the-job training for laboratory diagnosis | x | x | x | x | 4) Provide 2-days on-the-job training for laboratory diagnosis | x | x | x | x | 4) Provide 2-days on-the-job training for laboratory diagnosis | x | x | x | x
5) To check and report reagents/consumables gaps in all provincial labs twice | x | x | x | x | 5) To check and report reagents/consumables gaps in all provincial labs twice | x | x | x | x | 5) To check and report reagents/consumables gaps in all provincial labs twice | x | x | x | x | 5) To check and report reagents/consumables gaps in all provincial labs twice | x | x | x | x | 5) To check and report reagents/consumables gaps in all provincial labs twice | x | x | x | x
3/ Strengthen the provincial Health Management Information System (HMIS) and Pharmaceutical System.
1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | x | x | x | x | 1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | x | x | x | x | 1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | x | x | x | x | 1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | x | x | x | x | 1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | x | x | x | x
2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | x | x | x | x | 2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | x | x | x | x | 2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | x | x | x | x | 2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | x | x | x | x | 2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | x | x | x | x
3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | x | x | x | x | 3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | x | x | x | x | 3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | x | x | x | x | 3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | x | x | x | x | 3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | x | x | x | x
4/ Improve the knowledge, attitudes, and practices of the target communities with respect to health seeking behavior, malaria prevention and treatment, AM-LUM as the first-line malaria treatment and danger of malaria in pregnancy
1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | x | x | x | x | 1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | x | x | x | x | 1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | x | x | x | x | 1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | x | x | x | x | 1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | x | x | x | x
2) Distribute IEC materials to community meeting areas and health facilities | x | x | x | x | 2) Distribute IEC materials to community meeting areas and health facilities | x | x | x | x | 2) Distribute IEC materials to community meeting areas and health facilities | x | x | x | x | 2) Distribute IEC materials to community meeting areas and health facilities | x | x | x | x | 2) Distribute IEC materials to community meeting areas and health facilities | x | x | x | x
5/ Increase availability and accessibility to malaria services
1) To perform one supervision visit to assess the Health System 200 HFs | x | x |  |  | 1) To perform one supervision visit to assess the Health System 200 HFs | x |  |  |  | 1) To perform one supervision visit to assess the Health System 200 HFs | x |  |  |  | 1) To perform one supervision visit to assess the Health System 200 HFs | x |  |  |  | 1) To perform one supervision visit to assess the Health System 200 HFs | x
2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | x | x |  |  | 2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | x | x | x | x | 2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | x | x | x | x | 2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | x | x | x | x | 2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | x | x | x | x
3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | x | x | x | x | 3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | x | x | x | x | 3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | x | x | x | x | 3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | x | x | x | x | 3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | x | x | x | x
4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | x | x | x | x | 4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | x | x | x | x | 4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | x | x | x | x | 4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | x | x | x | x | 4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | x | x | x | x
5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | x | x | x | x | 5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | x | x | x | x | 5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | x | x | x | x | 5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | x | x | x | x | 5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | x | x | x | x
6) Provide support at DPS level in reinforcing EDs team and ACT distribution | x | x | x | x | 6) Provide support at DPS level in reinforcing EDs team and ACT distribution | x | x | x | x | 6) Provide support at DPS level in reinforcing EDs team and ACT distribution | x | x | x | x | 6) Provide support at DPS level in reinforcing EDs team and ACT distribution | x | x | x | x | 6) Provide support at DPS level in reinforcing EDs team and ACT distribution | x | x | x | x
7) Analyze supervision data and plan programming accordingly | x | x | x | x | 7) Analyze supervision data and plan programming accordingly | x | x | x | x | 7) Analyze supervision data and plan programming accordingly | x | x | x | x | 7) Analyze supervision data and plan programming accordingly | x | x | x | x | 7) Analyze supervision data and plan programming accordingly | x | x | x | x
8) Conduct an evaluation of the quality of lab diagnosis in the province | x |  |  |  | 8) Conduct an evaluation of the quality of lab diagnosis in the province | x |  |  |  | 8) Conduct an evaluation of the quality of lab diagnosis in the province | x |  |  |  | 8) Conduct an evaluation of the quality of lab diagnosis in the province | x |  |  |  | 8) Conduct an evaluation of the quality of lab diagnosis in the province | x
9) Accompaining two targeted municipality in producing master plan on Training & Supervision | x | x | x | x | 9) Accompaining two targeted municipality in producing master plan on Training & Supervision | x | x | x | x | 9) Accompaining two targeted municipality in producing master plan on Training & Supervision | x | x | x | x | 9) Accompaining two targeted municipality in producing master plan on Training & Supervision | x | x | x | x | 9) Accompaining two targeted municipality in producing master plan on Training & Supervision | x | x | x | x
10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | x | x | x | x | 10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | x |  |  |  | 10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | x |  |  |  | 10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | x |  |  |  | 10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | x

## LOGFRAME UIGE FY2012
The MENTOR Initiative- Logical Framework UIGE FY2012
Objectives | Activities | Outputs | Indicators | EOPS (PY2012) | Means of Verification | Progress
1/ Strengthen and reinforce the technical capacity of MOH health staff in targeted facilities to effectively implement malaria control activities. | 1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis | 1) 64 Municipal officers with Basic Package malaria in NMCP guidelines for correct and appropriate management of cases of malaria, differential diagnosis | 1) # of initial trainings planned 4-day training as TOT at provincial level for 64 officers | 1) 64 officers trained as trainers that will organise trainings in the municipalities | 1) Activity records | Benchmark progress to be established by end of 2012
| 2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis | 2) 200 HWs received Basic package malaria in NMCP guidelines for correct and appropriate management of cases of malaria, differential diagnosis | 2) # of health staff trained on Malaria essentials and DD | 2) 200 health workers who received 2-day training | 2) Activity records | Benchmark progress to be established by end of 2012
2/ Improve the operational capacity of laboratory services for malaria through quality control QC | 1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities | 1) 15 Lab technicians with standardized training in confirmatory diagnosis of malaria with both RDT and microscopy | 1) # of formal lab technician trainings | 1) one tem-days formal trainings of 15 lab technicians each | 1) Activity records | Benchmark progress to be established by end of 2012
| 2) Complete assesment of the labs in the province | 2) 25 labs will be assess according to the lab. Assessment guideline | 2)# of labs that have been assessed | 2) 25 labs had the assessment done | 2) Activity records | Benchmark progress to be established by end of 2012
| 3) Provide quality control of microscopy at individual health facilities labs, twice | 3) Microscopy quality control checks conducted | 3) # of microscopy quality control checks conducted | 3) 500 control slides collected (25 labs * 2 technical coaching visits * 10 slides collected per visit) | 3) Supervision checklist from each visit with review of quality control | Benchmark progress to be established by end of 2012
| 4) Provide 2-days on-the-job training for laboratory diagnosis | 4) Lab technicians received on-the-job training in laboratory diagnosis | 4.1) # of laboratories who received on-the-job training in laboratory diagnosis 4.2) # of lab tech received OJT | 4) 50 lab technicians | 4) Lab supervision checklist from each session of two days with signatures of lab technicians trained | Benchmark progress to be established by end of 2012
| 5) To check and report reagents/consumables gaps in all provincial labs twice | 5) the labs having their reagents check twice | 5) # of labs that had their reagents stock checked twice | 5) 25 labs reagents stock checked twice | 5) Activity records | Benchmark progress to be established by end of 2012
3/ Strengthen the provincial and Municipal Pharmaceutical | 1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis | 1) two supportive visit to the RMS were performed | 1) # of supportive visits done | 1) two supportive visits per RMS were done | 1) Visit report signed by RMS officers | Benchmark progress to be established by end of 2012
| 2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits | 2) to monitoring visit performed in the USs were main gaps have been found (20% of targeted HFs) | 2) # of monitoring visits done | 2) two monitoring visits in 20% of HFs with main gaps were done | 2) Visit report signed by HFs chief | Benchmark progress to be established by end of 2012
| 3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs | 3) to facilitate MRS to perform reinforcing 1-day training in the weekest HFs | 3) # of 1-day reinforcing training performed by the RMS | 3) 40 reinforcing training have been performed at HFs level by RMS supported by Mentor | 3) Training report | Benchmark progress to be established by end of 2012
4/ Improve the knowledge, attitudes, and practices of the target communities with respect to health seeking behavior, malaria prevention and treatment, AM-LUM as the first-line malaria treatment and danger of malaria in pregnancy | 1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman | 1) Health education presentations carried out | 1) # of community health education presentations carried out. | 1) 115 community health education presentations | 1) Activity records | Benchmark progress to be established by end of 2012
| 2) Distribute IEC materials to community meeting areas and health facilities | 2) HFs and community centers supplied with IEC materials | 2) # of HFs and community centers supplied | 2) 28 HFs with ANC service were supplied with IEC materials | 2) Supervision kit index & IEC session activity records | Benchmark progress to be established by end of 2012
5/ Increase availability and accessibility to malaria services | 1) To perform one supervision visit to assess the Health System 200 HFs | 1) 200 HFs have been supervised and supervision guideline filed | 1) # of HFs that have been supervised | 1)200 HFs have been monitored and assess | 1)guideline supervision filled | Benchmark progress to be established by end of 2012
| 2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). | 2) 4 DPS and 64 officers of the RMS partecipate to the WS | 2)# DPS and official RMS will partecipate to plan activities and be aware of the administratives requirements for implementations. | 2) 64 DPS and RMS officers partecipated to the WS and make a master plan of Municipal training and supervising activities | 2) Report of activity | Benchmark progress to be established by end of 2012
| 3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan | 3) analisis and evaluation of DPS performances on malaria planed activities | 3) N. Supervision round on planed activity | 3) Positive trend to all the evaluation indicators | 3) Reports produced | Benchmark progress to be established by end of 2012
| 4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation | 4) analisis and evaluation of RMS performances on malaria planed activities | 4) N. Supervision round on planed activity; Coartem and TDR out of stoack; capacity to provide LLIBNs at antenatal-care service | 4) Positive trend to all the evaluation indicators | 4) Reports produced | Benchmark progress to be established by end of 2012
| 5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics | 5) 12 working sessions on Malaria datas and statistics realised with DPS | 5) # of monthly meetings attended | 5) 12 montlhy meetings and presentations realized | 5) Monthly presentation and DPS statistics plus meetings notes | Benchmark progress to be established by end of 2012
| 6) Provide support at DPS level in reinforcing EDs team and ACT distribution | 6) Respond positively at 50% DPS request for ACT &EDs distribution within Uige Munimicipality and management, and disponibilize 1 Mentor supervisor once per week at DPS warehouse | 6) # of DPS request received and answered positively and Nbre of days Mentor staff worked at DPS warehouse | 6) 50% of DPS request attented | 6) Logistics guides and staff timesheet | Benchmark progress to be established by end of 2012
| 7) Analyze supervision data and plan programming accordingly | 7) Improved knowledge of malaria case management quality in the province | 7) Positive trends on suspected-confermated-treated proportion | 7) One presentation produced | 7) Analysis presented to partners | Benchmark progress to be established by end of 2012
| 8) Conduct an evaluation of the quality of lab diagnosis in the province | 8) Improved knowledge of quality of laboratory diagnosis and guidance for interventions | 8) Positive trend on QC Coherence | 8) One presentation produced | 8) Analysis presented to partners | Benchmark progress to be established by end of 2012
| 9) Accompaining two targeted municipality in producing master plan on Training & Supervision | 9) master quarterly on RMS training, supervision and budget plan has been produced | 9) The targeted two municipalities have produced the master plans | 9) master plan presented at quarterly | 9) Analisis presented to partners | Benchmark progress to be established by end of 2012
| 10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months | 10)DPS in produced jointly with Mentor a quarterly master plan on training and supervision | 10) DPS produced two training and two supervision quarterly plans | 9) master plan presented at quarterly | 10) master plan analisis by Mentor & DPS presented to partners | Benchmark progress to be established by end of 2012
ACTIVITIES OVERVIEW
| ACTIVITIES | Target | # HR | # Days | # Training
| 1 Mentor-DPS-RMS supervision | 200HFs | 1DPS+2 RMS | 1x100 | 1
| WS | 64 MRS and 4 DPS | 68 | 1 | 1
| TOT malaria | 64 MRS | 64 | 4 | 3
| TRAINING Nurses/doctors | nurses (including HFs chief) | 200 | 2 | 8
| Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
| LAB training | Lab tech | 15 | 10 | 1
| Lab OJT | Lab tech | 50 | 2 | 25
| DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
| RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
| Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
| LAB CQ/supervision | HFs | 25x2 | 1 | NA
| LAB. Assessment (indipendent) | lab tech | 25 | 1 | NA
| HFs monitoring supervision 20% | HFs | 40 | 1 | NA
| RMS supervison HFs | HFs | 200x2 | 1 | NA

## ACTIVITIES OVERVIEW 5YEARS
ACTIVITIES OVERVIEW FY2012
ACTIVITIES | Target | # HR | # Days | # Training
1 Mentor-DPS-RMS supervision | 200HFs | 1DPS+2 RMS | 1x100 | 1
WS | 64 MRS and 4 DPS | 68 | 1 | 1
TOT malaria | 64 MRS | 64 | 4 | 3
TRAINING Nurses/doctors | nurses (including HFs chief) | 200 | 2 | 8
Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
LAB training | Lab tech | 15 | 10 | 1
Lab OJT | Lab tech | 50 | 2 | 25
DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
LAB CQ/supervision | HFs | 25x2 | 1 | NA
LAB. Assessment (indipendent) | lab tech | 25 | 1 | NA
HFs monitoring supervision 20% | HFs | 40 | 1 | NA
RMS supervison HFs | HFs | 200x2 | 1 | NA
2013
ACTIVITIES | Target | # HR | # Days | # Training
1 Mentor-DPS-RMS supervision
WS | 64 MRS and 4 DPS | 68 | 1 | 1
TOT malaria | 64 MRS | 64 | 4 | 3
TRAINING Nurses/doctors | nurses (including HFs chief) | 200 | 2 | 8
Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
LAB training | Lab tech | 15 | 10 | 1
Lab OJT | Lab tech | 25 | 1 | 25
DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
LAB CQ/supervision | HFs | 25x2 | 1 | NA
LAB. Assessment (indipendent) | lab tech | 25 | 1 | NA
HFs monitoring supervision 20% | HFs | 40 | 1 | NA
RMS supervison HFs | HFs | 300 | 1 | NA
2014
ACTIVITIES | Target | # HR | # Days | # Training
1 Mentor-DPS-RMS supervision
WS | 64 MRS and 4 DPS | 68 | 1 | 1
TOT malaria | 64 MRS | 64 | 4 | 3
TRAINING Nurses/doctors | nurses (including HFs chief) | 300 | 1 | 12
Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
LAB training | Lab tech | 15 | 10 | 1
Lab OJT | Lab tech | 25 | 1 | 25
DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
LAB CQ/supervision | HFs | 25x2 | 1 | NA
LAB. Assessment (indipendent) | lab tech | 25 | 1 | NA
HFs monitoring supervision 20% | HFs | 40 | 1 | NA
RMS supervison HFs | HFs | 200 | 1 | NA
2015
ACTIVITIES | Target | # HR | # Days | # Training
1 Mentor-DPS-RMS supervision
WS | 64 MRS and 4 DPS | 68 | 1 | 1
TOT malaria | 64 MRS | 64 | 4 | 3
TRAINING Nurses/doctors | nurses (including HFs chief) | 200 | 1 | 8
Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
LAB training | Lab tech | 15 | 10 | 1
Lab OJT | Lab tech | 25 | 1 | 25
DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
LAB CQ/supervision | HFs | 25x2 | 1 | NA
LAB. Assessment (indipendent)
HFs monitoring supervision 20% | HFs | 40 | 1 | NA
RMS supervison HFs | HFs | 100 | 1 | NA
2016
ACTIVITIES | Target | # HR | # Days | # Training
1 Mentor-DPS-RMS supervision
WS | 64 MRS and 4 DPS | 68 | 1 | 1
TOT malaria | 64 MRS | 64 | 4 | 3
TRAINING Nurses/doctors | nurses (including HFs chief) | 100 | 1 | 4
Training HFs gaps | nurses (including HFs chief) | 40HFs | 1 | 40
LAB training | Lab tech | 15 | 10 | 1
Lab OJT | Lab tech | 25 | 1 | 25
DPS master plan training/ supervision coaching and monitor | DPS | 12 | 1 | NA
RMS master plan training/supervision coaching and monitor | RMS | 64 | 1 | 6
Target two municipalities coaching to budget plan and HIMS deep monitoring | RMS | 8 | 2 | 1
LAB CQ/supervision | HFs | 25x2 | 1 | NA
LAB. Assessment (indipendent) | lab tech | 25 | 1 | NA
HFs monitoring supervision 20% | HFs | 40 | 1 | NA
RMS supervison HFs

## CHRONO UIGE FY2012
Chronological framework UIGE Province FY2012
| April 2012 | May 2012 | June 2012 | July 2012 | August 2012 | September 2012 | October 2012 | November 2012 | December 2012 | January 2013 | February 2013 | March 2013
1/ Strengthen and reinforce the technical capacity of MOH health staff in targeted facilities to effectively implement malaria control activities.
1) Provide initial 4-days TOT to Municipal Malaria Focal point, ANC, EDs and Public Health officers on Malaria Essential and Differencial Diagnosis |  | x | x
2) Support and organise 2-days training with capacitated Municipal officers to 200 Municipal Nurses/Chiefs/doctors on Malaria Essential and differencial diagnosis |  | x | x | x | x | x | x | x | x | x | x | x
2/ Improve the operational capacity of laboratory services for malaria through quality assurance (QA).
1) Provide one 10-days formal training for 15 Lab technicians of all laboratories in the municipalities |  |  |  | x | x
2) Complete assesment of the labs in the province |  | x | x | x
3) Provide quality control of microscopy at individual health facilities labs, twice |  |  |  | x | x |  |  | x | x
4) Provide 2-days on-the-job training for laboratory diagnosis |  |  |  | x | x |  |  | x | x
5) To check and report reagents/consumables gaps in all provincial labs twice |  |  |  | x | x |  |  | x | x
3/ Strengthen the provincial Health Management Information System (HMIS) and Pharmaceutical System.
1) To complete two supportive visit to all municipalities RMS in order to guide, capacitate and monitor on correct implementation of supervision guideline on quarterly basis |  |  | x | x | x | x | x | x | x | x | x | x
2) To visit and monitor the HFs that showed to have gaps in the drugs management according to the RMS supervision visits |  |  | x | x | x | x | x | x | x | x | x | x
3) To facilitate RMS to provvide 1-day training on reinforce gaps management at weekest HFs |  |  | x | x | x | x | x | x | x | x | x | x
4/ Improve the knowledge, attitudes, and practices of the target communities with respect to health seeking behavior, malaria prevention and treatment, AM-LUM as the first-line malaria treatment and danger of malaria in pregnancy
1) Carry out health education presentations delivering key malaria messages at the ANC service during LLINs distribution to pregnant woman |  |  | x | x | x | x | x | x | x | x | x | x
2) Distribute IEC materials to community meeting areas and health facilities |  |  | x | x | x | x | x | x | x | x | x | x
5/ Increase availability and accessibility to malaria services
1) To perform one supervision visit to assess the Health System 200 HFs |  | x | x | x
2) Provides a one-day workshop on project presentation and planning for the 4 DPS provincial coordinators (Public Health, Essential Drugs, Malaria, ANC) and to 64 RMS municipals coordinators (Public Health, EDs, ANC, malaria focal point). |  |  | x | x | x
3) Assist and closely monitor DPS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation and budget operational master plan |  | x | x | x | x | x | x | x | x | x | x | x
4) Assist and closely monitor RMS services to ensure quality service delivery, data collection and reporting according to the master plan on Supervision and capacitation |  | x | x | x | x | x | x | x | x | x | x | x
5) Participate and reinforce the Monthly malaria meetings in datas presentation and statistics |  | x | x | x | x | x | x | x | x | x | x | x
6) Provide support at DPS level in reinforcing EDs team and ACT distribution |  | x | x | x | x | x | x | x | x | x | x | x
7) Analyze supervision data and plan programming accordingly |  | x | x | x | x | x | x | x | x | x | x | x
8) Conduct an evaluation of the quality of lab diagnosis in the province |  | x | x | x
9) Accompaining two targeted municipality in producing master plan on Training & Supervision |  | x | x | x | x | x | x | x | x | x | x | x
10) Accompaining DPS in producing a master plan on training and supervision and operational budeget plan every three months |  | x |  |  | x |  |  | x |  |  | x

## END Budget 2012
Donor categories | Donor code | Line | Description | Chart of Account code | Accounts code | Type of unit | Unit cost | ZAIRE |  |  | UIGE |  |  | Total
[8 empty] | Number of units | Total | Anticipated Other Contribution | Number of units | Total | Anticipated other Contribution | Number of units | Total | Total other contr.
| 01 |  | 1. INTERNATIONAL FIELD TEAM | 61
Personnel |  | 1A | Programme Coordinator 100% |  |  | Month | 3500 | 6 | 21000 |  | 6 | 21000 |  | 12 | 42000 | 0
Personnel |  |  | HQ Technical Support |  |  | Month | 4000 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 5000
Fringe benefits |  | 1B | In Country Living Allowance (ICLA) |  |  | Day | 22 | 165 | 3630 |  | 165 | 3630 |  | 330 | 7260 | 0
Fringe benefits |  | 5E | International Per Diem |  |  | Days | 50 | 2 | 100 |  | 2 | 100 |  | 4 | 200 | 0
Fringe benefits |  | 1C | Medical insurance |  |  | Month | 65 | 6 | 390 |  | 6 | 390 |  | 12 | 780 | 0
Travel |  | 5E | Visas / work permits |  |  | Expat | 535 | 1 | 535 |  | 1 | 535 |  | 2 | 1070 | 0
Fringe benefits |  | 1A | Relocation Allowance |  |  | Lumpsum | 300 | 0.5 | 150 |  | 0.5 | 150 |  | 1 | 300 | 0
Travel |  | 1D | Vaccinations and malaria prophylaxis |  |  | Month | 60 | 6 | 360 |  | 6 | 360 |  | 12 | 720 | 0
Other |  | 1B | Staff accommodation: rent, per diems travel |  |  | Month | 600 | 12 | 7200 |  | 12 | 7200 |  | 24 | 14400 | 0
Personnel |  | 1E | Technical Support |  |  | Lumpsum | 4500 |  |  | 10000 |  | 0 | 10000 | 0 |  | 20000
|  |  | 1. Sub-total | [5 empty] | 33365 | 12500 |  | 33365 | 12500 |  | 66730 | 25000
| 02 |  | 2. NATIONAL FIELD TEAM | 62 | [11 empty] | 0
Personnel |  | 2A | Project Manager (50% each province) |  |  | Month | 900 | 6 | 5400 |  | 6 | 5400 |  | 12 | 10800 | 0
Personnel |  | 2B | Logistician/Administrator base 100% |  |  | Month |  | 0 | 0 | 9600 | 0 | 0 | 9600 | 0 | 0 | 19200
Personnel |  | 2C | Technical Supervisors - MDA Campaign (1 per province) |  |  | Month | 700 | 12 | 8400 |  | 12 | 8400 |  | 24 | 16800 | 0
Personnel |  | 2D | Technical Supervisors - HF Training/Supply (1 per province) |  |  | Month | 700 | 12 | 8400 |  | 12 | 8400 |  | 24 | 16800 | 0
Personnel |  | 2E | Driver (50% each province) |  |  | Month | 450 | 6 | 2700 |  | 6 | 2700 |  | 12 | 5400 | 0
Personnel |  | 2E | Drivers/Mecanician |  |  | Month |  | 0 | 0 | 10800 | 0 | 0 | 10800 | 0 | 0 | 21600
Personnel |  | 2F | 3 Guards, 100% |  |  | Month |  |  | 0 | 11160 |  | 0 | 11160 | 0 | 0 | 22320
|  | 2G | Administrator/Finance |  |  | Month |  |  |  | 9600 |  |  | 9600 |  |  | 19200
Fringe benefits |  | 2H | Payroll taxes & social security (INSS) |  |  | Month | 220 | 12 | 2640 |  | 12 | 2640 |  | 24 | 5280 | 0
Fringe benefits |  | 2H | Personnel benefits- Christmas Bonus |  |  | Lumpsum | 1375 | 1 | 1375 |  | 1 | 1375 |  | 2 | 2750 | 0
Fringe benefits |  | 2H | Personnel benefits - Holiday Bonus |  |  | Lumpsum | 1375 | 1 | 1375 |  | 1 | 1375 |  | 2 | 2750 | 0
Fringe benefits |  | 2H | Personnel benefits - Severance National staff |  |  | Lumpsum | 2750 | 1 | 2750 |  | 1 | 2750 |  | 2 | 5500 | 0
Fringe benefits |  | 2H | Personnel benefits - Staff insurance |  |  | Lumpsum | 82.5 | 12 | 990 |  | 12 | 990 |  | 24 | 1980 | 0
Supplies |  | 2I | Daily workers |  |  | day | 100 | 30 | 3000 |  | 30 | 3000 |  | 60 | 6000 | 0
Fringe benefits |  | 2J | Training - capacity building |  |  | Lumpsum | 500 | 1 | 500 |  | 1 | 500 |  | 2 | 1000 | 0
|  |  | 2. Sub-total | [5 empty] | 37530 | 41160 |  | 37530 | 41160 | 0 | 75060 | 82320
| 03 |  | 3. OPERATIONAL EQUIPMENT & RUNNING COSTS | 63 | [11 empty] | 0
Other |  |  | Office rent |  |  | Month | 500 | 0 | 0 | 12000 | 0 | 0 | 12000 | 0 | 0 | 24000
Other |  | 3A | Office running costs (utilities and maintenance) |  |  | Month | 200 | 12 | 2400 |  | 12 | 2400 |  | 24 | 4800 | 0
Supplies |  | 3B | Office supplies, printing & copying |  |  | Month | 200 | 12 | 2400 |  | 12 | 2400 |  | 24 | 4800 | 0
Other |  | 3C | Communication equipment |  |  | Lumpsum | 1000 | 1 | 1000 |  | 1 | 1000 |  | 2 | 2000 | 0
Other |  | 3D | Communications running costs (telephone, sat phone, internet, courrier) |  |  | Month | 200 | 12 | 2400 |  | 12 | 2400 |  | 24 | 4800 | 0
Equipment |  | 3E | Computers, software, accessories, licences & maintenance |  |  | Lumpsum | 1000 | 2 | 2000 |  | 2 | 2000 |  | 4 | 4000 | 0
Equipment |  |  | Generator purchase |  |  | Lumpsum | 3000 |  | 0 | 3000 |  | 0 | 3000 | 0 | 0 | 6000
Other |  | 3F | Generator fuel |  |  | Month | 100 | 12 | 1200 |  | 12 | 1200 |  | 24 | 2400 | 0
Other |  | 3G | Bank charges |  |  | Month | 50 | 12 | 600 |  | 12 | 600 |  | 24 | 1200 | 0
Other |  | 3H | Audit fees |  |  | Lumpsum | 1000 | 0.5 | 500 |  | 0.5 | 500 |  | 1 | 1000 | 0
|  |  | 3. Sub-total | [5 empty] | 12500 | 15000 |  | 12500 | 15000 | 0 | 25000 | 30000
| 04 |  | 4. PROGRAMME Costs | 64 | [11 empty] | 0
|  |  | IRS - Spraying kits & clothing | 6402 |  | Lumpsum | 0 | 0 | 0 |  | 0 | 0 |  | #REF! | #REF! | 0
|  |  | Laboratory equipment: Microscopes, analysers & other | 6403 |  | Lumpsum | 0 | 0 | 0 |  | 0 | 0 |  | #REF! | #REF! | 0
Supplies |  | 4A | Stakeholder Quarterly meeting |  |  | Lumpsum | 4150 | 2 | 8300 |  | 2 | 8300 |  | 4 | 16600 | 0
|  |  | Logistical supplies - malaria control campaigns |  |  | Lumpsum | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
|  |  | Logistical supplies - other |  |  | Lumpsum | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Supplies |  | 4B | Visibility supplies (posters, pamphlets, shirts) |  |  | Lumpsum | 50 | 50 | 2500 |  | 60 | 3000 |  | 110 | 5500 | 0
Fringe benefits |  | 4C | Local travel/per diem/Lodging - national staff (50 HFs Zaire, 60 Uige) |  |  | Lumpsum | 50 | 50 | 2500 |  | 60 | 3000 |  | 110 | 5500 | 0
Supplies |  | 4C | Local travel/per diem - local collaborators (50 HFs Zaire, 60 Uige) |  |  | Lumpsum | 50 | 50 | 2500 |  | 60 | 3000 |  | 110 | 5500 | 0
|  |  | 4. Sub-total | [5 empty] | 15800 |  |  | 17300 |  | 0 | 33100 | 0
| 05 |  | 5. TRANSPORT - FLIGHTS - FREIGHT - STORAGE | 67 | [11 empty] | 0
Equipment |  | 5A | Vehicle Rent (2500/month @40% of grant) |  |  | month | 2500 | 5 | 12500 | 17500 | 5 | 12500 | 17500 | 10 | 25000 | 35000
Other |  | 5B | Vehicle insurance and taxes |  |  | Month | 300 | 5 | 1500 | 2100 | 5 | 1500 | 2100 | 10 | 3000 | 4200
Other |  | 5C | Vehicle maintenance, spare parts and repair (1 vehicle) |  |  | Month | 600 | 5 | 3000 | 4200 | 5 | 3000 | 4200 | 10 | 6000 | 8400
Other |  | 5D | Vehicle fuel (1 vehicles) |  |  | Month | 1000 | 8 | 8000 |  | 8 | 8000 |  | 16 | 16000 | 0
Travel |  |  | International freight, insurance & clearance |  |  | Month | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Travel |  | 5G | Local transport |  |  | Month | 50 | 12 | 600 |  | 12 | 600 |  | 24 | 1200 | 0
Other |  |  | Warehouse rent and maintenance |  |  | Month | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Travel |  | 5E | International flights |  |  | Flights | 2200 | 2 | 4400 |  | 2 | 4400 |  | 4 | 8800 | 0
Travel |  | 5F | National flights - Provincial travel |  |  | Flights | 150 | 6 | 900 |  | 6 | 900 |  | 12 | 1800 | 0
|  |  | 5. Sub-total | [5 empty] | 30900 | 23800 |  | 30900 | 23800 | 0 | 61800 | 47600
|  |  | Subtotal Programme Direct Costs |  |  |  |  | 130095 |  | 92460 | 131595 |  | 92460 | 261690 |  | 184920
|  |  | Indirect programme costs 15% |  |  | 0.15 |  | 19514.25 |  | 13869 | 19739.25 |  | 13869 | 39253.5 |  | 27738
|  |  | Total |  |  |  |  | 149609.25 |  | 106329 | 151334.25 |  | 106329 | 300943.5 |  | 212658

## Calculations
Regional Shareholder Coordination Meeting
Items | Nº of Persons | USD | No of Days | Costs
Per Diem Participants | 10 | 180 | 1 | 1800
Participants overland transport subsidy | 8 | 100 | 1 | 800
Participants air transport subsidy | 2 | 300 | 1 | 600
Facilitation subsidy | 0 | 0 | 0 | 0
Facilitator Transport Subsidy | 0 | 0 | 0 | 0
Per Diem Facilitator | 0 | 0 | 0 | 0
Coffee Break | 10 | 15 | 1 | 150
Lunch | 10 | 30 | 1 | 300
Didactic Material | 10 | 20 | 1 | 200
Room Rental | 1 | 200 | 1 | 200
Support Staff | 0 | 0 | 0 | 0
Fuel for car supporting | 0 | 0 | 0 | 0
Participants local transport subsidy | 10 | 10 | 1 | 100
Total |  |  |  | 4150
Routine Monitoring and Supervision (of all malaria control activities) - Quarterly Provincial to Municipal
Items | Nº of Persons | USD | No of HFs | Costs
Per Diem (1 MENTOR, 1 MoH) Zaire | 2 | 50 | 50 | 5000
Per Diem (1 MENTOR, 1 MoH) Uige | 2 | 50 | 60 | 6000
Total |  |  |  | 11000