## Africa
| Country Activity |  |  |  | 5-year strategy color code (wheat) |  |  | 5-year strategy color code (maize) |  |  | 5-year strategy color code (rice)
| 2012 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015
Blue countries
Egypt |  |  |  | Provide technical support
Ghana |  |  |  | Present at the West African Food Fortification training held by Muhlenchemie
Morocco |  |  | Work with GAIN to revitalize wheat fortification, and provide QA/QC training
Nigeria | Media campaign, visit country, and meet with partners | Media campaign |  | Provide technical support to FACT Nigeria survey training
South Africa |  | Hold workshop on the population-based Flour Fortification Program Monitoring and Surveillance System | Present at the Africa Network meeting coordinated by Smarter Futures, and meet with national leaders | Participate in the Africa Union New Partnership for Africa's Development nutrition technical consultative meeting
Green countries
Benin |  |  | Join training
Cote d'lvoire
Guinea
Lesotho | Advocate mandatory fortification, join training, and visit country |  |  | Join training
Malawi | Attend meeting, advocate mandatory fortification legislation and implementation, and visit country | Join training | Develope micronutrient strategy | Conduct maize landscape analysis, and join training
Mali |  |  | Join training
Mauritania
Mozambique |  | Join training |  | Join training, visit country, and meet with multiple partners
Senegal |  |  | Join training
Sudan |  |  | Join training
Swaziland | Attend meeting, advocate mandatory fortification legislation and implementation, and visit country |  |  | Join training
Tanzania | Attend meeting, advocate mandatory fortification legislation and implementation, and provide technical support to country and regional activities | Meet with partners, hold cost-economic benefit training workshop, and develope online resource using excel-based tool | Work on a proposal to DFID to do an industry assessment for maize mills, join the GIZ fortification workshop, and visit the East Central and South Africa Health Community offices | Conduct maize landscape analysis, present at the first Africa Birth Defects surveillance training, attend the Global Summit on Food Fortification, attend meetings related to fortification in East Africa, and meet with multiple partners
Togo |  |  | Join training | Join training
Yellow countries
Botswana |  | Visit country |  | Join training
Burkina Faso
Cameroon |  |  | Join the West African UEMOA fortification training | Join training
Democratic Rep. of Congo
Ethiopia | Attend World Bank's National Food Fortification Meeting and help with future agenda, povide technical support to country and regional activities, and conduct gap analysis to develop training curriculum for capacity building in food fortification | Attend steering committee meeting on national food fortification workshop, provide technical assistance, attend partners review meetings, and join training | Present at the Partners in Food Solutions fortification millers training program, and attend Ethiopia's National Fortification steering committee meeting
Kenya | Attend meeting, advocate mandatory fortification legislation and implementation, provide technical assistance in developing micronutrient monitoring guidelines, and attend the Kenya Annual Operation Plan | Join training |  | Conduct maize landscape analysis, participate in and provide technical support during the Muhlenchemie millers training, attend Kenya's National Food Fortification Conference, and meet with regional partners
Liberia |  |  |  | Join training
Namibia |  | Visit country |  | Join training
Rwanda |  | Join training |  | Join training
Sierra Leone
Uganda | Meet with Uganda HKI officer, attend meeting, advocate mandatory fortification legislation and implementation, review micronutrient guidelines with partners, attend the National Fortification Alliance and micronutrient technical group meeting, and review micronutrient guidelines | Attend the inauguration of Uganda National Working Group on Food Fortification, provide technical support to nutrition stakeholders, attend the National Fortification Alliance meeting, meet with SPRING team members, and join training; | Visit country, provid technical support, attend the National Working Group meeting, provide technical support to six mills, train Uganda National Bureau of Standards staff, and support Uganda's national working group | Conduct maize landscape analysis, participate in the Uganda training of bakeries and millers, Join the review of national fortification program held by the SPRING project, and participate in the development of a five-year plan
Red Countries
Algeria |  |  | Meet with partners and milling company officers, and follow up with industry leaders | Visit country
Angola
Burundi |  |  | Join training and form the National Fortification Alliance | Conduct maize landscape analysis and join training
Cape Verde
Central African Republic
Chad
Comoros
Congo
Djibouti |  |  | Join training, visit country, provide technical support and advocacy on drafting mandatory fortification of rice and pasta imports, follow up with the government on food needs and standards
Eritrea
Gabon
Gambia
Guinea Bissau
Libya
Madagascar
Mauritius | Attend meeting and advocate mandatory fortification legislation and implementation | Visit country and meet with leaders and nutritionists
Sao Tome and Principe
Seychelles
Tunisia
Zambia | Attend the East and Central Southern African Health Community meeting, visit country, and advocate mandatory fortification legislation and implementation |  | Visit country and track process of developing mandatory flour fortification standards | Conduct maize landscape analysis, meet with stakeholders related to QA/QC training, and join training
Zimbabwe | Visit country | Visit country, meet with regional WHO nutrition specialists, UNICEF officers, and the Ministry of Trade staff, and join training | Finish fortification strategy and develop draft standards | Conduct maize landscape analysis, attend meeting on food fortification, participate in the training of government analytical laboratory personnel, and hold QA/QC workshop
Grey countries
Equatorial Guinea
Niger |  |  |  | Join training
Somalia
Non-country specific activities
| 2012 | 2013 | 2014 | 2015
| Attend the Mideast/Africa meeting in Abu Dhabi, and provide technical support to East Central Southern African Health Community | Edit the final version of the Fortification Monitoring and Surveillance tool, provide QA/QC training for countries in WHO EMRO region, and start the Instant Noodle Shelf Life test funded by MI and Muhlenchemie | Publish a paper, send invitations for an Africa Network Meeting, and present at USAID-sponsored meeting held in Washington D.C. | Develope a maize milling scoping document and mapping tool for East Africa, present at the 7th meeting of the African Task Force on Food and Nutrition Development, establish new contacts with AkzoNobel, and develope terms for a rice supply chain analysis in West Africa
Color Code | Definition
Blue / purple | Over 75% of Industrial-milled flour fortified in country. FFI's main role is monitoring
Green | Confident country will move to 75% by January 2012. Targeted support as needed
Yellow | Organized efforts to increase fortification within country. Without support to fill gaps, moving to 75% unlikely
Red | No fortification activity in the country. Major support necessary to reach 75% fortification
Grey | Fortification of wheat and/or maize likely to have very limited health impact, or no data on country

## Asia Pacific
| Country Activity |  |  |  | 5-year strategy color code (wheat) |  |  | 5-year strategy color code (rice)
| 2012 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015
Priority I
Papua New Guinea (PNG) | Attend WHO Western Pacific Region regional committee meeting | Support and maintain rice fortification legislation, make connections with the Ministry of Health and local mills | Visit country and develop recommendations for implementations of flour fortification | Continue discussion on fortification and visit country to strengthen rice fortification program
Philippines | Attend the IAOM South East Asia meeting |  | Advocate fortification status and attend meeting | Present at a roundtable discussion on folic acid held by the National Academy of Science and Technology and also present at the Global Forum on Research and Innovation for Health 2015
Priority II | `
Afghanistan
Bangladesh | Visit country | Attend meeting and work with WFP on rice fortification | Attend meeting
Cambodia | Carry out fact-finding mission |  | Attend meeting
China | Visit country |  |  | Visit country and meet with fortification stakeholders
Maldives |  | Attend meeting
Nepal |  | Attend meeting | Attend meeting
New Zealand
Pakistan | Visit country, assess current fortification situation, and attend regional regulatory monitoring meeting | Visit country and discuss further support in the province of Pubjab, and work with partners as needed to support programs | Hold QA/QC training with GAIN and MI, and join training
Singapore | Visit country |  |  | Participate in the Regional Large Scale Food Fortification Consultation hosted by GAIN
Sri Lanka |  | Attend meeting | Attend meeting hosted by the National Nutrition Secretariat and present different policy options of rice fortification and attend meeting
Monitoring and Support
Fiji
Indonesia | Visit country and develop impact evaluations | Discuss to update flour standards, join meeting, and estimate contribution of fortification to hemoglobin levels | Visit country, attend meeting to discuss problems and recommendations with mandatory food fortification | Attend Grain and Feed Asia, meet with potential stakeholders, attend the Scaling Up Nutrition Business Network Asia Region meeting, and meet with delegates from 14 countries
Malaysia | Visit country, developed impact evaluations, and present at IAOM Asia district meeting
Mongolia | Visit country |  |  | Visit country to "restart" country level discussions on mandatory wheat flour fortification
Vietnam | Visit country and attend WHO Regional Committee Meeting of Ministers of Health | Attend the IAOM meeting and hold info session for Vietnamese millers |  | Visit country, provide feedback to the National Institute of Nutrition and technical support for drafting mandatory fortification decree, and meet with national stakeholders
Strategic Area of Focus
Myanmar |  | Attend meeting | Attend meeting
South Korea
Japan |  |  |  | Attend the Asian Congress of Nutrition and meet with stakeholders from the region
Taiwan
Thailand | Visit country | Attend meeting | Visit country and meet with the Thailand Birth Defects Association and nutrition community
Not prioritized in strategy
Solomon Islands |  |  | Approached by Australian government for helping the fortification program in Solomon Islands, FFI will advice and evaluate the impact of mandatory wheat fortification, visit country for fact finding and planning mission, and is in preparation for standards for rice fortification | Visit country, and attend the first Food Fortification National Committee meeting, provide ongoing support and training, and hold regulatory monitoring workshops and rapid assay show that rice has been fortified successfully
Non-country specific activities
| 2012 | 2013 | 2014 | 2015
|  | Conduct focus group research of the attendees of the WHO/GAIN rice meetings in Geneva last October to update them on integrating rice into FFI, visit Brunei for the first time, FFI Asia and WHO SEARO agree to develop a situation analysis on the status of preventative interventions for birth defects in the region, present flour fortification to the Interflour leadership team, meet with WHO South East Regional Office leaders and WFP colleagues, and develop a strategic paper for rice fortification | Attend WFP-hosted meeting to brainstorm for a regional meeting on rice fortification, send invitations for the regional rice fortification workshop, present at the "Scaling up Rice Fortification in Asia" meeting, and complete the instant noodles study | Work on rice fortification assay exercise with partners and learn rice fortification resources

## Europe
| Country Activity |  |  |  | 5-year strategy color code (wheat)
| 2012 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015
Priority I
Albania | Visit country, join workshop, follow up about needs, and develop QA/QC training | Develop communications strategy for partners to implement
Armenia | Join workshop and request communications campaign | Carry out a study tour to Canada and provide advocacy via e-mail | Meet with UNICEF representatives, provide technical support, suggest proactive communications in preparation for the fortification legislation hearing, and continue to support fortification campaigns | Continue to offer advocacy ideas and resources to the Ministry of Health and UNICEF country office, provide technical and communications support
Belarus
Bosnia and Herzegovina
Georgia | Join workshop, visit country, and follow up about need |  |  | Provide technical support to the UNICEF country office
Kosovo | Develop national monitoring plan, join workshop, and work with UNICEF Kosovo to develop a monitoring and evaluation plan | Start monitoring training for wheat flour fortification | Provide technical support
Republic of Macedonia | Join workshop, visit country, and follow up about need | Hold food control workshop
Moldova | Join workshop, visit country, and follow up about need, and requested for monitoring and evaluation and QA/QC training | Provide communications support (advocacy meetings/study tour)
Turkey | Attend the Turkish Wheat, Flour and Bread Congress and Exhibition, and hold two workshops | Attend IF Congress on Spina Bifida and Hydrocephalus, present on fortification as prevention and meet representatives from 20 IF member country delegations | Provide advocacy materials to the Spina Bifida Association in preparation for a meeting with the Ministry of Health | Support the Turkey IF member organization on flour campaign and provided contact information
Priority II
Azerbaijan | Visit country, conduct milling assessment, and join workshop | Conduct micronutrient survey and consult on the fortification of milk with Vitamin D | Visit country and receive status fortification on a UNICEF mission
Bulgaria
Germany |  | Lead a session on micronutrients at the Hidde Hunger Congress, partner with Folic Acid working group to advance fortification and give presentation | Present at the Teratology Society meeting and meet with nutrition experts to potentially build a coalition to support fortification
Poland |  |  | Seek opportunity to follow up with contacts
Russian Federation
Switzerland |  | Present at the annual meeting of the Foundation Folic Acid Offensive meeting
Ukraine |  | Establish contacts
United Kingdom | Visit country and submit advocacy letter to the Secretary of Health | Contact more than 30 partners to push forward fortification mandate | Continue to support UK campaigns
Czech Republic
Estonia
Greece
Hungary
Latvia
Lithuania
Slovakia
Slovenia
Monitoring and Support
Kazakhstan | Join workshop |  |  | Collaborate with GAIN on technical workshops
Kyrgyzstan | Join workshop
Turkmenistan |  |  | Join a UNICEF-hosted workshop, present flour fortification situation and lead sessions on food control, quality assurance, and fortification best practices | Present at both the International Health Forum and the national strategic meeting on health nutrition and conduct a two-day training providing general introduction to the FORTIMAS monitoring and surveillance methodology
Uzbekistan
Strategic Area of Focus
Austria | Hold workshop during the European Health Forum
Belgium
Croatia
Cyprus
Denmark
Finland
France
Ireland
Italy
Luxembourg
Malta
Montenegro
Netherlands
Norway
Portugal
Romania
Spain
Sweden
Serbia |  | Meet with millers and representatives from local spina bifida organization | Seek opportunity to follow up with contacts, visit country, and find potential connections on the country's annual milling day
Tajikistan |  |  |  | Collaborate with GAIN on technical workshops
Non-country specific activities
| 2012 | 2013 | 2014 | 2015
|  | Publish three paper, meet with multiple partners, and draft advocacy letter | Discuss with UNICEF potential activities for the next year | Smarter Futures Steering Group meet with the Ministry of Foreign Affairs of the Netherlands, and the partnership has been extended to the end of 2017

## India
| Market Channel Reachable Population |  |  |  | State Ranking | Country Activity |  |  |  | 5-year strategy color code (wheat) |  |  | 5-year strategy color code (rice)
| PDS Atta | CMM Atta | RFM Atta | RFM Maida | Rice | 2012 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015
Andhra Pradesh | 0 | 0 | 0 | 4 | 3 |  |  |  | Visit fortification flour mills
Arunachal Pradesh
Assam | 0 | 0 | 0 | 1 | 1
Bihar | 3 | 2 | 2 | 0 | 3
Chhattisgarh | 2 | 0 | 2 | 0 | 2 |  | Provide technical support that is required by the government
Goa
Gujarat | 3 | 2 | 3 | 0 |  |  | Meet with chief secretary of the Gujarat Government and discuss with leaders why the wheat flour fortification program was discontinued |  | Meet with the president of Gujarat Roller Millers Association
Haryana | 2 | 1 | 4 | 2 |  |  |  | Discuss potential future collaborations with WHO Southeast Asia region and CDC Birth Defect Prevention, discuss with GAIN and WHO officials about the Haryana wheat flour fortification project, hold meeting about the Haryana project and 25 people from multiple partners attended, and commit to conduct a supply chain analysis | Discuss partnership with multiple sectors and decide to only include wheat flour in the project, develop methodologies for the supply chain analysis, attend the Naryana Nutrition Mission meeting, conduct supply chain analysis, pilot fortification, visit 13 districts and interview 65 officials for supply chain analysis, and join a consultation on developing nutrition policy
Himachal Pradesh | 0 | 3 | 3 | 2 |  |  | Meet with government leaders |  | Present at a state workshop (70 participants), and do follow-up visits
Jammu and Kashmir | 2 | 4 | 1 | 2
Jharkhand | 1 | 3 | 1 | 2 | 1
Karnataka | 3 | 4 | 4 | 3 | 1 |  |  | Visit plants and flour mills and attend meetings in Bangalore
Kerala | 0 | 0 | 0 | 3 | 1
Madya Pradesh | 4 | 2 | 3 | 4 |  |  |  |  | Meet with officials to discuss mechanisms for wheat flour fortification
Maharashtra | 4 | 3 | 4 | 3
Manipur
Meghalaya | 0 | 0 | 0 | 0
Mizoram
Nagaland
Orissa/Odisha | 2 | 2 | 2 | 1 | 3 |  |  |  | Present at the Congress and meet with the principal secretary of the Food and Civil Supplies Department
Punjab | 1 | 1 | 2 | 2
Rajasthan | 3 | 3 | 4 | 3 |  |  | Attend the meeting of the Department of Food and Civil Supplies, Government of Rajasthan | Meet the Principle Secretary of the Food Department | Visit the Food Analysis and Research Laboratory and the Food Department Secretary
Sikkim
Tamil Nadu | 0 | 0 | 0 | 3 | 2 |  | Present at the Global Milling Conference and meet with local flour millers and founders of the Birth Defects Registry of India | Attend meetings with various stakeholders
Tripura
Uttarakhand | 1 | 1 | 1 | 1
Uttar Pradesh | 3 | 4 | 3 | 3 | 2
West Bengal | 3 | 3 | 0 | 3 | 1 |  | Meet with government leaders | Meet with the Food Secretary of the Government of West Bengal | Meet with the Principal Secretary and suggest a supply chain analysis
Andaman and Nicobar Islands
Chandigarh
Dadra and Nagar Haveli
Daman and Diu
Delhi | [5 empty] | Meet with the Food Minister of India and the Food Minister of Delhi State, multi-sector leaders, and regional WHO staff |  | Meet with stakeholders, visit plants that make fortified rice kernels, develop a one-year agreement for FFI India to continue to work in Delhi, present at a food industry conference and at B.P. Foods Corporate office, present at the 6th International Symposium on RET Foods and at a joint meeting led by the Ministry of Health and Family Welfare and WHO, present at the International Congress on Micronutrients and Child Health Workshop (more than 1000 participants)
Lakshadweep
Puducherry
Telangana (new state)
Non-state specific activities
[6 empty] | 2012 | 2013 | 2014 | 2015
[6 empty] | Visit country, attend meetings, present at the Wheat and Wheat Products-Moving towards Food Nutrition and Security seminar; also present at the Baking society of India, integrate rice into IFFN, provide technical and operational support for wheat fortification, and meet with World Food Program and PATH partners | Attend WHO SEARO/CDC Birth Defects meeting (10 countries), attend UNICEF India office meeting and the civil society organizations meeting, present at a national seminar, meet with Charities Aid Foundation-India CEO, meet with multiple NGO leaders, draft national guidelines for atta and maida fortification, meet with multiple partners, work with UNICEF to organize fortification training program, involve in advocacy events with multiple (and potential) partners, become a member of the "Postik" - a network for food fortification | Meet with "Postik" member organizations, attend meeting that involved national and international NGOs, join India's Sustainable Nutrition Security Group, develop an article that will be released at the 7th International Seminar on Wheat and Wheat Products, develop a concept note to address concerns about fortification expressed by the Indian government, establish new connections with the John and Editha Kappo Charitable Foundation (have several phone calls), attend meeting, meet with key national leaders, publish two paper, and review "Postik" 2014 activities | Meet with new UNICEF nutrition staff, meet with the "Postik" and discuss a National Consultation on Food Fortification, advocate changes in national fortification standards, attend a Food Conclave to discuss issues related to food-processing industries, involved with: ACF-India's seminar, and the 7th International Symposium held by Assocom and ICRISAT, attend the National Consultation on Wheat Flour Fortification, invite several partners to join a conference on business models for securing nutrition
Abbreviations | Definition
PDS | Public Distribution System
CMM | Commercial Chakki Mill
RFM | Roller Flour Mill
Score Ranking | Definition
Wheat | 0-no reachable population 1-low ranking 2-low-intermediate 3-intermediate-high 4-high ranking
Rice | 1-third priority state 2-second priority state 3-first priority state