## 1. Guidelines
GUIDELINES FOR USING THE PERFORMANCE MONITORING FRAMEWORK TO TRACK PROGRESS TOWARDS ELIMINATION OF IDD THROUGH USI
For further information, please contact: Jacky Knowles, GAIN USI M&E Consultant (jknowles@gainhealth.org) and Rizwan Yusafali USI Manager (ryusufali@gainhealth.org).
This workbook consists of 3 worksheets: 1. Guidelines on how to use the workbook; 2. Logic Model for elimination of IDD; 3. Performance Monitoring Framework listing indicators, which are also shown in the logic model to clarify the programme context, likely flow of information and cross-indicator linakages.
This workbook has been developed to help track progress towards the national USI goal. It should serve a dual purpose: a) provide a tool for tracking progress towards achieveing key objectives of the GAIN-UNICEF USI Partnership Project; helping to highlight successes and remaining challenges; b) provide a framework that can be used by national USI partners to inform programme and sustain monitoring of key programme indicators beyond the Partnership period.
The logic model illustrates the main GAIN-UNICEF partnership inputs, activities, outputs and outcomes (impact). These may not all apply in each specific National context and should be revised as part of the country strategy development process. Using a logic model helps the following:
• | developing understanding of the overall programme and the specific role(s) of different partners within it.
• | identifying critical linkages between components and likely sequence of activities for programme managers.
• | identifying which monitoring indicators are essential, depending on national programme priorities.
• | enabling programme managers to track the performance of the programme and identify successes and any potential barriers to success.
The National USI Performance Monitoring Framework should be based on the recommended core programme and sustainability indicators shown, but further refined to fit within the context of national strategies and Partnership work plans. By clicking on column headings within the framework, you can see an explanation of the column meaning and purpose. Indicators highlighted in purple are proposed as indicators that will be used to develop an index for ongoing and final assessment of project progress, achievements and - most importantly - sustainability

## 2. Logic Model
UNICEF/GAIN Partnership logic model for indicators of the elimination of IDD through USI
The model below provides an overview of national IDD elimination components. Related indicator numbers from the Performance Monitoring Framework are included in the oval shapes in this model to illustrate how these indicators link together to provide information about the overall programme.

## PerformanceMonitoringFramework
Universal Salt Iodization Partnership Project Monitoring and Evaluation Indicator Table
|  | Country Name | Ethiopia
|  | Target (Adequately Iodised Salt Supply (MT), HH Use (%)and Timeline): |  |  |  | Sustain 133,000; Improve 161,000 TOTAL 294,000 MT |  |  | 84% HHs by 2015
|  | Click on column headings to see a description of meaning |  |  | Core indicators highlighted in purple are proposed as indicators that will be used to develop an index for final assessment of project progress and sustainability |  |  |  | Highlighted cells indicate where requesting national team review/addition
| Obj. | Project Objective | Core Indicator Data needed in all countries | Supplementary Indicator(s) To obtain data for the key indicator and/or for national programme management | Calculation of Indicator Operational definition | Data Source/Collection Method | Partner Responsible for Indicator | Important Assumptions & Notes | Baseline Data | Source and Date | Updated Data 1 | Source and Date | Updated Data 2 | Source and Date | NOTES from national team when completing data
IMPACT
IMPACT | 1 | To reduce iodine deficiency in target populations | 1.1 Population median urinary iodine concentration (UIC) among women of reproductive age (WRA) (or pregnant women) indicates adequate iodine nutrition. |  | The median UIC value is recommended to estimate population iodine status. The median UIC indicates whether the iodine nutrition of a population is deficient, sufficient, more than adequate. Spot urinary iodine values cannot be used to assess the prevalence of iodine deficiency within a population. Where data permit, UIC should be disaggregated by socioeconomic group, geographic region, urban/rural location, household salt iodisation category (no iodine, below, within and above national/international standards), freq consumption of processed foods containing iodised salt, brand & type of salt (if possible), other relevant factors. | Collection Method: Biochemical time-series data (repeated cross-sectional surveys) to measure changes in UIC. In the absence of opportunities to conduct nationally representative surveys, it may be possible to establish ongoing assessments at selected sites. This is unlikely to provide data representative for the population but may be useful to show trends in iodine nutrition over time. Data Source: MOH, Office of Statistics (Agency supporting the survey) | GAIN | End of project assessment of iodine nutrition will not be conducted in all countries and where done, would ideally be in conjunction with another national survey, rather than as a stand alone iodine nutrition survey. Median UIC among sub-national groups of the population (by geographic region/wealth/salt iodine level) are more programmatically useful than a single national median, which may not reflect the actual situation in any one area of the country. Women of reproductive age (WRA) are recommended as the population group to assess in a household survey setting, although opportunities to assess status among pregnant women instead/as well should be investigated. GAIN will develop some standardised modules for questions related to sources of iodine in the diet, source of the salt, labelling, etc. (which would need adapting to make them nationally appropriate) as well as standardised tables for reporting on iodine status and for the household use of iodised salt and other products made with iodised salt. | Not available |  |  |  | Expect EMNS 2013-14
|  |  |  | 1.2 Population median urinary iodine concentration (UIC) among school age children (or other group such as pregnant women) indicates adequate iodine nutrition. |  |  |  |  | 24.5 µg/l | 2005 National Micronutrient survey |  |  | Expect EMNS 2013-14
OUTCOME
OUTCOME | 2 | To increase number of households and individuals with availability of adequately iodized salt among target groups | 2.1 Household coverage (% HHs with adequately iodised salt) |  | Numerator: number of HHs with availability adequately iodised salt x 100. Denominator: number of households where salt tested (nationally) If data permits, the indicator should be disaggregated by socioeconomic status, geographic region, urban/rural location, salt brand and type, use of "iodised" logo/other labelling on the package. | Collection Method: Numerator and denominator from surveys - data on ppm iodine in salt should be linked to households and salt iodine recommended to be assessed using a quantitative method. Data Source: MOH, Statistics Office | GAIN | • A representative sample of salt should be tested for iodine content by validated quantitative salt iodine methods. Collection of salt samples is a relatively simple and low cost addition to any household survey. • To maximise programme use of salt iodine data, sample collection should be accompanied by questions on the brand & type of salt in the HH (coarse/fine grain), use of "iodised" salt logo/labelling on packaging and other relevant factors. • The same calculation and sub-group analyses should performed for salt with any iodine (> 5ppm iodine by quantitative method) • Indicator 2.1 can be used to calculate: a) Newborns protected: Annual number births x % household adequately iodised salt coverage (indicator 2.1) b) Estimated population reach: Total population x % household adequately iodised salt coverage (indicator 2.1) and/or reach for specific target groups such as pregnant women. • Triangulate results with outcomes for objective 3 (nationally available supply of iodised salt) | 19.9% > 15ppm 34.4% 1-14ppm | 2005 National Micronutrient survey | 5.1% > 15 ppm 15.4% > 1 ppm | 2009 National Nutrition Programme baseline Survey 2011 EDHS | Expect EMNS 2013-14
|  |  |  | 2.2 Household coverage (%) with target foods/condiments produced using iodised salt (see indicator 4) | Numerator: # HHs using target staple food/condiment at least once every 2-3 days x 100 Denominator: # households where data on food/condiment use collected (nationally) If data permits, indicator should be disaggregated by number WRA in the household and by socioeconomic status. | Collection Method: Numerator and denominator from surveys - data on availability and freq of use questions for target processed foods should be linked to household. Data Source: MOH, Statistics Office |  | • This indicator will only be relevant where processed foods are a significant source of iodised salt. • Target foods will be identified as those that contribute significantly to salt intake, are regularly consumed by lower wealth quintile population and are produced by major food processing facilities • Target foods/condiments produced using iodised salt will be defined for objective 4. • To maximise programme use of data, where possible include questions on food brand, labelling re: iodine content, use of a seal/logo
OUTPUT: SUPPLY AND DISTRIBUTION
OUTPUT: SUPPLY & DISTRIBUTION | 3 | To increase domestic availability of iodised and adequately iodised salt | 3.1 Proportion (%) of domestic edible salt requirements adequately iodised |  | Numerator: (MT adequately iodised salt produced (3.3) per 6 month period x 100 Denominator: MT of domestic edible salt needs per 6 month period | Collection Method: Review of production and sales reports, personal contact with producers Data Source: Salt industry, local and central Min Industry or Trade contacts, FMHACA (QAQC outcomes) - see indicator 5 | GAIN | • Reliable production data may be difficult to obtain through industry and government channels (especially for small/non-registered producers). • Provide best estimates and indicate the source and likely accuracy of the data in monitoring reports and triangulate data with outcomes for objectives 7 and 2.1 to check reliability. • Reasonable estimates of total domestic edible salt needs and of iodised salt production are important to monitor the availability of iodised salt for the population plus likely leakage of non-iodised salt into the market. Overall it is important that every effort be made to obtain the most accurate supply data possible on a regular (6 monthly) basis. • Production data should be dissaggregated by scale of production, including separation of data for salt cooperatives/salt banks so that this can be used both for programme management and for tracking of this indicator for partnership project evaluation. | No data |  | 38% National team to verify | Based on 2012-13 analysis of salt production samples by FMHACA |  |  | Do you agree with update information?
|  |  |  | 3.2 Proportion (%) of domestic edible salt requirements iodised (use where reliable QAQC systems not in place and only able to obtain information about iodised salt, not the quality of iodisation) | Numerator: MT iodised salt produced per 6 month period (3.3) x100 Denominator: MT of domestic edible salt needs per 6 month period |  |  |  | 10% |  | > 80% National team to verify | Based on 2012-13 analysis of salt production samples by FMHACA |  |  | Do you agree with update information?
|  |  |  | 3.3 Total production (MT) of a) adequately iodised salt b) all iodised salt by different size producers over defined time period (usually 6 months) To be used in calculation of 3.1 and 3.2 | a) MT adequately iodised salt b) MT all iodised salt Produced by registered and unregistered producers per quarter. |  |  |  | 5,420 MT |  | a) 133,000 MT b) 350,000 MT | USI Partnership regional Meeting Addis Feb 2013 (estimates) |  |  | Baseline - I'm assuming 1 quintal = 100Kg - OK? 54,223 quintals = approx 5,520 MT
| 4 | To increase the use of adequately iodised salt by processed food producers. *Target foods will be identified as those contributing signficantly to salt intake, consumed across wealth quintiles and produced by major food processing facilities. |  | 4.1 Proportion (%) of target staple foods/condiments* produced using iodised salt | Numerator: Amount of iodised salt used in the production of these products by major food processors per quarter (indicator 4.2) x 100. Denominator: Amount of salt used in production of these products by major food processors per quarter. | Collection Method: Review reports salt sales to and purchase by food industry, personal contact with industry, food processing guidelines/recipes/policy Data source: Target processed food producers, Ministry of Industry/Trade, Major producers/importers of higher quality salt, National Food Chamber. | GAIN | • Identification of target foods/condiments produced using iodised salt to be assessed based on food industry or food chamber data, market data, focus groups and any existing dietary/food frequency survey information. • In some cases studies may be needed before foods can be identified and indicators 2.2 and 4.1 can be assessed. These will increase the global knowledge base for targeting USI
| 5 | To ensure that producers are conducting internal QC and meet national standards for iodine. | 5.1 Percentage of iodised salt facilities following SOPs for production of iodised salt. At minimum this should mean regular records for: salt production, KIO3 use, quality of iodisation |  | Numerator: Iodised salt facility (production/repacker) with at least minimum indicated records (from SOP) for production of iodised salt x 100. Denominator: Total number of iodised salt facilities (production/repacker) Disggregated by scale of production as appropriate. | Collection Method: Listing of production/repacking facilities (disaggregated by size). Review of facility quality control records, manuals/SOPs (where available), and staff responsibilities. Data source: Government inspection body (FMHACA), Private industry, Min Industry & Trade, Salt Bank Cooperatives, ICCIDD, information from objective 3 | GAIN | • The quality of information on salt production facilities and output (see objective 3) will also be important in determining accurate estimates for tracking achievements against this QAQC objective. • The 3 indicators here capture the main expectations for QAQC, in relation to the QAQC manual development, workshops, and planned tranings, which were aimed at medium and large scale producers. • The person designated as responsible for QC does not necessarily need to have the title of QC manager, however, it needs to be clearly identified as someone's specific responsibility. • Data from this objective (5) together with information on facility capacity and iodised salt production information (obj 3) can be used to determine the proportion (%) of national iodised salt produced or repacked by facilities with improved QAQC as a result of the Partnership inputs. • Determination of these indicators should be broken down by production capacity with different expectations in terms of QC for each. Additional indicators may be needed in countries where the majority of salt comes from multiple small scale producers (to discuss prior to reporting). Could have up to 4 outcomes for each indicator, as follows: Small (cottage-scale) > 1,000 MT/annum Medium 1,000 – 4,999 MT/annum Large 5,000-9,999 MT/annum Very Large ? 10,000 MT/annum | 1 facility |  | No update |  |  |  | 1 facility out of approx how many with an equivalent production capacity? or representing approx what % of total market share for iodised salt?
|  |  | 5.2 Percentage of producers/importers/repackers with a designated staff person responsible for quality management |  | Numerator: Number of salt production/repacking facilities with designated staff person responsible for QC x 100. Denominator: Total number of salt production/repacking facilities. Dissaggregate by scale of production as appropriate |  |  |  | 1 facility |  | No update |  |  |  | 1 facility out of approx how many with an equivalent production capacity? or representing approx what % of total market share for iodised salt?
|  |  |  | 5.3 Percentage of producers/importers/repackers with improved manual and procedures following the QAQC workshops and trainings | Numerator: Number of salt production/repacking facilities with improved quality manual and procedures following training through the Partnership x 100. Denominator: Total number of salt production/repacking facilities Disggregate by scale of production as appropriate |  |  |  | Not applicable |  | No update
| 6 | To ensure that food control departments are conducting external regulatory monitoring |  | 6.1a Percentage of production/repacking facilities inspected by responsible government department compared to the national workplan. | Numerator: Number of iodised salt facilities (production/repacker) visited (evidenced via records) by agreed government team x100 Denominator: Total number of iodised salt facilities (production/repacker) planned for inspection | Collection Method: Review workplan, review inspection records (to check that visit conducted and samples tested), listing of FMHACAofficials and responsibilities. Data source: Government inspection body (FMHACA), Min Industry, ICCIDD | GAIN | • The 2 indicators here (6.1 & 6.2) along with indicator 9.1 capture the main expectations for regulatory monitoring and can be applied in relation to the QAQC manual development, workshops, and planned trainings. • Data from this objective (6) together with information on facility QC capacity and iodised salt production information (objs 5 & 3) can be used to determine the proportion (%) of national iodised salt produced or repacked with inspection using improved QAQC methods as a result of the Partnership inputs. • Determination of this indicator should be broken down by production capacity and additional indicators may be required, as for indicator 5. | No data |  | No update
|  |  |  | 6.1b Percentage of iodised salt distribution hubs inspected by responsible government department compared to the national workplan. | Numerator: Number of checks at iodised salt distribution hubs (evidenced via records) by government team x100 Denominator: Total number of iodised salt distribution hub checks planned for inspection |  |  |  | No data |  | No update
|  |  |  | 6.1c Percentage of retail facilities inspected by responsible government department compared to the national workplan. | Numerator: Number of iodised salt retail facilities visited by agreed government team x100 Denominator: Total number of iodised salt retail facilities planned for inspection |  |  |  | No data |  | 80/160 facilities = 50%
|  |  |  | 6.2 Existence of improved regulatory monitoring manual and procedures following the QAQC workshops and trainings | Yes/No | Collection Method: Review FMHACA regulatory monitoring procedures in comparison with previous procedures. Data source: Government inspection body (FMHACA), Min Industry, ICCIDD |  |  | No data |  | No update
| 7 | To ensure an adequate and reliable supply of KIO3 for the iodisation of edible salt | 7.1 Adequacy of KIO3 supply. % domestic needs for KIO3 for adequately iodised salt that are met. |  | Numerator: KIO3 distributed to the salt industry x 100. Denominator: Total requirement for KIO3 to enable adequately iodised salt production for > 90% all edible salt produced in the country. | Collection Method: Review of import records, Private industry records, GPF and UNICEF procurement records. Data source: Ministry of Industry/Trade (customs), GAIN GPF and UNICEF procurement, national KIO3 suppliers, salt iodisation facilities | GAIN | It should be possible to get a fairly accurate estimate of national (and facility-based) KIO3 supply. This can be triangulated with data from objective 3 to help assess sufficiency for adequate iodisation of all domestic edible salt. | 1.9 MT of 22 MT requirement = 7% requirements met | [5 empty] | Is there no update for this - still all externally funded? I thought there was now seed funds and producers purchase it from the Govt who maintain the fund? And that you had some record of how much was purchased? What is current estimate for requirement?
|  |  |  | 7.2 Proportion of KIO3 supply funded by: a) the salt industry b) the Government. | Numerator: Current national KIO3 supply bought by a) the salt industry/b) Govt x 100. Denominator: Total current requirement for KIO3 to enable adequately iodised salt production for > 90% all edible salt produced in the country. |  |  |  | 0 (all externally funded) |  | No update |  |  |  | See abvoe re: expected update. On our Skype call you said that prodcuers were now purchasing it from the Govt but I wasn't clear if donor funds still used or not. 100% salt producers?
| 8 | To ensure that iodised salt is adequately distributed so that low income populations have access |  | 8.1 Percentage of publically distributed salt that is adequately iodised (publically subsidised distribution). | Numerator: MT of publically distributed salt adequately iodised salt. Denominator: Total salt distributed through public channels nationally. | Collection Method: salt distribution records. Data Source: Government department, supporting agency (e.g. WFP) | GAIN/ UNICEF
| 9 | Good institutional capacity for implementation and enforcement of USI exists | 9.1 Clear regulatory monitoring protocols exist with defined responsibilities, activities and follow up (regulatory monitoring SOPs) |  | Yes No | Collection Method: Review FMHACA responsibilities and regulatory monitoring procedures. Data source: Government inspection body (FMHACA), Min Industry, ICCIDD | GAIN | Regulatory monitoring SOPs should include assessment of iodised salt production SOPs so no need for a separate sustainability indicator for internal QC | No | Country Strategy July 2011 | Under development | USI Partnership regional Meeting Addis Feb 2013
|  |  | 9.2 KIO3 procurement (sufficient to meet domestic needs) can be maintained without external project funding. |  | a) Yes - through Government subsidies b) Yes - through salt industry funds c) No | Collection Method: Review financial reports for, and budgets related to, USI Data Source: Salt industry, Government, Outcomes for objective 7 | GAIN | Achievement for this indicator should be demonstrated by the presence of a proven self-sustaining cost recovery operation. | No Insufficient and not nationally funded | Country Strategy July 2011 | KIO3 distribution currently through MOH, industry supported scheme Under development | USI Partnership regional Meeting Addis Feb 2013
OUTPUT: COMMUNICATION
OUTPUT: COMMUNICATION | 10 | To ensure that consumers and retailers are aware of and accept iodised salt | 10.1 Is packaged iodised salt clearly labelled as iodised (labelling or logo)? |  | Numerator: number of households with packaged salt with a clear label/logo showing that salt is iodised x 100 Denominator: number of households with pacakged salt (sample size) Or equivalent calculation if a market based survey Numerator: number of retailers where all packaged salt has a clear label/logo showing that salt is iodised x 100 Denominator: number of retailers trading in pacakged salt (sample size) Or if neither of above possible, some indication from a salt situation analysis at production, of the proportion of iodised salt that is packaged and is clearly labelled as iodised. | Collection Method: Included in household survey module: is salt packaged? Y/N Does packaged salt have a logo (a) or is it clearly labeled (b) indicating it is iodised? Or market based food product survey. (or salt situation/analysis at production/distribution sites) Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, FMHACA (Post marketing survey), MOI, NGO | UNICEF | Notes from feedback August 2013: The majority of iodised salt is packed in 50 kg sacks therefore it is expected to be sold loose and not labelled at HH level, therefore may be better to use retail level indicator. The information for the household indicator will be included as part of the ENMS, not sure if retail level indicator also possible to collect or not. To include where appropriate based on national situation - percentage of salt that is packaged Where no household survey data are available, provide indication from salt industry packaging practices whether packaging includes a logo or other clear indication that the salt is iodised | Not labelled |  | Labelling is defined under the FMHACA directive, but needs more work for implementation - part of communication strategy under development (PSI will assist in degisn) | ?? | ENMS question H60 will provide data for this: [Does the package of table salt say "iodized"?] |  | Approx what % of salt in the retail market is packaged versus loose? As in notes column - The information for the household indicator will be included as part of the ENMS, not sure if retail level indicator also possible to collect or not.
|  |  |  | 10.2 Percentage of consumers who know of the benefits of iodised salt (Knowledge) | Numerator: number of consumers who can correctly name at least one benefit of iodised salt x 100 Denominator: number of consumers asked (sample size) | Collection Method: Questions in a KAP survey or other household survey: Can you name the benefits of iodised salt?' Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, NGO | UNICEF | To include where appropriate based on national plans Can be adapted to be specific for a given geographic area/demographic group, depending on national plans | < 10% | 2005 National Micronutrient survey (from country strategy) | No update |  |  |  | There is curently no question in the EMNS questionnaire to answer this. Is this important as a national indicator and if so, is it still possible to add to the questionnaire?
|  |  |  | 10.3 Percentage of retailers in low coverage areas who know the benefits of iodised salt (Knowledge) | Numerator: number of retailers in low coverage areas who can correctly name at least one benefit of iodised salt x 100 Denominator: number of retailers in low coverage areas asked (sample size) | Collection Method: Questions at start & follow up for retailer RTK strategy or other retailer survey: Can you name the benefits of iodised salt?' Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, NGO | UNICEF | To include where appropriate based on national plans - use where retailer RTK strategy implemented Can be adapted to be specific for a given geographic area/demographic group, depending on national plans
| 11 | Communications are in place to secure sustained production and distribution of iodized salt and to ensure consumer acceptance of the USI effort | 11.1 Communication strategy in place to address identified programme challenges |  | Yes/No | Collection Method: Review plans and policies Data source: Various ministries/IDD committee | UNICEF | Evidence that a communication strategy is in place to address specific national challenges, that activities and focus are reviewed and adjusted as needed. | No | Country Strategy July 2011 | Draft developed | USI Partnership regional Meeting Addis Feb 2013 |  |  | Do you expect to collect any baseline or impact data for the strategy?
|  |  | 11.2 Education about IDD and iodised salt are included as part of the school curriculum |  | Yes/No | Collection Method: Review curricula Data source: Ministry of Education | UNICEF | Indicate whether primary or secondary school curriculum. |  |  | Included in primary school science. Additional information materials and RTK will be distributed (not under partnership plan) |  |  |  | Was this included in the curriculum at the start of the project or is it progress made since the start (due to Partnership activities or other)?
|  |  | 11.3 Education about IDD and iodised salt is included as part of a) the food-technology training program, b) pre -service training of public employees (health and industry/commerce as relevant) and c) the pre and in service training of community health workers. |  | a) food-technology training program Yes/No b)pre-service training for public employees Yes/No c) pre-service or in-service training for community workers: Yes/No | Collection Method: Review curricula Data source: Ministry of Industry/food technology institutes, | UNICEF | Where there is no signficant national food industry or food technology training programme, note this and use N/A as response to (a) National team to identify relevant public employees to include - health, industry, other? Also community health workers may be interpreted differently in different countries, report for the equivalent position in your country. | No? to all? |  | a) No b) No c) Community health workers (non-Partnership support)? |  |  |  | Was this no to all at the baseline (project start?)
OUTPUT: ADVOCACY
OUTPUT: ADVOCACY | 12 | Clear political commitment national ownership of the programme exists. | 12.1 Existence of legislation and regulations for the production and import (or trade) of adequately iodised salt for human consumption. |  | a) Yes/No - legislation - production b) Yes/No - regulations - production c) Yes/No - legislation - import/trade d) Yes/No - regulations - import/trade | Collection Method: Review national legislative, regulatory and budget documents Data Source: Relevant Govt Department | UNICEF | The definition of USI includes iodisation of all salt for human and animal consumption, including salt used in the food industry. Scoring for sustainability would put less weight on the salt for livestock feed. Some countries may have regulations without legislation and some may have legislation without clear accompanying regulations. | No | Country Strategy July 2011 | a) Yes - legislation - production b) ? - regulations - production - under development? c) ? - legislation - import/trade d) ? - regulations - import/trade | USI Partnership regional Meeting Addis Feb 2013 |  |  | Can you provide information on b, c, and d. Thank you.
|  |  | 12.2 Scope of legislation/regulations includes mandatory iodization of a) table salt b) salt for processed food production c) salt for livestock feed |  | a) Yes/No b) Yes/No c) Yes/No | Collection Method: Review national legislative & regulatory documents Data Source: Relevant Govt Department | UNICEF |  | No | Country Strategy July 2011 | National team to verify |  |  |  | Can you provide information on the current situation.
|  |  | 12.3 Elimination of IDD through USI is integrated into national: a) food and nutrition policies, b) annual plans and budget, c) annual policy and progress reviews. |  | a) food and nutrition policies: Yes/No b) annual plans and budget: Yes/No c) annual policy and progress reviews: Yes/No | Collection Method: Review national legislative and regulatory documents, database structure, reports, workplans and budgets Data Source: MOH, Min Industry | UNICEF | This is an important indicator of sustainability and in line with the SUN strategy for mainstreaming all components of nutrition. | No data, probably not |  | a) Yes, NNP b) yes? C) ?? |  |  |  | Was this included in any plans at the start of the project? If elimination of IDD through USI is now included in NNP, does that mean there is budget allocated? And are annual progamme reviews conducted or going to be conducted, inlcluding for IDD?
|  |  | 12.4 Systems are in place to monitor population iodine status and iodized salt use (as defined by legislation) |  | a) Yes - for iodine status b) No - for iodine status c) Yes - for iodized salt use d) No - for iodized salt use | Collection Method: Review nutrition survey plans, coordinating group workplans, national budget allocation for monitoring. Data source: MOH, multi sector coordinating group | GAIN | This may be part of a larger system incorporating other nutrition, household, food industry etc. indicators; however, iodine specific information should feed into the annual review and planning process in indicator 13.3 | No | Country Strategy July 2011 | Under development | USI Partnership regional Meeting Addis Feb 2013
|  |  | 12.5 Existence of a a) national multi-sector coordination body coordinating the program for IDD elimination b) which includes the salt industry c) which has a work plan with clear roles and responsibilities d) is considered to function effectively |  | a) existence of coordination body: Yes/No b) salt industry included in coordination body: Yes/No c) work plan exists and defines clear roles and responsibilities: Yes/No d) functions effectively: Yes/No/Sometimes | Collection Method: Review official authorisation and outline of functions for coordinating body, national workplans, meeting minutes Data Source: Government documents, National workplan Reports on workplan progress | UNICEF | • The IDD secretariat can be taken to mean an independent group that meet for iodine specifically or a group who meet as part of a national micronutrient committee or similar and include issues related to iodine nutrition. • It may not be possible or relevant for salt industry representatives to participate in all meetings, however, there should be good evidence that they are consulted on programme strategy where relevant, e.g. revision of QAQC protocols, development of social marketing messages, etc. • For sub-indicator (d) the information will be somewhat subjective but should take into account whether the group meets sufficient regularity to report and review progress against the work plan. In situation where (a-c) are all "Yes" but (d) is "no" kindly provide additional qualitative feedback about the basis for this assessment. | No | Country Strategy July 2011 | a) existence of coordination body: Yes b) salt industry included in coordination body:No c) work plan exists and defines clear roles and responsibilities: Yes d) functions effectively: Yes (but no salt industry) |  |  |  | Is there a reason for no inclusion of the salt industry? Is there some mechansim for them to have input into plans etc.?
--- The USI country team may include additional indicators for each section as necessary ---