## Ethiopia
Ethiopias salt iodization Q/QA Progress Monitoring Matrix (Phase III)
Country | GAIN Focal Point | ICCIDD Focal point | In country consultant | SN | Salt Company | Contact details | Actual Estimated Annual Salt Production (MT) | Assessed (y/n) | Key QAQC Recommendations (use 1 row for each recommendation) | Recommendation implemented (y/n) | Target timeframe for implementation | Progress Status and other notes
Ethiopia | Asmelash, Lorenzo |  | Teshome Desta | 1 | Afar Salt Prodution SC (ASPSC/Ezana) | Wolde Gebreal Girmay,0913190351 | 25000-30000 MT/Annum | y | a.Facilitate already initiaated review/ updating of SOPS /Protocols as per recommendation of ESA and ensure their full implementation | N | 6 months period (Jan-June 2015) | Factory unexpectedly is out of production since assessment was conducted.Reason disagreement with newly formed share Company (KDABA).Some negoitation under way Still no tclear when production will resume. .
[9 empty] | b.Secure WYD equipment and ensure adequate supply of regents | N | ,, | WYD training provided . GAIN has not yet delivered WYDs.
[9 empty] | c. Improve storage conditions for KIO3 and packaging materials and dispose of damaged items on time | y | ,, | Additional laboratory and KIO3 storage facility is under construction about 50% completed
[9 empty] | d.Improve on over all recordin,and maintaining of documentation at fctory level | y | ,, | Partially implemented .Some improvement seen
[9 empty] | e.Standardize labeling and include traceability marking | N | ,, | No improvement made over past
[9 empty] | f.Keep dequate stock of KIO3 at HQ to avoid stock outs | N | ,, | No change made since production has totally curtailed
[9 empty] | g. Explore possibilities for using idle capacity by solving existing bottle necks | N | ,, | Situation infact worsened. Even existing production quota disrupted. No body knows what happens next.
|  |  |  | 2 | Dobi salt producers association | Abdu Ahmed,0911081237 | NA | y | a.Association needs to improve structurally and functionally (develop orgnogram, JDs, Operational mnuals and SOPs) Responsibilities needs to be clearly defined and assigned | NA | NA | Assement was conducted but only limited information was generated(phase 1 ). Dobi did not prticipate in SOP and WYD training (Phase 2) although invited. Did not develop work plan for implementation QA/QC. Therefore is not included in current monitoring (Phase 3)
[9 empty] | a. Technical standards/ specifications for procurement of inputs need to be developed and followed strictly | ,, | ,, | Dobi produces 10-15 % salt, therefore is too big to be ignored.Obviously situation is bit tough.May need separate approach and timing..
[9 empty] | b. Production data needs to be propely recorded and provided | ,, | ,,
[9 empty] | c.Technical standards/ specifications for procurement of inputs need to be developed and followed strictly | ,, | ,,
[9 empty] | d.System for receiving and issuing inputs and checking of material quality needs to be in place | ,, | ,,
[9 empty] | e. Overall storage facility and condition for KIO3, packging materials must be improved | ,, | ,,
[9 empty] | f. Labeling should be in agreement with national standard and include tracebility marking | ,, | ,,
|  |  |  | 3 | Tafo Iodized salt Production Factory (Hilina) | Abayneh Taye,0911516273 | 554 MT/Yr (table salt and Coarse salt ) | y | a.Existing iodization machine needs proper installation and commissioning if possible or substituted with new one as indicated | Y | 6 months period (Jan-June 2015) | Case of imported big machine stil lunder legal procedure.Seving and packaging /screening machines installed, Packaging materials have improved
[9 empty] | b.Change dry mixing method continous spray as originally planned | N | ,, | Can only be implemented once legal issues about the big machine close.ry mixing will continue until then.
[9 empty] | c.Iodization Factory must develop necessary technical standards and SOPs for salt iodization (can simply be adapted from sister factory (BEFF | y | ,, | develpoment of SOPs >90% completed and Implementation to be launched soon. Factory also under preparation for ISO certification.
[9 empty] | d. Avoid damage to existing excess stok of KIO3 | N | ,, | No action taken yet, still huge stok pile seen . There is plan for re-evaluation and certfication f or extensded use of the product.
[9 empty] | e.Product labeling to be in agreement with national standard. Include traeaibility mark | y | ,, | Some modification made but still not upto satndard. For example PPM not indicated in lables
[9 empty] | f.Ensure proper recording and maintain documentation |  | ,, | Progress made already , process continues on .
[9 empty] | g.avoid using two standards for iodine levels (Commercial product and WFP special order) |  | ,, | Currently 50 kg WFP ordered package not being produced . Only commercial salt is producedaccording to national standard. Production amount has incresed significantly .
|  |  |  | 4 | Yosis iodized salt Manufacturing PLC, | Sisay Tesema, 0911628949 |  | y | a proper installation and commissioning off iodization mchine required (currently only partly working).Consider option of using continous wet mixing method, by properly fixing mchine using the sprayer provided | N | 6 months (jan-June 2015) | Work plan not implemented. New site rented to move factory but unexpected complication occurred disrupting plan. Case under legal consideration. Manager admits delay but still commited to implementation of theQA/QC plan once new location is secured and transfer of factory completed.
[9 empty] | b. Improve factory working space and staffing?? (office, lab oratory, store..).indicated plan to move to new leased location needs to be facilitated | ,, | ,, | .
[9 empty] | c..Factory must clearly define and assign responsibilities properly. Currently most responsibility carried out by GM/owner | ,, | ,,
[9 empty] | d.Define technical standards/protocols for inputs includinfg raw salt and. Factory must develop and implement basic SOPs,procedures, protocols | ,, | ,,
[9 empty] | e.Buy/get KIO3 from legal suppliers/sourceavoid illegal sources . Ensure proper storage | ,, | ,,
[9 empty] | f.Factory must clearly define and assign responsibilities properly. Currently most responsibility carried out by GM/owner | ,, | ,,
[9 empty] | g. poor recording and documentation needs to urgently improve | ,, | ,,
Focus on quality. Secure WYD and establish laboratory to ensure proper iodine content | [8 empty] | Establish system for regularly collecting consumer feedback | ,, | ,,
|  |  |  | 5 | Afdera Salt Producers Mutual Support Assoc. (ASPMSA) | Mohamed Awel,0938630450 | 300,000 MT/annum | y | a. Develop proper organogram, JDs . Clearly define and assign responsibilities. | None | 6 months period (Jan-June 2015) | ASPMSA. has been pushed out of operation (suspended) since Dec. 2014. Newly established SC (KADABA) claims responsibility for salt iodization and distribution .Existing ASPMSA structure removed with out replacement. No proper handover conducted.Currently situation in total disarrey. QA/QC project suffered consequences of this unfortunate situation.
[9 empty] | b.Improve staffing, skill and work enviornment.. | ,, |  | Previous SPMSA staff suspended. New staff not properly recurrited and not trained on iodization.
[9 empty] | c. Develop technical standards (specifications) for raw inputs and ensure implementation | ,, |  | No body to take responsibility and follow upabout implementation of planned activities.
[9 empty] | d. Put inplace bsic/essential SOPs procedures and protocols and ensure their implementation | ,, |  | same
[9 empty] | e.Focus on iodization quality and strengthen committtement . Establish quality lab (WYD) to verify quality. Service should be accessible to all producers | ,, |  | Infact situation worsened due lack of responsibility/accountability
[9 empty] | f.Rationally use KIO3 supplied (no white washing) ,Improve storage conditions of KIO3, packaging materials and other inputs as per specification developed | ,, |  | Separate ( defacto) chnnel of obtaining and distributing KIO3 practiced.
[9 empty] | g.Labelling should be be harmonized with national standard | ,, |  | No body to take responsibility and follow upabout implementation of planned activities.
|  |  |  | 6 | M. Amole | Mulugeta Enki, 0914302721 | Iodized =596 MT/ annum, Noniodized =256 MT/ Annum | y | a. Existing operational manual, basic SOPs /protocols may require reviewing/updating | y | within following 6 months period (Jan-June 2015) | Most SOPs exist and routinely practiced. Factory aspires to go further in ensuring QA/QC for ISO certification.
[9 empty] | b.Assign specific responsibilities to individuals rather than units | y | ,, | Orientation/sensitization of staff conducted. Practically they are taking more responsibility for quality
[9 empty] | c.Improve recording and mainataining of documentation | y | ,, | Recording and documentation in qulity lab has significantly improved
[9 empty] | d. check iodine levels before release of products. . | y | ,, | agreed in principle , promised to be put it in practice.
[9 empty] | e.Establish routine annual schedule for machine servicing and maintennce | y | ,, | Decision reched to conduct scheduled bi annual maintenance/servicing in addition to down times
[9 empty] | f..Labelling of products must be uniform,complete and in agreement with national standard | y | ,, | New packging materials /products introduced since Jan. 2015 (250 g ,500 g and1000 g coarse iodized salt. 850 g table salt has been replaced by 700 g bottle). Labelling has also improved but further improvement is still needed(PPM range needs correction)
[9 empty] | g. Ensure access to noniodized raw salt, Increase market demand for product ( promotion) scale up production | y | ,, | Negotiation conducted with new supplier (source). Continuty of supply improved. New fair price negotiated .Over all supply situation improved.
|  |  |  | 5 | Shewit Salt Manufacturing PLC | Eyob Feuessa 0914726683 | 4107 MT/nnum | y | a. Roles and responsisbilites should be better defined and delinated | Y | within following 6 months period (Jan-June 2015) | Partially Implemented , new professional staff recuritted (Chemist, biologist and sanitarian), needs to continue.
[9 empty] | b. Ensure reliable access to raw salt | Y |  | Access to raw salt supply improved (source), but cost and continuty of supply remains a concern.
[9 empty] | c. Necessary protocols, SOPs need to be inplace and implemented | Y |  | development of 6 SOPs In progress, will be completed by June 2015. Full implementation will start immediately.
[9 empty] | d. Establish and mintain proper recording of the iodization process | Y |  | In progress
[9 empty] | e.Establish procedure for collecting and acting on consumer feedback whileimproving mrket access | Y |  | Partially. Production volume and market access has significantly improved
[9 empty] | f. Strengthe lab facility (space,equipment , personnel) to ensure proper iodization quality | Y |  | marked improvement made .Separate space chemist assigned, water distillin machine installed, Solution A&B prepared in the lab.Raw salkkt quality being checked for NACL content.
|  |  |  | 7 | Wolelah Salt Trading SC | Abdurehman Furie,0911035277 | 24,000 Mt /Yr | y | a. Proper organogram, JDs, Sops, Operationl Manuals need to be in place Responsibility needs to be clearly defined and assigned . | N | following 6 months period (Jan-June 2015) | Not implemented .Reason given relates to language problem. Multiple translation (English, Amharic and Somligna) has to be done. Needs expetise and time taking.
[9 empty] | b. Develop technical standards list of suppliers for purchase of inputs | y | ,, | same
[9 empty] | c. Develop and implement basic protocols for reciiving and issuing inputs and also check quality on receiving of inputsincluding quality of raw salt |  | ,, | already being used/practised effectively.
[9 empty] | d. Generlly recording and minataining of documentation needs improvement | Y | ,, | partially improved , requires to continue
[9 empty] | e. Ensure supply of regents. Create lab facility /office | Y | ,, | With FMHACA support identified and linked with private supplier. Keeps minimum stock of 3 months supply.
[9 empty] | f. Product labeling should be confirm with national standard and include tracebility marking | Y | ,, | New packaging material developed with recent transformation of Coop. to SC. Packaging material quality has improved 100 g/sac (80 g ext. material 20 g internal pp lining ) as opposed to previous weight of 80 g.
[9 empty] | g. set schedule maintenance and servicing of iodization equipment | Y | ,, | one full time macine maintenance technician employed nd on board.
[9 empty] | h. Establish system for collecting consumer feedback | N | ,, | Not first priority