## 1. Guidelines
GUIDELINES FOR USING THE PERFORMANCE MONITORING FRAMEWORK TO TRACK PROGRESS TOWARDS ELIMINATION OF IDD THROUGH USI
For further information, please contact: Jacky Knowles, GAIN USI M&E Consultant (jknowles@gainhealth.org) and Rizwan Yusafali USI Manager (ryusufali@gainhealth.org).
This workbook consists of 3 worksheets: 1. Guidelines on how to use the workbook; 2. Logic Model for elimination of IDD; 3. Performance Monitoring Framework listing indicators, which are also shown in the logic model to clarify the programme context, likely flow of information and cross-indicator linakages.
This workbook has been developed to help track progress towards the national USI goal. It should serve a dual purpose: a) provide a tool for tracking progress towards achieveing key objectives of the GAIN-UNICEF USI Partnership Project; helping to highlight successes and remaining challenges; b) provide a framework that can be used by national USI partners to inform programme and sustain monitoring of key programme indicators beyond the Partnership period.
The logic model illustrates the main GAIN-UNICEF partnership inputs, activities, outputs and outcomes (impact). These may not all apply in each specific National context and should be revised as part of the country strategy development process. Using a logic model helps the following:
• | developing understanding of the overall programme and the specific role(s) of different partners within it.
• | identifying critical linkages between components and likely sequence of activities for programme managers.
• | identifying which monitoring indicators are essential, depending on national programme priorities.
• | enabling programme managers to track the performance of the programme and identify successes and any potential barriers to success.
The National USI Performance Monitoring Framework should be based on the recommended core programme and sustainability indicators shown, but further refined to fit within the context of national strategies and Partnership work plans. By clicking on column headings within the framework, you can see an explanation of the column meaning and purpose. Indicators highlighted in purple are proposed as indicators that will be used to develop an index for ongoing and final assessment of project progress, achievements and - most importantly - sustainability

## 2. Logic Model
UNICEF/GAIN Partnership logic model for indicators of the elimination of IDD through USI
The model below provides an overview of national IDD elimination components. Related indicator numbers from the Performance Monitoring Framework are included in the oval shapes in this model to illustrate how these indicators link together to provide information about the overall programme.

## PerformanceMonitoringFramework
Universal Salt Iodization Partnership Project Monitoring and Evaluation Indicator Table
|  | Country Name | India
|  | Target (Adequately Iodised Salt Supply (MT), HH Use (%)and Timeline): |  |  |  | Sustain 4,402,000; Improve 930,000, Expand 248,000 TOTAL 5,580,000 MT |  |  | 90% HHs by 2015
|  | Click on column headings to see a description of meaning |  |  | Core indicators highlighted in purple are proposed as indicators that will be used to develop an index for final assessment of project progress and sustainability |  |  |  | Highlighted cells indicate where requesting national team review/addition
| Obj. | Project Objective | Core Indicator Data needed in all countries | Supplementary Indicator(s) To obtain data for the key indicator and/or for national programme management | Calculation of Indicator Operational definition | Data Source/Collection Method | Partner Responsible for Indicator | Important Assumptions & Notes | Baseline Data | Source and Date | Updated Data 1 | Source and Date | Updated Data 2 | Source and Date | Notes for when completing data updates Currently contains notes from Jacky's call with Arijit on 08/08/13
IMPACT
IMPACT | 1 | To reduce iodine deficiency in target populations | 1.1 Population median urinary iodine concentration (UIC) among women of reproductive age (WRA) (or pregnant women) indicates adequate iodine nutrition. |  |  | Collection Method: Biochemical time-series data (repeated cross-sectional surveys) to measure changes in UIC. In the absence of opportunities to conduct nationally representative surveys, it may be possible to establish ongoing assessments at selected sites. This is unlikely to provide data representative for the population but may be useful to show trends in iodine nutrition over time. Data Source: MOH, Office of Statistics (Agency supporting the survey) | GAIN | End of project assessment of iodine nutrition will not be conducted in all countries and where done, would ideally be in conjunction with another national survey, rather than as a stand alone iodine nutrition survey. Median UIC among sub-national groups of the population (by geographic region/wealth/salt iodine level) are more programmatically useful than a single national median, which may not reflect the actual situation in any one area of the country. Women of reproductive age (WRA) are recommended as the population group to assess in a household survey setting, although opportunities to assess status among pregnant women instead/as well should be investigated. GAIN will develop some standardised modules for questions related to sources of iodine in the diet, source of the salt, labelling, etc. (which would need adapting to make them nationally appropriate) as well as standardised tables for reporting on iodine status and for the household use of iodised salt and other products made with iodised salt. | Not available |  | Not yet available |  |  |  | Arijit to add baselines from country strategy (WHO database, regional surveys, State level surveys)
|  |  |  | 1.2 Population median urinary iodine concentration (UIC) among school age children (or other group such as pregnant women) indicates adequate iodine nutrition. |  |  |  |  | 133 µg/l (SAC) (31% <100 µg/l) Data source - 2004 WHO Report (Not nationally representative; pooled estimate from state & district level surveys; data collected between 1993 and 2002 at various timepoints) |  | 154µg/l (SAC?) (34% < 100µg/l); Data source - Andersson et al. J Nutr 2011. (Not nationally representative; pooled estimate from state & district level surveys) | 2012 Global scorecard Andersson et al.
OUTCOME
OUTCOME | 2 | To increase number of households and individuals with availability of adequately iodized salt among target groups | 2.1 Household coverage (% HHs with adequately iodised salt) |  | Numerator: number of HHs with availability adequately iodised salt x 100. Denominator: number of households where salt tested (nationally) If data permits, the indicator should be disaggregated by socioeconomic status, geographic region, urban/rural location, salt brand and type, use of "iodised" logo/other labelling on the package. | Collection Method: Numerator and denominator from surveys - data on ppm iodine in salt should be linked to households and salt iodine recommended to be assessed using a quantitative method. Data Source: MOH, Statistics Office | GAIN | • A representative sample of salt should be tested for iodine content by validated quantitative salt iodine methods. Collection of salt samples is a relatively simple and low cost addition to any household survey. • To maximise programme use of salt iodine data, sample collection should be accompanied by questions on the brand & type of salt in the HH (coarse/fine grain), use of "iodised" salt logo/labelling on packaging and other relevant factors. • The same calculation and sub-group analyses should performed for salt with any iodine (> 5ppm iodine by quantitative method) • Indicator 2.1 can be used to calculate: a) Newborns protected: Annual number births x % household adequately iodised salt coverage (indicator 2.1) b) Estimated population reach: Total population x % household adequately iodised salt coverage (indicator 2.1) and/or reach for specific target groups such as pregnant women. • Triangulate results with outcomes for objective 3 (nationally available supply of iodised salt) | 71.9% > 15 ppm (RTK) | Coverage Evaluation Survey UNICEF 2009 | 81.4% > 15 ppm (RTK) | 2012-13 MIS data collected from MOHFW (NRHM), Representativeness unknown |  |  | Arijit to update with NIDDCP data
|  |  |  | 2.2 Household coverage (%) with target foods/condiments produced using iodised salt (see indicator 4) | Numerator: # HHs using target staple food/condiment at least once every 2-3 days x 100 Denominator: # households where data on food/condiment use collected (nationally) If data permits, indicator should be disaggregated by number WRA in the household and by socioeconomic status. | Collection Method: Numerator and denominator from surveys - data on availability and freq of use questions for target processed foods should be linked to household. Data Source: MOH, Statistics Office |  | • This indicator will only be relevant where processed foods are a significant source of iodised salt. • Target foods will be identified as those that contribute significantly to salt intake, are regularly consumed by lower wealth quintile population and are produced by major food processing facilities • Target foods/condiments produced using iodised salt will be defined for objective 4. • To maximise programme use of data, where possible include questions on food brand, labelling re: iodine content, use of a seal/logo
OUTPUT: SUPPLY AND DISTRIBUTION
OUTPUT: SUPPLY & DISTRIBUTION | 3 | To increase domestic availability of iodised and adequately iodised salt | 3.1 Proportion (%) of domestic edible salt requirements adequately iodised |  | Numerator: (MT adequately iodised salt produced (3.3) + MT adequately iodised salt imported (3.4) - (minus) MT iodised salt exported per quarter (3.5) x 100 Denominator: MT of domestic edible salt needs per quarter | Collection Method: Review of production and sales reports, import/export orders, personal contact with producers/importers/exporters Data Source: Salt industry, import/export traders, local and central Min Industry or Trade contacts, FDA (QAQC outcomes) - see indicator 5 | GAIN | • Reliable production data may be difficult to obtain through industry and government channels (especially for non-registered producers/importers). • Provide best estimates and indicate the source and likely accuracy of the data in monitoring reports and triangulate data with outcomes for objectives 7 and 2.1 to check reliability. • Reasonable estimates of total domestic edible salt needs and of iodised salt production/import/export are important to monitor the availability of iodised salt for the population plus likely leakage of non-iodised salt into the market. Overall it is important that every effort be made to obtain the most accurate supply data possible on a regular basis. • Production data should be dissaggregated by scale of production, including separation of data for salt cooperatives/salt banks so that this can be used both for programme management and for tracking of this indicator for partnership project evaluation. | National team to verify if baseline information available |  | 75% | Salt Commissioner QA laboratory results 2012-13 |  |  | Will request updates every 6 months. Should be possible once MIS fully functioning.
|  |  |  | 3.2 Proportion (%) of domestic edible salt requirements iodised (use where reliable QAQC systems not in place and only able to obtain information about iodised salt, not the quality of iodisation) | Numerator: MT iodised salt produced/imported (3.5) - (minus) MT iodised salt exported per quarter (3.3) x100 Denominator: MT of domestic edible salt needs |  |  |  | National team to verify if baseline information available |  | National team to verify if updated information available
|  |  |  | 3.3 Total production (MT) of a) adequately iodised salt b) all iodised salt by registered and non-registered producers To be used in calculation of 3.1 and 3.2 | a) MT adequately iodised salt b) MT all iodised salt Produced by registered and unregistered producers per quarter. |  |  |  | b) 5,370,000 MT | 2008-9 From Country Strategy June 2012 | b) 6,200,000 MT Some of this exported | 2011-12 Salt Dept Report
|  |  |  | 3.4 Total import (MT) of adequately iodised salt Total import all iodised salt From registered and non-registered importers To be used in calculation of 3.1 and 3.2 | MT adequately iodised salt produced MT all iodised salt produced produced by registered and unregistered producers per quarter. |  |  |  | National team to verify if baseline information available |  | 0 MT | 2011-12 Salt Dept Report |  |  | Shall I delete this indicator since no imports?
|  |  |  | 3.5 Total export of iodised salt. | MT iodised salt exported by registered/non-registered exporters per quarter |  |  |  | National team to verify if baseline information available |  | 228700 | 2011-12 Salt Dept Report
| 4 | To increase the use of adequately iodised salt by processed food producers. *Target foods will be identified as those contributing signficantly to salt intake, consumed across wealth quintiles and produced by major food processing facilities. |  | 4.1 Proportion (%) of target staple foods/condiments* produced using iodised salt | Numerator: Amount of iodised salt used in the production of these products by major food processors per quarter (indicator 4.2) x 100. Denominator: Amount of salt used in production of these products by major food processors per quarter. | Collection Method: Review reports salt sales to and purchase by food industry, personal contact with industry, food processing guidelines/recipes/policy Data source: Target processed food producers, Ministry of Industry/Trade, Major producers/importers of higher quality salt, National Food Chamber. | GAIN | • Identification of target foods/condiments produced using iodised salt to be assessed based on food industry or food chamber data, market data, focus groups and any existing dietary/food frequency survey information. • In some cases studies may be needed before foods can be identified and indicators 2.2 and 4.1 can be assessed. These will increase the global knowledge base for targeting USI
| 5 | To ensure that producers are conducting internal QC and meet national standards for iodine. | 5.1 Percentage of iodised salt facilities following SOPs for production of iodised salt. |  | Numerator: Iodised salt facility (production/import/repacker) with complete records (from SOP) for production of iodised salt x 100. Denominator: Total number of iodised salt facilities (production/import/ repacker) Disggregated by scale of production as appropriate. | Collection Method: Review facility quality manuals, SOPs, QC records, staff responsibilities. Need listing of production/import/repacking facilities (certified and uncertified). Data source: Salt commissioners dept. Private industry, Salt Bank Cooperatives, ICCIDD, information from objective 3 | GAIN | • The quality of information on salt production facilities and output (see objective 3) will also be important in determining accurate estimates for tracking achievements against this QAQC objective. • The 3 indicators here capture the main expectations for QAQC, in relation to the QAQC manual development, workshops, and planned tranings, which were aimed at medium and large scale producers. • The person designated as responsible for QC does not necessarily need to have the title of QC manager, however, it needs to be clearly identified as someone's specific responsibility. • Data from this objective (5) together with information on facility capacity and iodised salt production information (obj 3) can be used to determine the proportion (%) of national iodised salt produced or imported/repacked by facilities with improved QAQC as a result of the Partnership inputs. • Determination of these indicators should be broken down by production capacity with different expectations in terms of QAQC for each. Additional indicators may be needed in countries where the majority of salt comes from multiple small scale producers (to discuss prior to reporting). Could have up to 4 outcomes for each indicator), as follows: Small (cottage-scale) > 1,000 MT/annum Medium 1,000 – 4,999 MT/annum Large 5,000-9,999 MT/annum Very Large ? 10,000 MT/annum | National team to verify if baseline information available |  | QC/QA protocols followed in iodine monitoring laboratories under salt commissioner QC/QA protocols are followed by majority of the big iodised salt producers Can national team relate update to specific indicator re: # facilities with SOPs etc.? | 2013 Fifth year annual report BMGF |  |  | All salt production facilities are registered with the Salt Commissioner and are obliged to have SOPs. Whether iodisation is done in accordance with the SOP varies. Regulatory monitoring procedures should include a review of records and can help to verify whether SOPs in place, record keeping and remedial action implemented where needed. If Salt Dept cannot provide information, enter some qualitative statement about all producers having SOPs in place however only X % following them (as determined by regulatory monitoring checks)
|  |  | 5.2 Percentage of producers/importers/repackers with a designated staff person responsible for quality management |  | Numerator: Number of salt production/import/repacking facilities with designated staff person responsible for QAQC x 100. Denominator: Total number of salt production/import/repacking facilities. Dissaggregate by scale of production as appropriate |  |  |  | National team to verify if baseline information available |  | National team to verify if updated information available
|  |  |  | 5.3 Percentage of producers/importers/repackers with improved manual and procedures following the QAQC workshops and trainings | Numerator: Number of salt production/import/repacking facilities with improved quality manual and procedures following training through the Partnership x 100. Denominator: Total number of salt production/import/repacking facilities Disggregate by scale of production as appropriate |  |  |  | N/A | [5 empty] | Not so relevant for India since SOPs already well developed and being used. Keep indicator in case training is conducted and SOPs are imporved further.
| 6 | To ensure that food control departments are conducting external QC monitoring |  | 6.1 Percentage of production/import/repacking facilities inspected by responsible government department compared to the national workplan. | Numerator: Number of iodised salt facilities (production/import/repacker) visited by agreed government team x100 Denominator: Total number of iodised salt facilities (production/import/repacker) planned for inspection | Collection Method: Review workplan, inspection records, listing of FDA officials and responsibilities. Data source: Government inspection body (FDA), Min Industry, ICCIDD | GAIN | • The 2 indicators here along with indicator 14.1 (Sustainability sheet) capture the main expectations for QAQC, in relation to the QAQC manual development, workshops, and planned tranings. • Data from this objective (6) together with information on facility capacity and iodised salt production information (objs 5 & 3) can be used to determine the proportion (%) of national iodised salt produced or imported/repacked with inspection using improved QAQC methods as a result of the Partnership inputs. • Determination of this indicator should be broken down by production capacity and additional indicators may be required, as for indicator 5. | National team to verify if baseline information available |  | National team to verify if updated information available
|  |  |  | 6.2 Existence of improved regulatory monitoring manual and procedures following the QAQC workshops and trainings | Yes/No | Collection Method: Review FDA regulatory monitoring procedures in comparison with previous procedures. Data source: Government inspection body (FDA), Min Industry, ICCIDD |  |  | National team to verify if baseline information available |  | National team to verify if updated information available
| 7 | To ensure an adequate and reliable supply of KIO3 for the iodisation of edible salt | 7.1 Adequacy of KIO3 supply. % domestic needs for KIO3 for adequately iodised salt that are met. |  | Numerator: KIO3 distributed to the salt industry x 100. Denominator: Total requirement for KIO3 to enable adequately iodised salt production for > 90% all edible salt produced in the country. | Collection Method: Review of import records, Private industry records, GPF and UNICEF procurement records. Data source: Ministry of Industry/Trade (customs), GAIN GPF and UNICEF procurement, national KIO3 suppliers, salt iodisation facilities | GAIN | It should be possible to get a fairly accurate estimate of national (and facility-based) KIO3 supply. This can be triangulated with data from objective 3 to help assess sufficiency for adequate iodisation of all domestic edible salt. | National team to verify if baseline information available |  | National team to verify if updated information available |  |  |  | GAIn would not have access to these data directly since KIO3 is sold in the market on a business basis. To request from the Salt dept, but not sure if they will share it or not. If not, a qualitative statement about KIO3 being produced in country and in sufficient amount to meet national salt requirements, will be OK
|  |  |  | 7.2 Proportion of KIO3 supply funded by: a) the salt industry b) the Government. | Numerator: Current national KIO3 supply bought by a) the salt industry/b) Govt x 100. Denominator: Total current requirement for KIO3 to enable adequately iodised salt production for > 90% all edible salt produced in the country. |  |  |  | National team to verify if baseline information available |  | National team to verify if updated information available |  |  |  | All funded by salt industry
| 8 | To ensure that iodised salt is adequately distributed so that low income populations have access |  | 8.1 Percentage of publically distributed salt that is adequately iodised (publically subsidised distribution). Quantity of publically-subsidised & distributed salt (all should be adequately iodised according to regulations) | Numerator: MT of publically distributed salt adequately iodised salt. Denominator: Total salt distributed through public channels nationally (or assess at State level if more appropriate). Quantity by State (unit weight per 6 months or stated time period) | Collection Method: salt distribution records. Data Source: Responsible State department | GAIN/ UNICEF | To include PDS, MDM and ICDS as possible. Dissaggregate by mecahnism (PDS/MDM/ICDS) and by State as possible/needed, since only some States may provide detailed information, etc. | 13 States distribute iodized salt through the Public Distribution System. |  | 13 States distribute iodised salt via public distribution system. 2 more pending. National team to verify if data available re: % adequately iodised or quantity (population covered). | 2013 Fifth year annual report BMGF |  |  | If there is some idea of quantity salt or number of states at the start of the project this may provide good evidence of progress in terms of coverage for lower income groups etc.
| 9 | Good institutional capacity for implementation and enforcement of USI exists | 9.1 Clear regulatory monitoring protocols exist with defined responsibilities, activities and follow up (regulatory monitoring SOPs) |  | Yes No | Collection Method: Review FDA responsibilities and regulatory monitoring procedures. Data source: Government inspection body (FDA), Min Industry, ICCIDD | GAIN | Regulatory monitoring SOPs should include assessment of iodised salt production SOPs so no need for a separate sustainability indicator for internal QC | Legal framework for regulatory monitoring exists but mechanisms for corrective actions at production limited in absence of licensing of iodised salt producers. Salt supply data collected routinely, weak sampling, system, and usage | From Country Strategy June 2012 | National team to verify if updated information available - has the framework been strengthened?
|  |  | 9.2 KIO3 procurement (sufficient to meet domestic needs) can be maintained without external project funding. |  | a) Yes/No - Sufficient for needs b) Yes/No - maintained without external funds - through Government subsidies c) Yes/No - maintained without external funds - salt industry funds | Collection Method: Review financial reports for, and budgets related to, USI Data Source: Salt industry, Government, Outcomes for objective 7 | GAIN | Achievement for this indicator should be demonstrated by the presence of a proven self-sustaining cost recovery operation. | a) ? - Sufficient for needs? b) ? - maintained without external funds - through Government subsidies c) ? - maintained without external funds - salt industry funds |  | National team to verify if updated information available
OUTPUT: COMMUNICATION
OUTPUT: COMMUNICATION | 10 | To ensure that consumers and retailers are aware of and accept iodised salt | 10.1 Is packaged iodised salt clearly labelled as iodised (labelling or logo)? |  | Numerator: number of households with packaged salt with a clear label/logo showing that salt is iodised x 100 Denominator: number of households with pacakged salt (sample size) Or equivalent calculation if a market based survey Numerator: number of producers/importers producing packaged salt with clear label/logo showing that salt is iodised x 100 Denominator: number of prodcuers/importers trading in pacakged salt (sample size) | Collection Method: Included in household survey module: is salt packaged? Y/N Does packaged salt have a logo (a) or is it clearly labeled (b) indicating it is iodised? Or collection of data from salt situation analysis at production/import. Or market based food product survey. Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, FDA, MOI, NGO | UNICEF | To include where appropriate based on national situation - percentage of salt that is packaged | No information available |  | No information available
|  |  |  | 10.2 Percentage of consumers who know of the benefits of iodised salt (Knowledge) | Numerator: number of consumers who can correctly name at least one benefit of iodised salt x 100 Denominator: number of consumers asked (sample size) | Collection Method: Questions in a KAP survey or other household survey: Can you name the benefits of iodised salt?' Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, NGO | UNICEF | To include where appropriate based on national plans Can be adapted to be specific for a given geographic area/demographic group, depending on national plans | No information at the state or country level |  | No information available at the state or country level
|  |  |  | 10.3 Percentage of retailers in low coverage areas who know the benefits of iodised salt (Knowledge) | Numerator: number of retailers in low coverage areas who can correctly name at least one benefit of iodised salt x 100 Denominator: number of retailers in low coverage areas asked (sample size) | Collection Method: Questions at start & follow up for retailer RTK strategy or other retailer survey: Can you name the benefits of iodised salt?' Data Source: organisation implementing the data collection, e.g. MOH, UNICEF, NGO | UNICEF | To include where appropriate based on national plans - use where retailer RTK strategy implemented Can be adapted to be specific for a given geographic area/demographic group, depending on national plans | Prevent goitre: 84% (Rajasthan), 89% (Orissa), 83% (Chhattisgarh), 85% (Tamil Nadu); Prevent cretinism: 32% (Rajasthan), 17% (Orissa), 42% (Chhattisgarh), 26% (Tamil Nadu); Prevents birth complications: 8% (Rajasthan), 17% (Orissa), 41% (Chhattisgarh), 30% (Tamil Nadu) | Mapping and Documentation of Salt Trade Practices (2011)
| 11 | Communications are in place to secure sustained support of public, industry, medical and academic stakeholders and to ensure consumer acceptance of the USI effort | 11.1 Communication strategy in place to address identified programme challenges |  | Yes/No | Collection Method: Review plans and policies Data source: Various ministries/IDD committee | UNICEF | Evidence that a communication strategy is in place to address specific national challenges, that activities and focus are reviewed and adjusted as needed. | Program of public education and social mobilization in place but weak strategy, reach and visibility | From Country Strategy June 2012 | Program of public education and social mobilization in place but weak strategy, reach and visibility
|  |  | 11.2 Education about IDD and iodised salt are included as part of the school curriculum |  | Yes/No | Collection Method: Review curricula Data source: Ministry of Education | UNICEF | Indicate whether primary or secondary school curriculum. | Yes. IDD included in primary school curriculum in all 15 states |  | IDD included in primary school curriculum in all 15 states
|  |  | 11.3 Education about IDD and iodised salt is included as part of the food-technology training program, pre -service training of public employees (health and industry/commerce as relevant) and the pre and in service training of community health workers. |  | a) food-technology training program b)pre-service training for public employees Yes/No c) pre-service or in-service training for community workers: Yes/No | Collection Method: Review curricula Data source: Ministry of Industry/food technology institutes, | UNICEF | Where there is no signficant national food industry or food technology training programme, note this and use N/A as response to (a) | Not applicable to India |  | Not applicable to India
OUTCOME: SUSTAINABILITY
OUTPUT: ADVOCACY | 12 | Clear political commitment national ownership of the programme exists. | 12.1 Existence of legislation and regulations for the production and import (or trade) of adequately iodised salt for human consumption. |  | a) Yes/No - legislation - production b) Yes/No - regulations - production c) Yes/No - legislation - import/trade d) Yes/No - regulations - import/trade | Collection Method: Review national legislative, regulatory and budget documents Data Source: Relevant Govt Department | UNICEF | The definition of USI includes iodisation of all salt for human and animal consumption, including salt used in the food industry. Scoring for sustainability would put less weight on the salt for livestock feed. Some countries may have regulations without legislation and some may have legislation without clear accompanying regulations. | 2006 Reinstatement of the ban on sale of non iodized salt for human consumption. Implemented under the PFA | 2006 reinstatement. From Country Strategy June 2012 | PFA has been repealed since 2012. There is a central ban on the sale of non iodized salt for human consumption under FSSA
|  |  | 12.2 Scope of legislation/regulations includes mandatory iodization of a) table salt b) salt for processed food production c) salt for livestock feed |  | a) Yes/No b) Yes/No c) Yes/No | Collection Method: Review national legislative & regulatory documents Data Source: Relevant Govt Department | UNICEF |  | a) yes b) no c) no |  | a) yes; b) no; c) no
|  |  | 12.3 Elimination of IDD through USI is integrated into national: a) food and nutrition policies, b) annual plans and budget, c) annual policy and progress reviews. |  | a) food and nutrition policies: Yes/No b) annual plans and budget: Yes/No c) annual policy and progress reviews: Yes/No | Collection Method: Review national legislative and regulatory documents, database structure, reports, workplans and budgets Data Source: MOH, Min Industry, refer to outcomes for objectives 10 to 12 | UNICEF | This is an important indicator of sustainability and in line with the SUN strategy for mainstreaming all components of nutrition. | NIDDCP included in the Prime Minister’s 20 point program and reflected in 11th Five year Plan of GoI. Part of the National Rural Health Mission (NRHM). Not clear re: progress review and planning |  | a) yes; b) yes; c) yes
|  |  | 12.4 Systems are in place to monitor population iodine status and iodized salt use (as defined by legislation) |  | Yes - for iodine status No - for iodine status Yes - for iodized salt use No - for iodized salt use | Collection Method: Review nutrition survey plans, coordinating group workplans, national budget allocation for monitoring. Data source: MOH, multi sector coordinating group, refer to outcomes for objectives 10 & 12 | GAIN | This may be part of a larger system incorporating other nutrition, household, food industry etc. indicators; however, iodine specific information should feed into the annual review and planning process in indicator 13.3 | Iodine status: Central and State IDD Cells (MOHFW) monitor iodine levels and assess impact of USI, but not well functioning. Salt iodine: Salt dept for supply. Dependent on NFHS and DLHS surveys for HH use. | From Country Strategy June 2012 | Iodine status: still no established system. Plan for NFHS or other 2014-15 Salt iodine: MIS to monitor supply. HH use still less systematic (NFHS or other 2014) | 2013 Fifth year annual report BMGF
|  |  | 12.5 Existence of a a) national multi-sector coordination body coordinating the program for IDD elimination b) which includes the salt industry c) which has a work plan with clear roles and responsibilities d) is considered to function effectively |  | a) existence of coordination body: Yes/No b) salt industry included in coordination body: Yes/No c) work plan exists and defines clear roles and responsibilities: Yes/No d) functions effectively: Yes/No/Sometimes | Collection Method: Review official authorisation and outline of functions for coordinating body, national workplans, meeting minutes Data Source: Government documents, National workplan Reports on workplan progress | UNICEF | • The IDD secretariat can be taken to mean an independent group that meet for iodine specifically or a group who meet as part of a national micronutrient committee or similar and include issues related to iodine nutrition. • It may not be possible or relevant for salt industry representatives to participate in all meetings, however, there should be good evidence that they are consulted on programme strategy where relevant, e.g. revision of QAQC protocols, development of social marketing messages, etc. • For sub-indicator (d) the information will be somewhat subjective but should take into account whether the group meets sufficient regularity to report and review progress against the work plan. In situation where (a-c) are all "Yes" but (d) is "no" kindly provide additional qualitative feedback about the basis for this assessment. | a) Central Steering Committee & Program Implementation Committee exist b)? C) no d) no | From Country Strategy June 2012 | a) Yes - National Coalition for Sustained Iodine Intake (NSCII). Partner’s Working Group under the SCO. Coalition of partners (National and in 2 States) b) Yes C) Yes D) Yes | 2013 Fifth year annual report BMGF
--- The USI country team may include additional indicators for each section as necessary ---