Annex F: Project Logframe and Targets

| PROJECT NAME | Myanmar Arteminsinin Resistance Containment Plan (Private sector component: Rapid monotherapy replacement) |
| --- | --- |
| IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (end of project) | Assumptions: Sentinel site surveillance within Myanmar is allowed by GoM and completed in a timely manner (with results disseminated to MARC partners); Spread of resistant P.falciparum parasites follows previous patterns observed with antimalarials such as chloroquine (i.e. SE Asia westwards to South Asia and then to sub-Saharan Africa) |
| To prevent (or at minimum significantly delay) the spread of artemisinin resistant Plasmodium falciparum parasites within Myanmar and beyond its borders | Parasite clearance rates in eastern Myanmar | Planned | 25% (artesunate) on China border; 10-20% (one ACT) on Thai border; ACT treatment failure rate currently <10% | No decrease in parasite clearance rate from baseline | No decrease in parasite clearance rate from baseline | No decrease in parasite clearance rate from baseline |  |
|  |  | Achieved |  |  |  |  |  |
|  |  |  | Source |  |
|  |  |  | Sentinel site surveillance, collected by WHO within the MARC framework, indicating the extent of artemisinin resistance in eastern Myanmar (and other regional sites in Asia and sub-Saharan Africa as appropriate.) |  |
|  | Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  |
|  |  | Planned |  |  |  |  |  |
|  |  | Achieved |  |  |  |  |  |
|  |  |  | Source |  |

| OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (end of project) | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-standard antimalarials in the private sector (particularly artesunate monotherapy), replaced with government approved and quality assured ACT, and sub-optimal dosing reduced among the target population in eastern Myanmar. | % target population (disaggregated by age and gender) with suspected malaria in the last two weeks who received a nationally approved, quality-assured artemisinin-based combination therapy (ACT) within 24 hours of the onset of fever | Planned | 21% (442,246) |  |  | 83% (1,315,624) | Household surveys can be implemented within the target area and complement that being conducted under 3DF; PSI is permitted by donors and GoM to sell through the private sector in Myanmar; Phased diagnostics scale up in the informal private sector; Main biological risk groups vary from location to location due to variance in transmission intensity (in some areas children under five years-old living in or near forested areas are most at risk, in others it is adult men migrating through the forest); Monotherapy ban is enforced, but not introduced too early (i.e. prior to ACT roll out). |
|  |  | Achieved |  |  |  |  |  |
|  |  |  | Source |  |
|  |  |  | Baseline: MARC document (to be confirmed/improved with baseline population-based HH survey in 2011). Target: Population-based HH survey in 2014. |  |
|  | Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (end of project) |  |
|  | % target population (disaggregated by age and gender) with suspected malaria in the last two weeks who received a full course of a nationally approved, quality-assured ACT within 24 hours of the onset of fever | Planned | 21% (442,246) |  |  | 79% (1,258,756) |  |
|  |  | Achieved |  |  |  |  |  |
|  |  |  | Source |  |
|  |  |  | Baseline: MARC (as above). Nearly all those receiving ACT currently do so for free from a formal provider with some supervision, PSI therefore assumes full courses are provided. If full courses are provided at the same cost or lower as the current monotherapy partial treatment course, PSI anticipates full ACT doses being dispersed to 90% of consumers in the private sector (with the assistance of supporting interventions aimed at providers). Data to be confirmed/improved with population-based HH survey in 2011. Target: Population-based HH survey in 2014. |  |
|  | Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (end of project) |  |
|  | % target population (disaggregated by age and gender) with suspected malaria in the last two weeks who completed a full course of a nationally approved, quality-assured ACT within 24 hours of the onset of fever | Planned | 19% (411,289) |  |  | 73% (1,170,643) |  |
|  |  | Achieved |  |  |  |  |  |
|  |  |  | Source |  |
|  |  |  | Baseline: Assumption that a maximum of 7% of those who receive a full treatment fail to adhere to the regimen once the supply chain and provider behavior are addressed. To be confirmed/improved with population-based HH surveys. Target: Population-based HH survey in 2014. |  |
| INPUTS ($) | DFID ($) | BMGF ($) | Govt ($) | Other (PI) ($) | Total ($) | DFID SHARE (%) |
|  | $ 24,378,152 | $7,500,000 | $ - | $ 1,912,171 | $ 33,790,323 | 72% |
| INPUTS (HR) | DFID (FTEs) |  |  |

| OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increased opportunity, ability and motivation of private sector providers to effectively prescribe and dispense nationally approved, quality assured ACT. | % target outlets with nationally approved and quality assured first-line ACT in stock at time of survey | Planned | 0% | 50% | 90% | 95% | Supply chain not interrupted by conflict, currency or constitutional changes. Initial estimated volume of ACTs inserted at the top of the supply chain is sufficient. Import regulations do not change significantly, affecting procurement planning and supply chain management. Mystery client methodology appropriate for more rural communities. Outlet survey data is cross-referenced with household survey data (as per ACTwatch methodology). |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Baseline: Rapid supply chain assessment results from 2010 (limited sample), to be confirmed/improved with nationally representative outlet surveys/audits in 2011. Milestones and Target: Annual outlet/audit surveys. |  |
|  | Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (end of project) |  |
|  | % target outlets with no reported stock-out of nationally approved and quality assured first-line ACT lasting more than 1 week within the past 3 months | Planned | n/a | TBD | TBD | TBD |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Annual outlet survey/audits |  |
|  | Output Indicator 1.3 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
|  | % target outlets selling nationally approved, quality assured ACT at a price less than or equal to the cost of a typical dose of the most common artemisinin monotherapy at baseline | Planned | n/a | 85% | 85% | 85% |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Annual outlet survey/audits |  |
|  | Output Indicator 1.4 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
|  | % target outlet providers that correctly state the recommended first line ACT treatment for uncomplicated malaria | Planned | TBD | TBD after baseline | TBD after baseline | TBD after baseline |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source: |  |
|  |  | Annual outlet survey/audits |  |
|  | Output Indicator 1.5 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
|  | Volumes of antimalarials sold/distributed to consumers in the past 7 days. Volume data will be disaggregated by: 1) quality assured (QA) ACTs; 2) non-QA ACTs; 3) artemisinin monotherapies 4) non-artemisinin monotherapies. | Planned | ACT (0%) 0 treatments/wk AMT (42%) approx. 17,501 treatments/wk | ACT (23%) approx. 8,653 treatments/wk AMT (23%) approx. 8,847 treatments/wk | ACT (40%) approx. 13,794 treatments/wk AMT(5%) Approx 1,850 treatments/wk | ACT (36%) approx. 10,936 treatments/wk AMT (0%) 0 treatments/wk |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Baseline: Extrapolation from a rapid supply chain assessment in 2010. This is to be built upon with much more thorough baseline outlet surveys/audits - for all antimalarials - and a more rigorous and representative supply chain assessment (by LSHTM) in 2011. Therefore all baseline and milestone information above is provisional and also based on target area only. Milestones and Target: Annual outlet/audit surveys. |  |
| IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
| 25% | % target outlet providers who treat a "mystery client" with suspected malaria using a full course of ACT and providing instructions for correct use. | Planned | 0 | 35% | 89% | 90% |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source | RISK RATING |
|  |  | Baseline: Initial mystery client survey 2011. Milestones and Target: Annual mystery client surveys to be cross referenced with household and outlet surveys. |  |
| INPUTS ($) | DFID ($) | BMGF ($) | Govt ($) | Other (PI) ($) | Total ($) | DFID SHARE (%) |
|  | $ 4,480,162 | $1,378,333 | $- | $ 351,415 | $ 6,209,910 | 72% |
| INPUTS (HR) | DFID (FTEs) |  |  |

| OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increased opportunity, ability and motivation of the target population in eastern Myanmar to promptly and effectively treat suspected malaria with a nationally approved and quality assured ACT. | % target population (disaggregated by age and gender) who name a nationally approved and quality assured first-line ACT as the most effective treatment for malaria | Planned | TBD |  |  | 70% | PSI able to conduct representative household surveys. Self-reported behavior of respondents mirrors reality. Target audience able to differentiate between antimalarials and ACTs. |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Population-based household surveys, cross-referenced against outlet surveys/audits. |  |
|  | Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  |
|  | % target population (disagregated by age and gender) who can correctly state the treatment regimen for a nationally approved and quality assured ACT | Planned | TBD |  |  | 60% |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Population-based household surveys, cross-referenced against outlet surveys/audits. |  |
| IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  |
| 70% | % target population (disagregated by age and gender) who can name a source where a nationally approved and quality assured first-line ACT can be purchased | Planned | TBD |  |  | 80% |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source | RISK RATING |
|  |  | Population-based household surveys, cross-referenced against outlet surveys/audits. |  |
| INPUTS ($) | DFID ($) | BMGF ($) | Govt ($) | Other (PI) ($) | Total ($) | DFID SHARE (%) |
|  | $ 18,463,180 | $5,680,244 | $ - | $ 1,448,213 | $ 25,591,637 | 72% |
| INPUTS (HR) | DFID (FTEs) |  |  |

| OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increased opportunity, ability, and motivation of private sector providers to conduct a rapid diagnostic test prior to the appropriate prescription and dispensing of nationally approved, quality assured ACT. | % target outlets with nationally approved and quality assured RDTs in stock at time of survey | Planned | 0% | 0% | 5% | 18% | Policy allows trained informal providers to conduct RDTs. Providers can be motivated to conduct RDTs despite the potential loss of revenue resulting in negative tests. |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Annual outlet survey/audits. |  |
|  | Output Indicator 3.2 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
|  | % target outlet providers that correctly state the 5 key steps in conducting a rapid diagnostic test for malaria | Planned | 0% | 0% | 5% | 18% |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source |  |
|  |  | Annual outlet survey/audits. |  |
| IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone Year 1 | Milestone Year 2 | Target (end of project) |  |
| 5% |  | Planned |  |  |  |  |  |
|  |  | Achieved |  |  |  |  |  |
|  |  | Source | RISK RATING |
| INPUTS ($) | DFID ($) | BMGF ($) | Govt ($) | Other (PI) ($) | Total ($) | DFID SHARE (%) |
|  | $ 1,434,810 | $ 441,423 | $ - | $ 112,543 | $ 1,988,776 | 72% |
| INPUTS (HR) | DFID (FTEs) |  |  |

| OUTPUT 1 | ACTIVITY 1.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Increased opportunity, ability, and motivation of private sector providers to effectively prescribe and dispense nationally approved, quality assured ACT. | Conduct baseline research | Baseline studies complete by end of Q2 | Target price points agreed by end of Q2 |  | Access permission block research. Delays in DHA/PPQ approval, and/or price uncertainties complicate choice of ACT. Contractual wrangling with distributors. Monotherapy ban put in place too quickly, disrupting the market. | Dr. Tin Aung, Director of Strategic Information |
|  | ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Replace AMT with ACT distribution | ACT agreed and ordered in first month | Contract with distributor(s) signed and first ACTs sold by end of Q2 | 9 million treatments sold by end of project |  | International Advisor for Malaria |
|  | ACTIVITY 1.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Develop a provider-targeted behavior change communications campaign | Communication plan developed for health providers by end of Q2, including detailing support materials | Communications campaign launched and 132 Detailers deployed and active in Q3 |  |  | Aung Thura, Senior Director Social Marketing |
|  | ACTIVITY 1.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Undertake advocacy activities to prevent the renewal of FDA registration of AMT | New registrations and license renewals of oral monotherapies are stopped by FDA once the replacement of AMT with ACT is under way |  |  |  | External Relations Director, Malaria |

| OUTPUT 2 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| --- | --- | --- | --- | --- | --- | --- |
| Increased opportunity, ability, and motivation of the target population in eastern Myanmar to promptly and effectively treat suspected malaria with a nationally approved and quality assured ACT. | Develop a user-targeted behavior change communications campaign | Communication plan developed for users by end of Q2 | Communication materials produced and tested, campaign placed and aired from Q3 |  | Delays in censor's approval of campaign materials | Aung Thura, Senior Director Social Marketing |
|  | ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
| OUTPUT 3 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer |
| Increased opportunity, ability, and motivation of private sector providers to conduct a rapid diagnostic test prior to appropriately prescribe and dispense nationally approved, quality assured ACT. | Develop plan, and gain no-objection from policy makers (plan to cover BCC/detailing approach and incentives, pricing structure, protocols for non-Pf treatment, response to negative tests etc.) | Pilot of RDTs with informal providers under way in year 1 | Plan agreed by end year 1 |  | Delays in policy approval for training informal providers | Malaria Programme Director External Relations Director, Malaria |
|  | ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | ToT IPCs in RDT. IPCs train providers in the field. | 1,900 outlets trained by end of yr 2 | 7,000 outlets trained by end of yr 3 |  |  | Malaria Programme Director |
|  | ACTIVITY 3.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer |
|  | Supply RDTs to trained ommunity Drug Sellers, collect data and used RDTs | 250,000 RDTs used correctly in yr 2 | 950,000 RDTs used correctly in yr 3 |  |  | Malaria Programme Director |

# Footnotes

MARC Impact Goal

WHO working definition: (1) An increase in parasite clearance time, as evidenced by 10% of cases with parasites detectable on day 3 after treatment with an ACT (suspected resistance); or (2) Treatment failure after treatment with an oral artemisinin-based monotherapy with adequate antimalarial blood concentration, as evidenced by the persistence of parasites for 7 days, or the presence of parasites at day 3 and recrudescence within 28-42 days (confirmed resistance).

Within the MARC framework, WHO is reviewing current sentinel surveillance data for Myanmar and is in the process of expanding and improving surveillance. PSI anticipates having an improved baseline with standardized methodology before drugs are deployed, and annual data with which to monitor this indicator.

As described in MARC section 8.7.1.”Monitoring and surveillance to assess Artemisinin resistance” WHO will conduct Therapeutic Efficacy Studies annually in 9 sites nationwide, and establish a further 20 sites using microscopy to monitor Day 3 parasite loads.

Quality assured refers to ACTs that meet stringent regulatory authority approval and WHO pre-qualified status.

An additional 7% are treated with CQ (for P.vivax malaria).

Ngasala, B.E., et al. (2011). Effectiveness of artemether-lumefantrine provided by community health workers in under-five children with uncomplicated malaria in rural Tanzania: an open label prospective study. Malaria Journal 2011, 10:64, Smithuis, F. et al. ( 2006). Efficacy and effectiveness of dihydroartemisinin-piperaquine versus artesunate-mefloquine in falciparum malaria: an open-label randomized comparison.  Lancet 2006; 367: 2075–85.

The relatively large number of indicators associated with this output reflect international best practice for pharmaceutical outlet/audit surveys (see notes re: M&E in narrative and appendices) and mirror those used for the BMGF-funded ACTwatch project. Combined, they also relate to the DFID Malaria Framework for Results [output] Indicator (f); Average availability of 14 selected essential medicines in public and private health facilities, plus a first-line ACT for the treatment of uncomplicated malaria.

Target outlets are all providers in the private sector able to stock and dispense antimalarials.

Number of target outlets to be determined. Estimates range from 10-50,000.

This particular milestone could differ significantly from that stated here due to the predicted rapidity of the  "switch" once ACT is available, monotherapies are banned and old stocks of monotherapies are sold (typically only 3 months of stock are carried).

This will be inflation linked. Influence over this will be limited.

Not applicable as no outlets currently sell ACT at the same price as a typical monotherapy.

Published data suggests that treatment compliance is significantly improved when interventions focus on providing effective treatment, provider knowledge and behavior, packaging and provision of correct dosages. Yeung and White (2005) Trop. Med. Int. Health. vol 10, no.2: pp 121-138.

Target population defined as total population within target townships (risk associated primarily with proximity to forest cover).

For consistency with the BMGF format Budgets, costs are presented here in US$.  For reference, the GBP equivalents are presented below, based on an exchange rate of 1.60 USD/GBP (31st March 2011)