## 2015-16
DFID countries
As reported in Annual Review submitted 29 July 2016
TREATMENTS
COUNTRY | FY 2015 to 2016 |  |  | Treated Population by age group (where available)
| Planned | Actual | Reported Coverage | SAC | Adults | Comments
Cote d'Ivoire | 579653 | 1409871 | 85.03% (March 2016) 63.71% (April 2016) | 1409871 | 0 | In April, two districts were not treated which explains a lower reported coverage
DRC | 1500000 | 1487821 | 83% | 1487821 | 0 | When all the treatment numbers by health zones are added, the total figure obtained is 1,572,752. What is reported in the annual report is 1,487,821. There is an error in the Excel formula used in the annual report and the 2 last health zones (Kalamba and Kapanga) were not included in the formula.
Ethiopia | 5359117 | 8179236 | 73.99% (Apr 2015) 78.68% (Nov 2015) | - | - | Significant increase in numbers treated caused by first treatment round being delayed from from March 2015 to April 2015 (and therefore between two operational years).
Liberia | 100000 | 0 | - | - | - | PCT delayed
Malawi | 6298402 | 6188939 | 90% | 4066693 | 2122246
Mozambique | 5064859 | 4436484 | 89.7% | - | -
Niger | 110050 | 89442 | 81.27% | 38813 | 50629 | One district only (Say). Remainder delayed to 16/17
Tanzania | 4323628 | 2920958 | 77.2% | 2920958 | 0
Uganda | 1209146 | 890089 | 84.5% | 890089 | 0
Zambia | 960330 | 0 | - | - | - | PCT delayed
Zanzibar | 2216068 | 1499429 | 73.70% (June 2015) 82.70% (Dec 2015) | - | -
Total | 27721253 | 27102269 |  | 10814245 | 2172875
PCT delayed to 2016/17
All other countries
TREATMENTS
COUNTRY | FY 2015 to 2016 |  |  | Treated Population by age group (where available)
| Planned | Actual | Reported Coverage | SAC | Adults | Comments
Burundi | 2538631 | 717141 | 88.5% | - | - | Elimination project suspended and target numbers were reduced.
Madagascar | 1406755 | 1278388 | 72.6% | 1278388 | 0
Mauritania | 0 | 0* | - | - | - | Awaiting final treatment report
Nigeria | 0 | 0 | - | - | -
Rwanda | 327750 | 212224 | 72% | 212224 | 0
Senegal | 0 | 0 | - | - | -
Sudan | 2800000 | 3084874 | Not available | - | -
Yemen | 400902 | 356803 | 89% | 356803 | 0
Total | 7474038 | 5649430 |  | 1847415 | 0
*Treatment numbers pending
Note on C14: Jun-16 treatment numbers preliminary
Note on C15: Still missing three districts.