## SCH Treatment 140415
Reported by SCI | [6 empty] | Added by GiveWell
Total at 10/03/2015 | [6 empty] | Alan's note in email with this file: "We are still waiting for a report from Rwanda and Burundi"
SCH ONLY | [7 empty] | Plans | Estimates (for comparison) |  | Estimates compared to Plans
COUNTRY | FY1 | FY2 | FY3 | FY4 | FY5 | TOTAL | Country | FY5 Plans | Apr-2015 Report | FY5 + April15 Report | Difference | % Difference
| Oct 10 - Mar 11 | Apr 11- Mar 12 | Apr 12 - Mar 13 | Apr 13 - Mar 14 | Apr 14 - Mar 15 | Oct 10 -Mar 15 |  | Source: SCI report to GiveWell (September 2014), Annex 1 | Source: SCI's ICOSA Mid-Year Report to DFID, 2015, Pg 9 | - | - | -
Cote d'Ivoire | 0 | 0 | 649859 | 853708 | 2821040 | 4324607 | Cote D'Ivoire | 5400000 |  | 2821040 | -2578960 | -47.76%
Liberia | 0 | 17400 | 0 | 625632 | 0 | 643032 | Liberia | 500000 |  | 0 | -500000 | -100%
Malawi | 0 | 2071817 | 2037487 | 0 | 4305956 | 8415260 | Malawi | 5600000 |  | 4305956 | -1294044 | -23.11%
Tanzania | 0 | 0 | 122996 | 2062685 | 2100000 | 4285681 | Tanzania | 600000 |  | 2100000 | 1500000 | 250%
Mozambique | 0 | 2391871 | 1819000 | 5816716 | 4257365 | 14284952 | Mozambique | 7000000 | 3300000 | 7557365 | 557365 | 7.962%
Zambia | 0 | 19800 | 0 | 36929 | 988023 | 1044752 | Zambia | 2600000 |  | 988023 | -1611977 | -62%
Niger | 0 | 482028 | 272994 | 1338453 | 966042 | 3059517 | Niger | 2100000 |  | 966042 | -1133958 | -54%
Uganda | 0 | 308305 | 0 | 646246 | 23017 | 977568 | Uganda | 400000 |  | 23017 | -376983 | -94.25%
Zanzibar | 0 | 945282 | 1059318 | 1694264 | 1610281 | 5309145 | Zanzibar | 2600000 |  | 1610281 | -989719 | -38.07%
DRC | 0 | 0 | 0 | 0 | 1630700 | 1630700 | DRC | 1700000 |  | 1630700 | -69300 | -4.076%
Yemen | 2124436 | 1862245 | 10240903 | 3496013 | 7224480 | 24948077 | Yemen | N/A |  | N/A | N/A | N/A
Ethiopia | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Ethiopia | 3700000 | 3400000 | 3400000 | -300000 | -8.108%
Madagascar | 0 | 0 | 0 | 0 | 151052 | 151052 | Madagascar | 300000 |  | 151052 | -148948 | -49.65%
Total | 2124436 | 8098748 | 16202557 | 17970646 | 26077956 | 70474343 | Total (planned and reported) | 32500000 | 6700000 | 25553476 | -6946524 | -21.37%
Cummulative Total | 2124436 | 10223184 | 26425741 | 44396387 | 70474343
[7 empty] | Burundi | 660000 |  | N/A
[7 empty] | Rwanda | 200000 |  | N/A
[7 empty] | Sudan | 4500000 |  | N/A
[7 empty] | Total (planned) | 37860000