## 8th Aug 2015
Givewell Query | Description of relevant SCI activity | Document | Document Reference number | Responsibility/Owner | Due Date | Action Status | File status
Spending tracking, including spending in countries | The development of the enhanced programme and financial management tools with assistance from Accenture Development Partners (ADP) has established a framework for planning, delivery and reporting progress against targets and timelines are being rolled out and reviewed to ensure they are as streamlined as possible. Processes have focused very much on the tracking of funds sent to country. SCI has also invested in the finance function including a FInancial Director with extensive overseas experience to provide appropriate skill sets to support the programme. The roll out of monthly financial reporting is in progress and will aid more effective tracking of the financial performance of each country. Monthly variance analysis is being included as part of the monthly finance meeting with Programme Managers to assist with forecasting and tracking of perforamance. An assessment tool for countries to report on SCI's programme and financial management is under development and has ben piloted. This will allow SCI to receive feedback from countries and identify areas for improvement. | SCI Process maps for financial management tools | 1
|  | Job description of Financial Director and CV current post holder | 2
|  | Template for country programme budget | 3
Revenue tracking | SCI's Finance Director is developing a more comprehensive SCI financial strategy that will focus on revenue tracking to be completed by Dec 2015. Finance policies and a reference manual are in development. To assist this SCI will invest in additional Accounting Software that will interface with the Imperial College systems but will allow a greater level of granularity of data and allow reports to be generated in a more timely manner. Resources have been allocated from Imperial College central finance function to assist in the development and implementation of the appropriate software. | Scoping document | 4 | Blandine/Finance team | COB 19/08/15 | completed | populated
Funds held at start and end of a reporting period | The new accounting software package will allow for more timely reporting of funds held at any one time. In addition analysis of variance against budget at the country level is also being undertaken to identify areas ofopportunity for efficiency. Comparision across countries can also provide valuable data. | Budget versus actuals summary for DFID countries | 5
Plans for Next year and Fundraising goals | At SCI's Board meeting the Board reveiwed SCIs progress against the targets set out in the Straetgic plan. In light of the progress made the Board strongly advised that SCI should increase its target from 200 million treatments by 2018 to 300 million. This will require adjustment to the fund raising targets and also a review of the countires in which SCI is currently delivering. The SCI team are currently reviewing information from Nigeria to see whether this fulfills the criteria for inclusion as one of SCIs supported country programmes and predicted treatment numbers. An adjusted framework detailing the target treatments and fundrasing targets for 2016 -2018 will be reveiwed by the Advisory Board when it next meets on the 30th September 2015. This will then need to be discussed with in country partners and agreed by December 2015. | Board meeting draft minutes 10 July 2015 | 6
|  | Board meeting presentation Progress against target 10 July 2015 | 7
|  | XL sheet supporting progress against target presentation 10 July 2015 | 8
Reserves Strategy | As part of the development of an overall SCI Financial Policy the new Finance Director has drafted a Reserves Strategy. This will be further discussed at the Board Meeting on the 30th September and with Imperial College Central Finance Function with the aim of finalising by December 2015. | Draft Reserve stratgy concept note Aug 2015 | 9
Potential sources of funding | SCI convened a meeting of its major high networth donor and an external fundraiser to discuss the key areas that would need to be covered by an more comprehensive SCI fund raising strategy. SCI is also working very closely with the Imperial College Fundraising team (Imperial Advancement) in the development of appropriate approaches to future funding streams. To support this SCI is implementing Raiser's Edge CRM tool. | Annex 4 from Board meeting - Fundraising strategy 10 July 2015 | 10
| SCI has also idetified an immediate need for a Communications Officer and this will be advertised shortly with the aim of having someone in post by Nov/Dec 2015. | Communication Officer Job Description | 11 |  |  |  | populated
Cost effectiveness analysis
Cost effectiveness data and cost per treatment | SCI has participated in and convened a number of meetings with other NTD stakeholders to standardise Value for Money (VFM) metrics. SCI has also worked with other partners on WHO Tool for Integrated planning and costing http://www.ntdenvision.org/resource/tipac_multilingual to capture all financial and economic inputs to country programmes. Some preliminary value for money (VFM) calculations have been carried out but require further analysis. SCI has also engaged a VFM Officer who is starting in mid October 2015. | Meeting notes from VFM disucssions Q1 2015 | 12 |  |  |  | populated
|  | Value for Money and Sustainabilty discussion and preliminary analysis from DFID Annual Review Aug 2015 | 13
|  | VFM Officer Job description June 2015 | 14 |  | COB 19/08/15