## Explanation
Explanation of the content of this spreadheet
Objective
Make clear and list the distribution and post-distribution monitoring reports we expect to receive between the start of March 2018 and the end of June 2018, and timing.

## 1. Reporting to end Jun18
| Updated: | 2018-07-11 | [9 empty] | Note: PDM is the new term used for previously called post-distribution check-ups (PDCUs)
|  |  |  | Narrative Report |  |  |  | Data
| Country | Location | Report Phase | Initial ETA | Revised ETA | Received | Delta | Initial ETA | Revised ETA | Received | Delta | Comment
1 | PNG 2017 | Morobe | Distribution | 2017-11-15 | 2018-01-01 | 2017-12-22 | 37 | 2017-11-15 |  | 2017-12-13 | 28
2 | PNG 2017 | Madang | Distribution | 2018-02-28 |  | 2018-03-15 | 15 | 2017-12-28 |  | 2018-03-08 | 70
3 | PNG 2017 | East Sepik | Distribution | 2018-06-03 |  | 2018-04-30 | -34 | 2018-04-03 |  | 2018-05-02 | 29
4 | PNG 2017 | EHP | Distribution | 2017-12-13 |  | 2017-10-29 | -45 | 2017-10-13 |  | 2017-11-07 | 25
5 | PNG 2017 | Sandaun | Distribution | 2018-05-02 |  | 2018-04-25 | -7 | 2018-03-02 |  | 2018-04-05 | 34
6 | PNG 2018 | Chimbu | Distribution | 2018-06-23 |  | 2018-06-12 | -11 | 2018-04-23 |  | 2018-05-04 | 11
7 | PNG 2018 | Jiwaka | Distribution | 2018-06-30 |  | 2018-06-01 | -29 | 2018-04-30 |  | 2018-05-10 | 10
8 | PNG 2018 | WHP | Distribution | 2018-06-28 |  | 2018-06-01 | -27 | 2018-04-28 |  | 2018-05-30 | 32
9 | Zambia 2018 | Eastern | Distribution | 2018-01-30 | 2018-04-30 | 2018-06-01 | 122 | 2018-01-30 |  | 2018-04-30 | 90
10 | Zambia 2018 | North-Western | Distribution | 2018-03-15 | 2018-06-15 | 2018-07-05 | 112 | 2018-03-15 |  | 2018-04-30 | 46 | Updated report received from NMEC 05-Jul-18 replaces version rcvd 14-Jun-18
11 | Zambia 2018 | Central | Distribution | 2018-03-22 | Imminent | 2018-07-05 | 105 | 2018-03-22 |  | 2018-05-30 | 69 | Rcvd from NMEC 05-Jul-18. Original report rcvd 01-Jun-18 was a training report
12 | Zambia 2018 | Western | Distribution | 2018-03-29 | Imminent | 2018-07-05 | 98 | 2018-03-29 |  | 2018-05-30 | 62 | Rcvd from NMEC 05-Jul-18. Report sent to AMF 24-Jun-18 was not narrative report as agreed
13 | Uganda 2017 | Eastern (Wave 2) | Distribution | 2017-07-25 |  | 2017-09-08 | 45 | 2017-05-25 |  | 2017-09-08 | 106
14 | Uganda 2017 | Eastern (Wave 3) | Distribution | 2017-08-13 |  | 2017-09-08 | 26 | 2017-06-13 |  | 2017-09-08 | 87
15 | Uganda 2017 | Western (Wave 4a) | Distribution | 2017-10-22 |  | 2018-03-25 | 154 | 2017-08-22 |  | 2018-03-25 | 215
16 | Togo 2017 | All regions | Distribution | 2018-01-01 |  | 2018-04-01 | 90 | 2017-10-25 |  | 2017-10-30 | 5
17 | Ghana 2016 | Greater Accra | PDM-18 | 2018-04-15 |  | 2018-05-30 | 45 | 2018-02-15 |  | 2018-02-28 | 13
18 | Ghana 2016 | Northern | PDM-24 | 2018-07-01 |  | 2018-06-25 | -6 | 2018-05-01 |  | 2018-06-01 | 31
19 | Ghana 2016 | Upper-West | PDM-18 | 2018-06-15 |  | 2018-06-14 | -1 | 2018-04-15 |  | 2018-03-02 | -44
20 | Malawi 2014/15 | Balaka | PDM-18 | 2018-01-01 |  | 2018-06-14 | 164 | 2017-11-01 |  | 2017-11-01 | 0
21 | Malawi 2014/15 | Balaka | PDM-24 | 2018-03-01 |  | 2018-06-14 | 105 | 2018-03-01 |  | 2018-03-01 | 0
22 | Malawi 2014/15 | Ntcheu | PDM-18 | 2018-08-15 |  | 2018-06-14 | -62 | 2017-07-15 |  | 2017-07-15 | 0
23 | Malawi 2014/15 | Ntcheu | PDM-24 | 2018-01-15 | 2018-03-15 | 2018-06-14 | 150 | 2018-01-15 |  | 2018-01-15 | 0
24 | Malawi 2014/15 | Dowa | PDM-30 | 2018-03-10 |  | 2018-06-14 | 96 | 2018-03-10 |  | 2018-03-10 | 0
25 | DRC 2016 | Nord-Ubangi | PDM-12 | 2017-07-15 |  | 2017-08-27 | 43 | 2017-05-15 |  | 2017-08-16 | 93
26 | DRC 2016 | Nord-Ubangi | PDM-18 | 2018-01-15 |  | 2018-06-07 | 143 | 2017-11-15 |  | 2017-11-29 | 14
| PNG 2017 | WHP | PDM-09 | 2018-05-14 | 2018-11-30 |  |  | 2018-10-30 |  |  |  | Not conducted
| PNG 2017 | Jiwaka | PDM-09 | 2018-05-14 | 2018-11-30 |  |  | 2018-10-30 |  |  |  | Not conducted
| Togo 2017 | Centrale | PDM-09 | 2018-05-25 | 2018-10-07 |  |  | 2018-09-07 |  |  |  | Move to 9 month PDMs in Togo so first PDM July, report in October
| Togo 2017 | Kara | PDM-09 | 2018-05-25 | 2018-10-07 |  |  | 2018-09-07 |  |  |  | Move to 9 month PDMs in Togo so first PDM July, report in October
| Togo 2017 | Plateaux | PDM-09 | 2018-05-25 | 2018-10-07 |  |  | 2018-09-07 |  |  |  | Move to 9 month PDMs in Togo so first PDM July, report in October
| Togo 2017 | Savanes | PDM-09 | 2018-05-25 | 2018-10-07 |  |  | 2018-09-07 |  |  |  | Move to 9 month PDMs in Togo so first PDM July, report in October
| Uganda 2017 | Various | PDM-06-Arm1 | 2018-05-10 | 2018-09-15 |  |  | 2018-08-10 |  |  |  | Delayed due to budget issues. PDM to be carried out July, report due mid-October
| Uganda 2017 | Various | PDM-06-Arm2 | 2018-05-10 | 2018-09-15 |  |  | 2018-08-10 |  |  |  | Delayed due to budget issues. PDM to be carried out July, report due mid-October
| DRC 2016 | Nord-Ubangi | PDM-24 | 2018-04-15 | 2018-08-15 |  |  | 2018-08-15 |  |  |  | Delayed due to budget issues. PDM carried out June/July.
27 | Ghana 2018 | All regions | Pre-Distribution | 2018-04-01 | 2018-05-01 | 2018-05-14 | 43 | N/A |  | - | - | Registration begins in Ghana 19-Jul-18
28 | Malawi 2018 | All districts | Pre-Distribution | 2018-04-01 | 2018-05-01 | 2018-06-07 | 67 | N/A |  | - | - | Registration begins in Malawi 02-Jul-18
NOT TAKING PLACE
| Malawi 2014/15 | Dedza | PDM-36 | 2017-11-15 | 2018-01-15 |  |  | 2017-11-15 |  |  |  | Not conducted as not considered value for money (Dedza PDM-30, 40% hang-up)
| DRC 2015 | Kasai-Occidental | PDM-24, PDM-30 | 2017-11-15 | 2018-01-15 |  |  | 2017-11-15 |  |  |  | Could not be carried out due to the increasing civil unrest going on at the time which would have put our partner teams in an unsafe position.
Formulas:
Revised ETA = EDATE([Initial ETA],2)

## 2. Future Reporting
Note: PDM is the new term used for previously called post-distribution check-ups (PDCUs)
|  |  | Narrative Report |  |  |  | Data
Country | Location | Report Phase | Initial ETA | Revised ETA | Received | Delta | Initial ETA | Revised ETA | Received | Delta | Comment
Not yet expected to have reported
Ghana 2016 | Greater Accra | PDM-24 | 2018-09-15 |  |  |  | 2018-08-15 |  |  |  | PDM 24 due to take place July 2018 (July 2016 distribution)
Ghana 2016 | Upper West | PDM-24 | 2018-12-01 |  |  |  | 2018-11-01
Ghana 2016 | Upper West | PDM-30 | 2019-06-01 |  |  |  | 2019-05-01
Uganda 2017 | Various | PDM-12-Arm1 | 2018-10-10 | 2018-11-10 |  |  | 2018-10-10 | 2018-11-10
Uganda 2017 | Various | PDM-18-Arm1 | 2019-04-15 |  |  |  | 2019-04-15
Uganda 2017 | Various | PDM-24-Arm1 | 2019-10-15 |  |  |  | 2019-10-15
Uganda 2017 | Various | PDM-30-Arm1 | 2020-04-15 |  |  |  | 2020-04-15
Uganda 2017 | Various | PDM-12-Arm2 | 2018-10-14 | 2018-11-14 |  |  | 2018-10-14 | 2018-11-14
Uganda 2017 | Various | PDM-18-Arm2 | 2019-04-14 |  |  |  | 2019-04-14
Uganda 2017 | Various | PDM-24-Arm2 | 2018-10-14 |  |  |  | 2018-10-14
Uganda 2017 | Various | PDM-30-Arm2 | 2020-04-14 |  |  |  | 2020-04-14
Uganda 2017 | Various | PDM-09-Arm3 | 2018-07-15 | 2018-09-15 |  |  | 2018-07-15 | 2018-09-15
Uganda 2017 | Various | PDM-18-Arm3 | 2019-04-15 |  |  |  | 2019-04-15
Uganda 2017 | Various | PDM-30-Arm3 | 2020-04-15 |  |  |  | 2020-04-15
Uganda 2017 | Various | PDM-09-Arm4 | 2018-07-15 | 2018-09-15 |  |  | 2018-07-15 | 2018-09-15
Uganda 2017 | Various | PDM-18-Arm4 | 2019-04-15 |  |  |  | 2019-04-15
Uganda 2017 | Various | PDM-30-Arm4 | 2020-04-15 |  |  |  | 2020-04-15
Uganda 2017 | Various | PDM-18-Arm5 | 2019-04-15 |  |  |  | 2019-04-15
Uganda 2017 | Various | PDM-30-Arm5 | 2020-04-15 |  |  |  | 2020-04-15
Uganda 2017 | Various | PDM-12-Arm6 | 2018-05-15 | 2018-09-15 |  |  | 2018-05-15 | 2018-09-15
Uganda 2017 | Various | PDM-18-Arm6 | 2019-01-15 |  |  |  | 2019-01-15
Uganda 2017 | Various | PDM-24-Arm6 | 2019-07-15 |  |  |  | 2019-07-15
Uganda 2017 | Various | PDM-30-Arm6 | 2020-01-15 |  |  |  | 2020-01-15
Togo 2017 | Centrale | PDM-18 | 2019-06-15 |  |  |  | 2019-05-15
Togo 2017 | Kara | PDM-18 | 2019-06-15 |  |  |  | 2019-05-15
Togo 2017 | Plateaux | PDM-18 | 2019-06-15 |  |  |  | 2019-05-15
Togo 2017 | Savanes | PDM-18 | 2019-06-15 |  |  |  | 2019-05-15
Togo 2017 | Centrale | PDM-27 | 2020-03-15 |  |  |  | 2020-02-15
Togo 2017 | Kara | PDM-27 | 2020-03-15 |  |  |  | 2020-02-15
Togo 2017 | Plateaux | PDM-27 | 2020-03-15 |  |  |  | 2020-02-15
Togo 2017 | Savanes | PDM-27 | 2020-03-15 |  |  |  | 2020-02-15
Zambia 2018 | Eastern | PDM-09 | 2019-01-15 |  |  |  | 2018-12-15
Zambia 2018 | North-Western | PDM-09 | 2019-04-15 |  |  |  | 2019-03-15
Zambia 2018 | Central | PDM-09 | 2019-04-15 |  |  |  | 2019-03-15
Zambia 2018 | Western | PDM-09 | 2019-04-15 |  |  |  | 2019-03-15
Zambia 2018 | Eastern | PDM-18 | 2019-10-15 |  |  |  | 2019-09-15
Zambia 2018 | North-Western | PDM-18 | 2020-01-15 |  |  |  | 2019-12-15
Zambia 2018 | Central | PDM-18 | 2020-01-15 |  |  |  | 2019-12-15
Zambia 2018 | Western | PDM-18 | 2020-01-15 |  |  |  | 2019-12-15
Zambia 2018 | Eastern | PDM-27 | 2020-07-15 |  |  |  | 2020-06-15
Zambia 2018 | North-Western | PDM-27 | 2020-10-15 |  |  |  | 2020-09-15
Zambia 2018 | Central | PDM-27 | 2020-10-15 |  |  |  | 2020-09-15
Zambia 2018 | Western | PDM-27 | 2020-10-15 |  |  |  | 2020-09-15
PNG 2018 | Eastern Highlands | Distribution | 2018-08-15 |  |  |  | 2018-08-15
PNG 2018 | Morobe | Distribution | 2018-09-15 |  |  |  | 2018-09-15
PNG 2018 | Madang | Distribution | 2018-10-15 |  |  |  | 2018-10-15
PNG 2018 | East Sepik | Distribution | 2018-11-15 |  |  |  | 2018-11-15
PNG 2018 | Sandaun | Distribution | 2018-11-15 |  |  |  | 2018-11-15
PNG 2018 | Western | Distribution | 2018-12-15 |  |  |  | 2018-12-15
PNG 2018 | Central | Distribution | 2018-12-15 |  |  |  | 2018-12-15
PNG 2018 | Western Highlands | PDM-09 | 2019-03-01 |  |  |  | 2019-02-01
PNG 2018 | Jiwaka | PDM-09 | 2019-03-01 |  |  |  | 2019-02-01
PNG 2018 | Chimbu | PDM-09 | 2019-02-01 |  |  |  | 2019-01-01
PNG 2018 | Eastern Highlands | PDM-09 | 2019-04-01 |  |  |  | 2019-03-01
PNG 2018 | Morobe | PDM-09 | 2019-05-01 |  |  |  | 2019-04-01
PNG 2018 | Madang | PDM-09 | 2019-06-01 |  |  |  | 2019-05-01
PNG 2018 | East Sepik | PDM-09 | 2019-07-01 |  |  |  | 2019-06-01
PNG 2018 | Sandaun | PDM-09 | 2019-07-01 |  |  |  | 2019-06-01
PNG 2018 | Western | PDM-09 | 2019-08-01 |  |  |  | 2019-07-01
PNG 2018 | Central | PDM-09 | 2019-08-01 |  |  |  | 2019-07-01
PNG 2018 | Western Highlands | PDM-18 | 2019-12-01 |  |  |  | 2019-11-01
PNG 2018 | Jiwaka | PDM-18 | 2019-12-01 |  |  |  | 2019-11-01
PNG 2018 | Chimbu | PDM-18 | 2019-11-01 |  |  |  | 2019-10-01
PNG 2018 | Eastern Highlands | PDM-18 | 2020-01-01 |  |  |  | 2019-12-01
PNG 2018 | Morobe | PDM-18 | 2020-02-01 |  |  |  | 2020-01-01
PNG 2018 | Madang | PDM-18 | 2020-03-01 |  |  |  | 2020-02-01
PNG 2018 | East Sepik | PDM-18 | 2020-04-01 |  |  |  | 2020-03-01
PNG 2018 | Sandaun | PDM-18 | 2020-04-01 |  |  |  | 2020-03-01
PNG 2018 | Western | PDM-18 | 2020-05-01 |  |  |  | 2020-04-01
PNG 2018 | Central | PDM-18 | 2020-05-01 |  |  |  | 2020-04-01
PNG 2018 | Western Highlands | PDM-27 | 2020-09-01 |  |  |  | 2020-08-01
PNG 2018 | Jiwaka | PDM-27 | 2020-09-01 |  |  |  | 2020-08-01
PNG 2018 | Chimbu | PDM-27 | 2020-08-01 |  |  |  | 2020-07-01
PNG 2018 | Eastern Highlands | PDM-27 | 2020-10-01 |  |  |  | 2020-09-01
PNG 2018 | Morobe | PDM-27 | 2020-11-01 |  |  |  | 2020-10-01
PNG 2018 | Madang | PDM-27 | 2020-12-01 |  |  |  | 2020-11-01
PNG 2018 | East Sepik | PDM-27 | 2021-01-01 |  |  |  | 2020-12-01
PNG 2018 | Sandaun | PDM-27 | 2021-01-01 |  |  |  | 2020-12-01
PNG 2018 | Western | PDM-27 | 2021-02-01 |  |  |  | 2020-01-01
PNG 2018 | Central | PDM-27 | 2021-02-01 |  |  |  | 2020-01-01
Ghana 2018 | Ashanti | Distribution | 2018-11-15 |  |  |  | 2018-10-15
Ghana 2018 | Brong-Ahafo | Distribution | 2018-11-15 |  |  |  | 2018-10-15
Ghana 2018 | Upper East | Distribution | 2018-11-15 |  |  |  | 2018-10-15
Ghana 2018 | Ashanti | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Ghana 2018 | Brong-Ahafo | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Ghana 2018 | Upper East | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Ghana 2018 | Ashanti | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Ghana 2018 | Brong-Ahafo | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Ghana 2018 | Upper East | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Ghana 2018 | Ashanti | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Ghana 2018 | Brong-Ahafo | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Ghana 2018 | Upper East | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Balaka | Distribution | 2018-11-15 |  |  |  | 2018-10-15
Malawi 2018 | Chikwawa | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Chiradzulu | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Dedza | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Dowa | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Kasungu | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Mangochi | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Mulanje | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Nkhotakota | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Ntcheu | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Phalombe | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Thyolo | Distribution | 2018-11-15 |  |  |  | 2018-11-15
Malawi 2018 | Balaka | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Chikwawa | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Chiradzulu | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Dedza | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Dowa | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Kasungu | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Mangochi | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Mulanje | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Nkhotakota | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Ntcheu | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Phalombe | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Thyolo | PDM-09 | 2018-08-15 |  |  |  | 2018-07-15
Malawi 2018 | Balaka | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Chikwawa | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Chiradzulu | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Dedza | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Dowa | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Kasungu | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Mangochi | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Mulanje | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Nkhotakota | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Ntcheu | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Phalombe | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Thyolo | PDM-18 | 2020-05-15 |  |  |  | 2020-04-15
Malawi 2018 | Balaka | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Chikwawa | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Chiradzulu | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Dedza | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Dowa | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Kasungu | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Mangochi | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Mulanje | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Nkhotakota | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Ntcheu | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Phalombe | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15
Malawi 2018 | Thyolo | PDM-27 | 2021-02-15 |  |  |  | 2021-01-15

## Ghana-KeyDates
Ghana 2016 PDMs - decision on when to stop
Info @ 02Jun18
Region | Dist. Date (midpoint) | PDM-06 | PDM-12 | PDM-18 | PDM-24 | PDM-30 | Registration Start 2018 Campaign | Distribubtion Start 2018 Campaign
Northern | 2016-04-01 | 2016-11-01 | 2017-05-01 | 2017-10-01 | 2018-04-01 | 2018-10-01 | 2018-05-25 | 2018-06-18
Greater Accra | 2016-07-01 | 2017-01-01 | 2017-07-01 | 2018-01-01 | 2018-07-01 | 2019-01-01 | 2018-10-10 | 2018-11-14
Upper West | 2017-03-01 | 2017-03-01 | 2017-09-01 | 2018-03-01 | 2018-09-01 | 2019-03-01 | NO NETS 2018 | NO NETS 2018
complete
still to perform
Proposal
Region | Dist. Date (midpoint) | PDM-06 | PDM-12 | PDM-18 | PDM-24 | PDM-30 | Registration Start 2018 Campaign | Distribubtion Start 2018 Campaign
Northern | 2016-04-01 | 2016-11-01 | 2017-05-01 | 2017-10-01 | 2018-04-01 | 2018-10-01 | 2018-05-25 | 2018-06-18
Greater Accra | 2016-07-01 | 2017-01-01 | 2017-07-01 | 2018-01-01 | 2018-07-01 | 2019-01-01 | 2018-10-10 | 2018-11-14
Upper West | 2017-03-01 | 2017-03-01 | 2017-09-01 | 2018-03-01 | 2018-09-01 | 2019-03-01 | NO NETS 2018 | NO NETS 2018
Complete
Perform
Do not perform