## PD
Table 1
2014/2015 LONG LASTING INSECTICIDE NET (LLIN) DISTRIBUTION PLAN
MASS POINT DISTRIBUTION CAMPAIGNS
NO | REGION | 2014 | 2015 | [11 empty] | 2015 Estimated Population | Estimated LLIN need | Comments
|  | NOV | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC
1 | VOLTA | [13 empty] | 2384939.7295 | 1324966.5164 | Distribution Completed | 1.8
2 | EASTERN | [13 empty] | 2907214.7833 | 1615119.324 | Distribution Completed | 1.8
3 | BRONG AHAFO | [13 empty] | 2576625.0799 | 1431458.3777 | Distribution Confirmed | 1.8
4 | WESTERN | [13 empty] | 2597701.0192 | 1443167.2329 | Distribution Confirmed | 1.8
5 | CENTRAL | [13 empty] | 2515605.3614 | 1397558.5341 | Pending | 1.8
6 | ASHANTI | [13 empty] | 5434995.9478 | 3019442.1932 | Pending | 1.8
7 | NORTHERN | [13 empty] | 2860446.847 | 1589137.1372 | Pending | 1.8 | bar: 2015 AUG
8 | UPPER EAST | [13 empty] | 1105385.3007 | 614102.9449 | Pending | 1.8 | bar: 2015 SEPT
9 | GT. ACCRA | [13 empty] | 4603793.0634 | Population to be covered to be estimated | Pending
10 | UPPER WEST | [13 empty] | 0 | 0 | No Distribution
| TOTAL | [13 empty] | 26986707.1322 | 12434952.2604
Note on B14: Author: minus 4 regions undertaking IRS
Note on B17: Author: No LLIN will be distributed in the region

## Sheet1
Table 1
LONG LASTING INSECTICIDE NET (LLIN) DISTRIBUTION PLAN (2014/2015/2016)
MASS POINT DISTRIBUTION CAMPAIGNS
REGION | 2015 Estimated Population | 2015 Estimated LLIN need | 2016 Estimated Population | 2016 Estimated LLIN need | 2014 | 2015 | [11 empty] | 2016
[5 empty] | NOV | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC
VOLTA | 2384939.7295 | 1324966.5164 | - | -
EASTERN | 2907214.7833 | 1615119.324 | - | -
BRONG AHAFO | 2576625.0799 | 1431458.3777 | - | -
WESTERN | 2597701.0192 | 1443167.2329 | - | -
CENTRAL | 2566065 | 1425591.6667 | - | -
ASHANTI | 5461933 | 3034407.2222 | - | -
NORTHERN | 2860448.647 | - | 2943402 | 1635223.3333
UPPER EAST | 1105385.3007 | - | 1124193 | 624551.6667
GT. ACCRA | 4603793.0634 | Population to be covered to be estimated | 4816174 | 2675652.2222
UPPER WEST | 0 | 0 | 786050 | 0
TOTAL | 27064105.623 | 10274710.3399 |  | 4935427.2222
Note on A14: MINUS 4 REGIONS WITH IRS
Note on A17: NO DISTRIBUTION IN REGION COS OF IRS