## Sheet1
| Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
Organisation set-up
Plan Nepal work in discussion with Nepalese colleagues
Visit Nepal - Agree plan & actions
- Establish office alongside Registrar
- Identify sentinal hospitals (5)
- Hire staff x 2
Plan Indian work in discussion with Indian colleagues
Visit India - Agree plan & actions
- Establish office alongside Registrar
- Identify sentinal hospitals (20-30)
- Hire staff x 4
Visit FAO in Rome to sign MOU
Obtain ethics for Indian and Nepalese hospital work | bar: Q1 to Q2
Train staff for data collection | bar: Q2
Pesticide legislative and policy analysis | bar: Q2 to Q5
Survey of cases presenting to hospital in India & Nepal | bar: Q3 to Q8
Analysis of data collected in the first six months | bar: Q5
Implications for pesticide regulation discussed with Registrars | bar: Q5
Discussions with Registrars and FAO re necessary regulation | bar: Q5 to Q6
Drafting of legislation in Nepal | bar: Q6 to Q7
Implementation of regulation in Nepal | [8 empty] | Currently unclear how rapidly legislation could progress | bar: Q7
Monitoring of legislation (continuing) | bar: Q7 to Q8
Discussion in India re need for cluster RCT to determine potential legislative effect | bar: Q5 to Q6
If cRCT needed, design and funding applications made | bar: Q6
Start planning trial groundwork | bar: Q8
If cRCT not needed, drafting of legislation | bar: Q6 to Q7
Implementation of regulation in India | [8 empty] | Currently unclear how rapidly legislation could progress | bar: Q7
Monitoring of legislation (continuing) | bar: Q7 to Q8
Evaluation | bar: Q8