## Sheet1
ANNEX B: PERFORMANCE ASSESSMENT FRAMEWORK
County: |  | Angola
Implementing Partner: |  | The MENTOR Initiative
Currency: |  | USD dollars
Periods Covered and Dates for Periodic Reports and Disbursment Requests
|  |  | PY1 | PY2 | P9 | P10 | P11 | P12 | PY3 | PY4 | PY5
Period Covered: from |  |  | 2013-03-25 | 2014-04-01 | 2015-04-01 | 2015-07-01 | 2015-10-01 | 2016-01-01 | 2015-04-01 | 2016-04-01 | 2017-04-01
Period Covered: to |  |  | 2014-03-31 | 2015-03-31 | 2015-06-30 | 2015-09-30 | 2015-12-31 | 2016-03-31 | 2016-03-31 | 2017-03-31 | 2018-03-31
Date Report Periodic Report Due |  |  | 2014-04-30 | N/A | 2015-07-31 | 2015-10-31 | 2016-01-31 | 2016-04-30 | N/A | N/A | N/A
Disbursement Request |  |  | Yes | N/A | No | Yes | No | Yes | TBD | TBD | TBD
Annual Report Due Date: |  |  | PY1: 2014-04-30; PY2: 2015-04-30; P9: 2016-04-30; P10: 2017-04-30; P11: 2018-04-30
Audit Report Due Date: |  |  | PY1: 2014-09-30; PY2: 2015-09-30; P9: 2016-09-30; P10: 2017-09-30; P11: 2018-09-30
Goals:
1 | To assist the MoH in achieving a significant reduction in the burden of soil-transmitted helminth and schistosomiasis infections in high burden areas of northern Angola
Impact / Outcome Indicator |  | Indicator | PY1: Baseline; P10: Targets; PY5: Comments:
|  |  | Value | Year | Source | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Impact |  | STH Prevalence Rate | TBD | 2014 | MoH Angola | N/A | TBD | N/A | TBD | N/A | Zaire and Uige are estimated to have high NTD transmission. Huambo is moderate NTD transmission.
Impact |  | Schistosomiasis Prevalence Rate | TBD | 2014 | MoH Angola | N/A | TBD | N/A | TBD | N/A
Impact |  | LF Prevalence Rate | TBD | 2014 | MoH Angola | N/A | TBD | N/A | TBD | N/A
Outcome 1.1 |  | Timely completion of national NTD workplans and guidelines. Angola participates in international NTD control activities.
Outcome 2.1 |  | Passive NTD treatment data is reported and effective enough for comparison against baseline mapping information
Outcome 3.1 |  | % coverage enrolled SAC through school based MDA | TBD | 2014 | MENTOR | 565,621/1,131,242 | TBD | TBD | TBD | TBD | 50% SAC in year 1, 85% in years following
Outcome 3.1 |  | % coverage of community based MDA | TBD | 2014 | MENTOR | N/A | 47/94 | 70/94 | 94/94 | 94/94 | 50% in year 2, 75% year 3, 100% years following
Outcome 3.1 |  | % coverage of at risk population | TBD | 2014 | MENTOR | N/A | TBD | TBD | TBD | TBD | TBD Post-mapping
Outcome 3.2 |  | % coverage enrolled SAC through school based MDA | TBD | 2014 | MENTOR | 565,621/1,131,242 | TBD | TBD | TBD | TBD | 50% SAC in year 1, 85% in years following
Outcome 3.2 |  | % coverage of community based MDA | TBD | 2014 | MENTOR | N/A | 47/94 | 70/94 | 94/94 | 94/94 | 50% in year 2, 75% year 3, 100% years following
Outcome 3.2 |  | % coverage of at risk population | TBD | 2014 | MENTOR | N/A | TBD | TBD | TBD | TBD | TBD Post-mapping
Outcome 3.3 |  | % coverage of community based MDA | TBD | 2014 | MENTOR | N/A | 47/94 | 70/94 | 94/94 | 94/94 | 50% in year 2, 75% year 3, 100% years following
Outcome 3.3 |  | % coverage of at risk population | TBD | 2014 | MENTOR | N/A | TBD | TBD | TBD | TBD | TBD Post-mapping
Outcome 3.4 |  | % Trained in Program Activities | TBD | 2014 | MENTOR | 3536/3177 | TBD | TBD | TBD | TBD
Outcome 4.1 |  | % School Coverage | TBD | 2014 | MENTOR | N/A | 1063/2127 | 2127/2127 | 2127/2127 | 2127/2127 | 50% schools year 2, 100% in years following
Program Objectives, NTD Macro Categories and Indicators
Objective No. | Objective Description
1 | Ministry of Health has sustainable integrated NTD program across 3 provinces and capacity to scale to national coverage
Outcome 1: Effective National NTD MOH Department and Provincial Coordination Comittees are in place and operational and competent in co-ordination, planning, procurement, supply chain and analysis for NTD control by project completion
2 | Primary Health Care System (PHC) in provinces has competency and delivers systematic NTD control
Outcome 1: Primary Health Care clinics able to accurately diagnose, record, treat and manage priority NTDs and quantify and monitor disease prevalence by project completion.
3 | The intensity of infection of schistosomiasis, lymphatic filariasis and intestinal worms in children, women and men reduced significantly from baseline.
Outcome 1: Treat 75% of eligible at-risk population for intestinal worms through mass drug administration (MDA) of albendazole by project completion (to World Health Organization standards).
Outcome 2: Treat minimum 75% of eligible at-risk population for schistosomiasis through MDA of Praziquantel by project completion (to World Health Organization standards).
Outcome 3: Treat minimum 80% of eligible at risk population for lymphatic filiariasis through MDA of Albendazole and Ivermectin or DEC as appropriate by project completion (to World Health Organization standards).
Outcome 4: Community drug distributors and education officials are trained to competently and safely adminisiter MDA drugs by project completion
4 | WASHE is integrated into school curriculum and hand washing with soap increased significantly from baseline
Outcome 1: 2,127 (all) schools receive hygiene kits or replenishment, annually and sytematically by project completion and children in 2,127 (all) schools learn water, sanitation and personal hygiene based on WASHE package by project completion
Objective No. | NTD Macro Category | Output/Description | Activity | Output Indicator | Deliverables | Means of Verification | Annual Targets |  | Periodic Targets PY3 |  |  |  | Annual Target Totals |  |  |  | Targets | Comments
[7 empty] | Year 1 | Year 2 | P9 | P10 | P11 | P12 | Year 2/HT Y1 | Year 3/ HT Y2 | Year 4/ HT Y3 | Year 5 | Cumulative Y/N
1.1.1 | NTD Capacity Building | NTD programme activities coordinated and planned at both national and provincial levels | Provide planning, coordination and implementation support to NTD program activities at the national and provincial levels | Number of NTD stakeholder meetings in Uige, Huambo and Zaire Provinces (1 per province/month plus quarterly national) | One meeting per province/month and quarterly national meetings | Signed Attendance sheet | All stake holder meetings | H:12 U:12 Z:12 National:4 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 1 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 1 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 1 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 1 | H:12 U:12 Z:12 National:4 | H:12 U:12 Z:12 National:4 | H:12 U:12 Z:12 National:4 | H:12 U:12 Z:12 National:4 | N | One meeting per province/month + 1 national meeting per quarter. National meeting includes M&E meeting in 1.1.5 of DC proposal logframe.
1.1.2 | NTD Capacity Building | Improved technical and logistical capacity of the provincial and national NTD teams | Provide technical support and capacity building to provincial and national NTD teams. | Number of Rational and feasible NTD local annual work plans developed and agreed with stakeholders (1 per province plus one national) | One workplan per province/year including drug supply. One national plan per year. | Produced Workplan | All work plans completed | 4 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 2 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 2 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 2 | H:3 U:3 Z:3 B: 1 KK: 1 KS: 1 National: 2 | 4 | 4 | 4 | 4 | N | One workplan per province +1 national, per year
|  |  | Provide logistical support to provincial and national NTD teams. | Percentage of logistical support requests fulfilled by the programme | 80% of the requests are fulfilled | Activity Reports | N/A | 80% of MoH Requests | NA | NA | NA | NA | 80% of MoH Requests | 80% of MoH Requests | 80% of MoH Requests | None | N | Ongoing - dependent on requests from MoH, aim to fulfil at least 80% of those requests.
1.1.3 | Supervision | Ministry of Health has capacity for NTD information Management in Uige, Huambo, Zaire Provinces | To organise regular meetings to accurately analyze NTD burden data in Uige, Huambo and Zaire Provinces | Number of monthly meetings between MENTOR/MoH in Uige, Huambo and Zaire Provinces to analyze health facility (HF) NTD data (1 per province/month) | One meeting per province/month | Signed attendance sheet | Huambo: 3 Uige: 3 Zaire: 3 | Huambo: 3 Uige: 3 Zaire: 3 | H:2 U:3 Z:2 | H:2 U:3 Z:2 | H:2 U:3 Z:2 | H:2 U:3 Z:2 | Huambo: 3 Uige: 3 Zaire: 3 | 36 | 36 | 36 | N | Meetings will be linked to routine malaria data meetings with MoH (USAID funded), but will be jointly funded by this budget as they will be more regular (monthly)
|  |  | Support logistically the NTD data collection | Percentage of logistical support requests fulfilled by the programme | 80% of the requests are fulfilled | Activity Reports | N/A | 80% of MoH Requests | H:3 U:3 Z:3 | H:3 U:3 Z:3 | H:3 U:3 Z:3 | H:3 U:3 Z:3 | 80% of MoH Requests | 80% of MoH Requests | 80% of MoH Requests |  | N | Ongoing - dependent on requests from MoH, aim to fulfil at least 80% of those requests.
1.1.4 | Supervision | Procurement & supply of NTDs drugs for schools, communities and health facilities is ensured | To organise specific meetings targeting NTD drug supply needs for both MDA at schools and case management stock and technical requirements at health facilities. | Number of Mentor/MoH/MoE and other stakeholders logistical meetings to manage the drug supply system (1 per province per month) | One meeting per province/month | Signed attendance sheet | Huambo: 1 Uige: 1 Zaire: 1 | 36 | H:3 U:3 Z:3 | H:3 U:3 Z:3 | H:3 U:3 Z:3 | H:3 U:3 Z:3 | 36 | 25 | 33 | 33 | N | 50% of the municipalities in Year 1, 75% in Year 2, 100% in Year 3
2.1.1 | Training and Workshops | First line health workers are trained to effectively prevent, manage and report NTD cases | Organise training sessions of health workers on the prevention, management & reporting of NTD cases in Huambo, Uige and Zaire provinces | No. of HF or ANC based health workers trained | At least 2 workers trained per health facility supported/3 years based on prioritization | Filled supervision form, training registers | Health Facilities: H: 100 U: 60 Z: 50 ANC: H:20 U:15 Z: 15 | 356 | 144 | 292 | 225 | 72 | 356 | 356 | 356 | TBD | N | There are 534 health facilities. At the end of year 4 we want to have 2 workers trained per health facility. 534*2=1068. Every year from yr 2 onwards we should train 1068/3= 356. Disease mapping will inform which health facilities to target in priority (those in high prevalence areas).
2.1.2 | Support to Health Facilities | Health workers in primary health care facilities have access to NTD case management technical guidelines | Produce NTD technical guidelines and disseminate to health workers | Number of NTD treatment guidelines developed and provided to HFs | One technical guidelines kit is provided to every health facility supported over 3 years | activity reports; guidelines present in health facilities | Huambo: 202 Uige: 122 Zaire: 96 | 534 | 0 | 0 | 0 | 0 | 534 | 534 | 534 | TBD | N | 2 sets of technical guidelines provided to every health facility supported (guidelines for STH, Schisto and other NTDs including drug administration guidelines). Updated and disseminated once per year.
2.1.3 | NTD Capacity Building | The capacity of provincial NTD Programme services to accurately analyze NTD disease data is improved in Uige, Huambo and Zaire Provinces | Perform specific joint technical supervisions with Provincial NTD coordinators to municipal health departments on NTD data collection and analysis | Joint analysis of HF passive NTD patient data collection is conducted with specialist assistance | Percentage of Municipal Health Departments (Reparticoes Municipal Da Saúde) presenting a monthly report on NTDs | Filled supervision form | N/A | 132 H:44, U:64, Z:24 | H:0, U:16, Z:0 | H:0, U:16, Z:0 | H:0, U:16, Z:0 | H:0, U:16, Z:0 | 132 H:44, U:64, Z:24 | 132 H:44, U:64, Z:24 | 132 H:0, U:16, Z:0 | N/A | N | At least one supervision visit per municipality, per quarter
2.1.4 | IEC/ACSM | Health workers in all health facilities have access to IEC technical guidelines and education material | Produce and disseminate IEC technical guidelines and education material in partnership with the national NTD program | No. of IEC technical guideline sets/kits developed and provided to HFs | One IEC technical guidelines kit per health facility supported | activity reports; guidelines present in health facilities | N/A | 534 | 72 | 146 | 113 | 34 | 534 | 534 | 365 | 0 | N | One set of updated IEC technical guidelines & education kit (guidelines for STH, Schisto and LF, including patient education) per health facility supported per year
2.1.5 | Support to Health Facilities | MoH NTD case management and materials supply chain to in health facilities is reinforced | Perform technical support supervisions and coaching on NTD case management, medicine stock and supply chain management | Number of Joint MENTOR/MoH technical coaching visits to HFs assisting with distribution/delivery of NTD supplies + WAASH program implementation | 50% of health facilities reached each year | Filled stock management supervision form | Huambo: 100 Uige: 60 Zaire: 50 | 267 | 50 | 81 | 150 | 85 | 267 | 267 | 267 | TBD | N | 50% of all health facilities will be visited every year. The Program Coordinators will have to prioritise the ones with the most difficuties or the ones in areas with the highest disease burden.
3.1.1 | NTD Mapping | Disease prevalence is mapped in Uige, Zaire and Huambo Provinces | Perfom mapping studies for STH and schistosomiasis in schools | Number of sampled schools visited to test children | 100% of sampled schools reached. | Study report | 0 | 593 | NA | NA | NA | NA | 593 | N/A | 593 | N/A | Y | 17,790 students to be tested in 593 schools
3.1.2 | NTD Mapping | Disease prevalence is mapped in Uige, Zaire and Huambo Provinces | Perfom mapping studies for lymphatic filariasis in communities | Number of sampled villages visited to test residents | 100% of sampled villages reached. | Study report | 0 | 99 | NA | NA | NA | NA | 99 | N/A | 99 | N/A | Y | 9,900 adults to be tested in 99 villages
3.1.3 | Mass Drug Administration | MDAs for intestinal worms reach school children in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in schools in Huambo, Uige and Zaire provinces | No. of enrolled school aged children (5-15) treated for STH in Huambo, Zaire and Uige | <15 year old school children receive MDA in Zaire, Huambo, Uige and Bié Provinces | Provincial MDA report; MDA session filled form | H:300,000; U:174,899; Z:90,722; Total:565,621 | H:510,000 U:297,328 Z:154,227 Total:961,555 | H: 163,859 SAC in two Municipalities (85%) | U:284,092 SAC (85%); Z: 85,479 SAC (85%); B: 403,408 SAC(85%); KK: 162,852 SAC (85%) | KS: 223,428 SAC (85%) | U: 284,092 SAC (85%) | H:510,000 U:297,328 Z:154,227 Total:961,555 | H:510,000 U:297,328 Z:154,227 Total:961,555 | H:510,000 U:297,328 Z:154,227 Total:961,555 | H:510,000 U:297,328 Z:154,227 Total:961,555 | N | Treatment numbers here are estimates based on the percentage of total school children in Zaire, Huambo, Uige Provinces. Population numbers to be confirmed. Treatment numbers will also provide gender ratios for each province.
3.1.4 | Mass Drug Administration | MDAs for intestinal worms reach unenrolled school-aged children in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in Huambo, Uige and Zaire provinces | No. of unenrolled school aged children (5-15) treated for STH in Huambo, Zaire, and Uige. | 200,000 in Year 1; 300,000 patients from Year 2 onwards | Provincial MDA report; MDA session filled form | Annual Targets Year 1: H:75,200 U:69,600 Z:55,200 Total:200,000; Annual Targets Year 2: H:112,800 U:104,400 Z:82,500 Total:300,000 | H:112,800 U:104,400 Z:82,500 Total:300,000 | H:112,800 U:104,400 Z:82,500 Total:300,000 | H:112,800 U:104,400 Z:82,500 Total:300,000 | H:112,800 U:104,400 Z:82,500 Total:300,000 | N | Treatment numbers here are estimates based on the percentage of total school children in Zaire, Huambo, Uige Provinces. Population numbers to be confirmed. Treatment numbers will also provide gender ratios for each province.
3.1.5 | Mass Drug Administration | MDAs for intestinal worms cover all eligible municipalities in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in communities in Huambo, Uige and Zaire provinces | No. of communes reached through CDD MDA | Increasingly scaled % program coverage in years 2-4, reaching 100% by year 4 onwards. | Provincial MDA community based campaign reports | N/A | 47 | 0 | U: 38,912 PRE-SAC through CDTi (85%); KK: 63,522 PRE-SAC through CDTi | 0 | 0 | 47 | 70 | 94 | 0 | N | Total eligible communes reached with MDAs 50% (47) yr 2, 75% (70) yr 3, 100% (94) yr 4. Eligibility of commmunes will be determined by the disease mapping.
3.1.6 | Mass Drug Administration | MDAs for intestinal worms reach children between 1 and 5 years old in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in communities in Huambo, Uige and Zaire provinces | No. of pre-SAC that receive MDA in Huambo, Zaire and Uige | Increasingly scaled % program coverage in years 2-4, reaching 100% by year 4 onwards. | Provincial MDA community based campaign reports | Annual Targets Year 1: N/A; Annual Targets Year 2: 312199 | 312199 | 468299 | 624399 | 0 | N | Percentage of estimated total children between 1 and 5 years old in Zaire, Huambo, Uige Provinces that receive Albendazole MDA once in the year (based on increasing geographical coverage each year) Treatment numbers will also provide gender ratios for each province.
3.1.7 | Mass Drug Administration | MDAs for intestinal worms reach pregnant women in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in communities in Huambo, Uige and Zaire provinces | No. of pregnant women that receive MDA in Huambo, Zaire and Uige | Increasingly scaled % program coverage in years 2-4, reaching 100% by year 4 onwards. | Provincial MDA campaign reports | Annual Targets Year 1: N/A; Annual Targets Year 2: 195124 | 195124 | 292686 | 390249 | 0 | N | Percentage of estimated total eligible pregnant and lactating women in Zaire, Huambo, Uige Provinces that receive Albendazole MDA once in the year. (based on increasing geographical coverage each year) Treatment numbers will also provide gender ratios for each province.
3.1.8 | Mass Drug Administration | MDAs for intestinal worms reach 75% of those in high risk groups in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole in communities in Huambo, Uige and Zaire provinces | No. of high risk adults (>15) that receive MDA in Huambo, Zaire and Uige | Target to be set post-mapping | Provincial MDA campaign reports | Annual Targets Year 1: N/A; Annual Targets Year 2: Numbers to be locally determined when disease mapping is completed | Numbers to be locally determined when disease mapping is completed | Numbers to be locally determined when disease mapping is completed | Numbers to be locally determined when disease mapping is completed | 0 | N | Percentage of estimated total adults engaged in high-risk activities (fishing, miners, tea pickers, car washers, etc.) in Zaire, Huambo, Uige Provinces that received Albendazole MDA once in the year. Treatment numbers will also provide gender ratios for each province.
3.2.1 | Mass Drug Administration | MDAs for schistosomiasis reaches school children in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Praziquantel in schools in Huambo, Uige and Zaire provinces | No. of enrolled school aged children (5-15) treated for Schisto in Huambo, Zaire and Uige | 3.1 <15 year old school children receive MDA in Zaire, Huambo, Uige and Bié Provinces | Provincial MDA report; MDA session filled form | H:300,000; U:174,899; Z:90,722; Total:565,621 | TBD | H: 281,947 SAC in 6 Municipalities (85%) | U: 72,635 SAC tin 5 Municipalities (CDTi Municipalities); B: 188,083 SAC (85%); | 0 | 0 | TBD | TBD | TBD | TBD | N | Total number of treatments delivered, based on number of school children (between 5 and 15 years of age) in Zaire, Huambo and Uige Provinces that received Praziquantel MDA. Treatment numbers will also provide gender ratios for each province.
3.2.2 | Mass Drug Administration | MDAs for schistosomiasis reaches unenrolled school-aged children in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Praziquantel in Huambo, Uige and Zaire provinces | No. of unenrolled school aged children (5-15) treated for Schisto in Huambo, Zaire, and Uige. | 2.7 200 000 STH and scistosomiasis patients treated in Year 1 in Huambo, Uige and Zaire Provinces; 300 000 patients treated in Bié, Huambo, Uige and Zaire Provinces in Year 2; 420 000 patients treated from Year 3 onwards | Health facilities MDA campaigns reports; NTD provincial programmes and Provincial Directions of Health reports | Annual Targets Year 1: H:75,200 U:69,600 Z:55,200 Total:200,000; Annual Targets Year 2: TBD | TBD | TBD | TBD | TBD | N | Total number of treatments delivered, based on number of estimated unenrolled school-aged children (between 5 and 15 years of age) in Zaire, Huambo and Uige Provinces that received Praziquantel MDA. Treatment numbers will also provide gender ratios for each province.
3.2.3 | Mass Drug Administration | MDAs for schistosomiasis cover all eligible communes in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Praziquantel in communities in Huambo, Uige and Zaire provinces | No. of communes reached through CDD MDA | Increasingly scaled % program coverage in years 2-4, reaching 100% by year 4 onwards. | Provincial MDA campaign reports | N/A | 47 | 0 | 0 | 0 | 0 | 47 | 70 | 94 | 0 | N | Total eligible communes reached with MDAs 50% (47) yr 2, 75% (70) yr 3, 100% (94) yr 4. Eligibility of commmunes will be determined by the disease mapping.
3.2.4 | Mass Drug Administration | MDAs for schistosomiasis reaches 75% of qualifying adults in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Praziquantel in communities in Huambo, Uige and Zaire provinces | No. of high risk adults (>15) that receive MDA in Huambo, Zaire and Uige | Target to be set post-mapping | Provincial MDA campaign reports | Annual Targets Year 1: N/A; Annual Targets Year 2: TBD | TBD | TBD | TBD | 0 | N | Percentage of estimated total adults living in high risk areas or engaged in high-risk activities (fishing, miners, tea pickers, car washers, etc.) in Zaire, Huambo, Uige Provinces that received Praziquantel MDA once in two years. Treatment numbers will also provide gender ratios for each province.
3.3.1 | Mass Drug Administration | MDAs for lymphatic filariasis cover all eligible municipalities in Zaire, Huambo, Uige Provinces | Conduct annual joint MDA/IEC campaigns with Albendazole & Ivermectin OR DEC in communities in Huambo, Uige and Zaire provinces OR bi-annual MDA with Albendazole | No. of communes reached through CDD MDA | Increasingly scaled % program coverage in years 2-4, reaching 100% by year 4 onwards. | Provincial MDA campaign reports | N/A | 47 | TBD | KK: 247,963 of LF endemic Municipalities | TBD | TBD | 47 | 70 | 94 | 0 | N | Total eligible communes reached with MDAs 50% (47) yr 2, 75% (70) yr 3, 100% (94) yr 4. Eligibility of commmunes will be determined by the disease mapping.
3.3.2 | Mass Drug Administration | MDAs for lymphatic filariasis reach all eligible population in Zaire, Huambo, Uige Provinces (excluding SAC in output #1) | Conduct annual joint MDA/IEC campaigns with Albendazole & Ivermectin OR DEC in communities in Huambo, Uige and Zaire provinces OR bi-annual MDA with Albendazole | No. of people at risk of LF receive treatment in Huambo, Zaire and Uige | Target to be set post-mapping | Provincial MDA campaign reports | N/A | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 0 | N | See section on STH for number of children treated with Albendazole above. Numbers of pre-SAC and adults to be determined when disease mapping is completed, based on presence and prevalence of the disease. Treatment numbers will also provide gender ratios for each province.
3.4.1 | Training and Workshops | Education and health officials are trained to train teachers to competently and safely deliver MDA | Provide annual basic NTD training to provincial and municipal coordinators and education area coordinators | No. of government officials that receive training as part of cascade | See comments, to be revised. | Activity Reports | N/A | 100 (to be confirmed) | H: 12 | U: 32; Z: 12; B: 18; KK: 18 | KS: 24 | U: 32 | 100 (to be confirmed) | 100 (to be confirmed) | 100 (to be confirmed) | 0 | N | 3 trainers from the national level, 3 per province (total 9), + 2 per municipality (total 66) + area coordinators (up to 22).
3.4.2 | Training and Workshops | Teachers and school directors trained in basic NTD package | Provide annual basic NTD training to teachers and school directors of MDA supported schools | No. of teachers involved in MDA campaign planning and delivery in their schools | At least Two teachers and one director per MDA targeted school receive basic sensitization on NTDs | Teachers' IEC report for each school | Huambo: 200 Uige: 120 Zaire: 100 | 6381 | H: 1,220 | U: 2,166; Z: 516; B: TBD; KK: TBD | KS: TBD | U: 2,166 | 6381 | 6381 | 6381 | 6381 | N | At least 2 teachers per MDA targeted school + 1 director receive basic sensitization on NTDs per MDA = 3 people per school (761 schools in Huambo, 1084 in Uige, 282 in Zaire)
3.4.3 | Training and Workshops | Community drug distributors are trained to competently and safely deliver MDA | Provide annual basic NTD training to community drug distributors | No. of CDDs involved in MDA campaign planning and delivery | At least XX per MDA targeted commune receive training | Activity Reports | N/A | TBD | 0 | U: 797; KK:TBD | 0 | 0 | TBD | TBD | TBD | 0 | N | Number to be determined according to the number of communes and municipalities
3.4.4 | IEC/ACSM | Opportunities for linking MDA to other community based campaigns will be maximized where feasible | Conduct joint IEC campaigns with other community-based pgrograms (Vaccination and others) | Number and type of non-program funded community campaigns to which MDA activities develop linkages (at least 2 per year per province) | At least 2 annual joint IEC campaigns are conducted in every province | IEC campaign report; Activity reports | 1 | 3 | 0 | U: 140,197 Elegible Population (5 Municipalities CDTi - Oncho Only) (75%); KK: 15,989 Elegible Population (5 Municipalities CDTi - Oncho Only) (75%); | 0 | 0 | 3 | 3 | 3 | 3 | N | Linkages will be oportunistic with mass vaccination programmes, or mass commodity distributions programmes as and when other organisations plan these. One per province in year 2.
4.1.1 | Assessments and Surveys | Understanding of existing hygiene and sanitation knowledge and practices amongst teachers and children acquired | Conduct a KAP study on NTD transmission and WASH practices | No. of KAP Studies | 1 KAP study per province completed twice over years 2-4 | Studies Concluded | N/A | 3 | NA | NA | NA | NA | 3 | 0 | 3 | 0 | N | One survey per province
4.1.2 | Assessments and Surveys | Assessment of a sample of 10 schools in each province for existing WASH facilities | Assess the condition and current provision of WASH facilities in schools in the operational area | Number of schools sampled for assessment report | 1 Assessment report is produced on the assessment of water, hygiene and sanitation conditions is conducted in a sample of 10 schools per province | Assessment report | N/A | 30 | NA | NA | NA | NA | 30 | 0 | 30 | 0 | N | Assessment report is produced on the assessment of water, hygiene and sanitation conditions conducted in a sample of 10 schools per province. This assessment should be performed during the mapping
4.1.3 | WASH | Children in schools are sensitised to the main NTD transmission modes and the risks associated with poor hygiene and sanitation practices | Undertake hygiene information, education and communication interventions in schools targeting priority NTDs | Number of schools reached with WASH package IEC interventions | Year two 50% of all schools reached, Years three and following 100% | WASH reports | N/A | 1063 | 258 | 490 | 473 | 135 | 1063 | 2127 | 2127 | 0 | N | Number of registered schools receiving WASHE package IEC interventions including life-skills hygeine education (yr 2 50%, 100% as of Yr 3)
4.1.4 | WASH | Schools are assisted to improve their hygiene environment with basic hygiene and sanitation 'kits'. | Distribute, replenish or replace hygiene 'kits' to all schools annually when IEC interventions are carried out | Number of hygiene kits distributed to the schools | At least 1 hygiene kit/MDA targeted school is distributed | WASH reports | N/A | 1063 | 258 | 490 | 473 | 135 | 1063 | 2127 | 2127 | 0 | N | At least one hygiene kit (soap, 'tippy tap' handwashers, etc.) per targeted school is distributed, replenished or replaced annually (year 2 reaching 50% of schools, 100% as of Yr 3). This number reflets total number of hygiene kits delivered
4.1.5 | NTD Capacity Building | The government’s supervision, monitoring and follow up of integrated WASHE program is strengthened | Provide information from all WASH assessment reports to provincial Ministry of Education officials | No. of reports submitted to government stakeholders | 2-3 reports per province per year | WASH reports | N/A | 9 | U: 1; Z: 1; H: 0 | U: 1; Z: 1; H: 1 | U: 1; Z: 1; H: 1 | U:1; Z: 1; H: 1 | 9 | 6 | 9 | 0 | N | KAP, WASH assessment & annual provincial WASH activity reports (3) shared with MoEd leader for each province. There will be no KAP in Year 3, so only WASH reports and assessments will be shared.
|  |  | Perform technical support supervisions together with DPS and DPE in the WASH program implementation | Number of Joint MENTOR/MoH technical coaching visits to Schools assisting WASH program implementation | Same number of Schools as HF supervised | Filled supervision form | NA | NA | 50 | 81 | 150 | 85 | TBD | TBD | TBD | TBD | N | Same number of Schools as HF supervised