## Grant Tracking Tool
GRANT MANAGEMENT TRACKING TOOL
| PU = Program Update |  |  | Year 1
| DSB = Disbursement |  |  | Year 2
| DR = Donor Report |  |  | Year 3
| GA = Grant Agreement Signed |  |  | Year 4
MDA = MDA occuring
Training
Mapping
Close Out
No Cost Extension
[8 empty] | 2012 |  |  |  |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
| Rainy Seasons, School Closures | [24 empty] | X |  |  | X
| COUNTRY | GRANT NO. | IPI | DONORS | TOTAL GRANT $ | Start Date | End Date | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | ANGOLA | 080194 | Mentor Intiative | Helmsley, Dubai Cares, Legatum, JP Morgan | 7285315 | 25-March-13 | 1-Jan-18 | MAR: DSB 25-Mar; JUN: DSB 20-Jun; JUL: PU 31-Jul; OCT: PU 31-Oct; JAN: DSB 1-JanPU 31-Jan; X FEB: DR (DC); X APR: DSB 1-AprPU 30-Apr; X JUL: PU 31-JulDR (JP Morgan); X OCT: PU 31-OctMDA; X NOV: DR 14-Nov (Helms) DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: DSB 1-AprPU 30-Apr; X MAY: DR 31-May (DC); X JUN: DR 15-Jun (Helms); X JUL: PU 31-Jul; X OCT: PU 31-Oct; X NOV: DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: DSB 1-JanPU 30-Apr; X MAY: DR 31-May (DC); X JUN: DR 15-Jun (Helms); X JUL: PU 31-Jul; X OCT: PU 31-Oct; X NOV: DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: DSB 1-AprPU 30-AprDR 30-Apr (Helms); X MAY: DR 31-May (DC); X JUL: PU 31-Jul; X OCT: PU 31-Oct; X NOV: DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: PU 30-Apr; X MAY: DR 31-May (DC)
2 | BURUNDI | 080139 | CBM | Legatum | 331500 | 9-Jan-12 | 31-Apr-14 | JAN: DSB 9-Jan; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; X APR: PU 31-Apr; X JUN: NCE
4 | DRC | 080217 | CNTD | Gates, SOCO Int. | 371020 | 15-Jul-13 | 31-Mar-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; JAN: PU 31-Jan; X FEB: DSB 1-Feb; X APR: PU 30-Apr; X MAY: DSB 1-May; X JUN: DR (Gates) 30-Jun
4 | DRC |  | APOC | Gates, Cargill | 1875000 | 1-Jan-14 | 31-Dec-14 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; JAN: PU 31-Jan; X FEB: DSB 1-Feb; X APR: PU 30-Apr; X MAY: DSB 1-May; X JUN: DR (Gates) 30-Jun; X SEP: GADSB; X MAR: PU 31 Mar; X SEP: DR 1 Sep; X SEP: DR 1 Sep; X SEP: DR 1 Sep
5 | ETHIOPIA | 080218 | CNTD | Gates, Melissa Murdoch | 362451 | 15-Jul-13 | 15-Dec-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; OCT: DSB 30-Oct; DEC: PU 31-Dec; JAN: DSB 31-Jan; X MAY: DR 19-May (Murdoch); X JUN: DR (Gates) 30-Jun; X NOV: DR (Murdoch); X MAY: DR (Murdoch); X NOV: DR (Murdoch)
| ETHIOPIA |  | FMoH | Shefa | 750000 | 24-Mar-14 | 31-Dec-14 | X MAR: DSB; X JUL: PU 15-JulDR 31-JulDSB; X OCT: MDA; X NOV: DR 19-Nov (Murdoch); X JAN: PU 30-Jan; X FEB: DR 15-Feb
| ETHIOPIA |  | SCI | Cargill | 1875000 | April-14 | Feb-17 | X SEP: MDA; X OCT: PU 31-Oct,MDA; X MAR: PU 31-Mar; X APR: MDA early April DR 30-Apr; X SEP: PU 30-Sep,MDA; X OCT: MDA; X MAR: PU 31-Mar; X APR: DR 30-Apr; X AUG: PU 30-Sep; X SEP: MDA; X OCT: MDA; X MAR: PU 31-Mar; X MAY: DR 1-May
6 | INDIA | 080221 | DtW | Gates, GGI, Legatum, Scott Powell | 180000 | 15-Aug-13 | 15-July-13 | SEP: GA; OCT: DSB 3-Oct; X FEB: PU 28-Feb; X APR: PU 30-Apr; X JUN: DSB 1-JunDR (Gates) 30-Jun; X JUL: PU 31-Jul
7 | KENYA | 080179 | EA/DTW | Campbell, Legatum | 593531 | 1-Nov-14 | 30-Jun-17 | JUN: DSB 1-Jun; SEP: DSB 1-SeptPU 15-Sept; NOV: Revised GA Starts; JAN: PU 15-Jan; X FEB: MDA; X APR: PU 15-Apr; X JUN: DSB 1-JunDR 16-Jun (Campbell); X JUL: PU 15 Jul; X SEP: DSB 1-Sep PU 15 Sept; X JAN: Audit/AR 30th; X FEB: PU 15-Feb; X MAR: MDA; X MAY: PU 15-MayDSB; X JUN: Audit/AR 30th; X AUG: PU 15-Aug; X NOV: PU 15-NovDSB; X FEB: PU 15-Feb; X MAY: PU 15-MayDSB; X JUN: Audit/AR 30th; X AUG: PU 15-Aug; X NOV: PU 15-NovDSB; X FEB: PU 15-Feb; X MAY: PU 15-MayDSB; X JUN: Audit/AR 30th; X JUN: Audit/AR 30th
8 | LIBERIA | 080196 | SCI | Dubai Cares | 390000 | 1-Sep-13 | 31-Aug-17 | SEP: GA; OCT: DSB 1-Oct; X MAR: PU 31-Mar; X APR: DR 15-Apr; X OCT: DSB 15-OctPU 15-Oct; X NOV: DR 15-Nov; X FEB: Update to DC on Ebola and start up; X APR: PU 15-Apr; X JUL: Update memo to DC on start up; X OCT: DSB 15-OctPU 15-Oct; X NOV: DR 15-Nov; X APR: PU 15-Apr; X MAY: DR 15-May; X OCT: DSB 15-OctPu 15-Oct; X NOV: DR 15-Nov; X APR: PU 15-Apr; X MAY: DR 15-May; X OCT: DSB 15-OctPU 15-Oct; X NOV: DR 15-Nov; X APR: PU 15-Apr; X MAY: DR 15-May; X OCT: PU 15-Oct; X NOV: DR 15-Nov
9 | MALI | 080206 | HKI | Al Ansari, Gates, Mining Cos | 1304566 | 2013-04-01 | 2014-06-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; NOV: DSB 13-Nov; JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DSB 15-MayDR (Ansari) 1-May; X JUN: DR (Gates) 30-JunPU 30-Jun
10 | NAMIBIA | 080193 | Synergos | DC, Gates, Legatum | 1,043,021 | 2014-06-01 | 2017-05-31 | X JUN: DSB; X OCT: DR 1-Oct DCPU 31-OctMDA 20-24; X JAN: PU 31-Jan; X MAR: MDA; X APR: PU 30-Apr; X MAY: DR 1-May Annual; X JUL: PU 31-Jul; X SEP: IP Annual Rep 30-Sep; X OCT: DR 1-Oct DC SAPU 31-Oct; X JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DR 1-May Annual; X JUL: PU 31-Jul; X SEP: IP Annual Rep 30-Sep; X OCT: DR 1-Oct DC SAPU 31-Oct; X JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DR 1-May Annual; X JUL: PU 31-Jul; X SEP: IP Annual Rep 30-Sep
11 | NIGER | 080202 | HKI | Al Ansari, Gates | 78000 | 2013-04-01 | 2013-09-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; DEC: DSB 20-Dec; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
12 | NIGERIA | 080201 | Sightsavers | Al Ansari, Gates | 500000 | 2013-05-01 | 2013-12-31 | MAY: DSB 3-May; JUN: PU 30-Jun; SEP: DSB 30-SepPU 30-Sep; JAN: PU 31-Jan; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
| NIGERIA |  | Mitosath
13 | RWANDA | 080140 | SCI | Gates, OUP, Legatum | 1643507 | 2012-02-13 | 2014-12-31 | JAN: DSB 9-Jan; FEB: GA OUP; MAR: PU 15-Mar; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; DEC: DR (OUP) 15-Dec; JAN: DSB 9-Jan PU 31-Jan; X MAR: MDA; X APR: PU 30-Apr; X MAY: DR (OUP) 15-May; X JUN: DR (Gates) 30-Jun; X JUL: PU 31-Jul; X SEP: DSB 9-Sep; X OCT: PU 31-Oct,MDA; X DEC: DR (OUP) 15-DecPU 15-Dec; X JAN: PU 31-Jan; X JUL: DR (OUP) 15-Jul; X AUG: DR (OUP) 1-Aug; X JUL: DR (OUP) 15-Jul
| TANZANIA |  | SS
15 | TANZANIA |  | KCCO |  |  |  |  | X MAR: DR 31-Mar
| YEMEN |  | SCI | Al Ansari | 243343 | 2014-05-01 | 2015-03-31 | X JUN: DSB; X AUG: PU 31-Aug; X SEP: DR 15-Sep; X NOV: PU 30-NovMDA; X MAR: PU 31-Mar; X APR: DR 15- Apr
14 | YEMEN | 080200 | SCI | Al Ansari, Gates | 150000 | 2013-03-01 | 2013-12-31 | FEB: GA; MAR: DSB 1-Mar; JUN: PU 30-Jun; SEP: DSB 30-SepPU 30-Sep; JAN: DSB 31-JanPU 31-Jan; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
15 | ZAMBIA |  | GGI (St. Pauls, EHCZ) | Legatum | N/A |  | 2014-06-30 | X MAR: DR 31-Mar; X SEP: DR (SIFund) 30-Sep
16 | ZIMBABWE | 080180 | SCI | Zakharov, Masiyiwa | 146500 | 2012-09-01 | 2016-01-31 | FEB: DSB 1-Feb; MAY: PU 30-May; AUG: DSB 15-Aug; SEP: DR 15-Sept; JAN: PU 31-Jan; X MAR: DSB 15-Mar; X SEP: DR 31-Aug; X OCT: MDA 20-25,Training 28 Sept - 4 Oct; X DEC: PU 1-Dec; X FEB: DR; X JAN: PU 31-Jan

## Seasonal Calendar
GRANT MANAGEMENT TRACKING TOOL
| Rainy Season |  |  | Year 1
| School Closures |  |  | Year 2
| Significant Religious Event (RD=Ramadan) |  |  | Year 3
| Other Interruption to Programs |  |  | Year 4
Training
Mapping
MDA = MDA occuring
Close Out
No Cost Extension
[8 empty] | 2012 |  |  |  |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
| Board Meetings, Quarter Reports | [24 empty] | X |  |  | X
| COUNTRY | Primary Religion (>30%) | IPI | DONORS | TOTAL GRANT $ | Start Date | End Date | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | ANGOLA | Christianity | Mentor Intiative | Helmsley, Dubai Cares, Legatum, JP Morgan | 7285315 | 25-March-13 | 1-Jan-18 | MAR: DSB 25-Mar; JUN: DSB 20-Jun; JUL: PU 31-Jul; OCT: PU 31-Oct; JAN: DSB 1-JanPU 31-Jan; X FEB: DR (DC); X APR: DSB 1-AprPU 30-Apr; X OCT: MDA; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season
2 | BURUNDI | Christianity | CBM | Legatum | 331500 | 9-Jan-12 | 31-Apr-14 | JAN: DSB 9-Jan; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; X APR: PU 31-Apr; X SEP: Rainy Season; X OCT: Rainy Season; X NOV: Rainy Season; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Rainy Season
4 | DRC | Christianity | CNTD | Gates, SOCO Int. | 371020 | 15-Jul-13 | 31-Mar-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; JAN: PU 31-Jan; X FEB: DSB 1-Feb; X APR: PU 30-Apr; X MAY: DSB 1-May; X OCT: Rainy Season; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Rainy Season
4 | DRC | Christianity | APOC | Gates, Melissa A Cargill | 1875000 | 1-Jan-14 | 31-Dec-14 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; JAN: PU 31-Jan; X FEB: DSB 1-Feb; X APR: PU 30-Apr; X MAY: DSB 1-May; X OCT: Rainy Season; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Rainy Season; X OCT: Rainy Season; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Rainy Season
5 | ETHIOPIA | 080218 | CNTD | Gates, Melissa Murdoch | 362451 | 15-Jul-13 | 15-Dec-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; OCT: DSB 30-Oct; DEC: PU 31-Dec; JAN: DSB 31-Jan; X MAY: DR 19-May (Murdoch); X JUN: DR (Gates) 30-Jun; X NOV: DR (Murdoch); X MAY: DR (Murdoch); X NOV: DR (Murdoch)
| ETHIOPIA | Christianity, Islam | FMoH | Shefa | 750000 | 24-Mar-14 | 31-Dec-14 | X MAR: DSB; X JUN: Rainy Season; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season,Schools Closed; X OCT: MDA
| ETHIOPIA | Christianity, Islam | SCI | Cargill | 1875000 | April-14 | Feb-17 | X JUN: Rainy Season; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season,Schools Closed,MDA; X OCT: MDA; X JUN: Rainy Season,RD-18th; X JUL: Rainy Season,Schools Closed, 18,RD 16th; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season,Schools Closed,MDA; X OCT: MDA; X JUN: Rainy Season; X JUL: Rainy Season,School Break; X AUG: Rainy Season,School Break; X SEP: Rainy Season,School Break,MDA; X OCT: MDA
6 | INDIA | Hinduism | DtW | Gates, GGI, Legatum, Scott Powell | 180000 | 15-Aug-13 | 15-July-13 | SEP: GA; OCT: DSB 3-Oct; X FEB: PU 28-Feb; X APR: PU 30-Apr; X JUN: Rainy Season,Schools Closed; X JUL: Rainy Season
7 | KENYA | Christianity | IPA/DTW | Campbell, Legatum | 1146473 | 31-Aug-12 | 30-Aug-17 | JUN: DSB 1-Jun; SEP: DSB 1-SeptPU 15-Sept; OCT: DR; JAN: PU 15-Jan; X FEB: MDA; X APR: PU 15-Apr; X JUN: Rainy Season; X AUG: Schools Closed; X SEP: Schools Closed; X APR: Rainy Season; X MAY: Rainy Season; X JUN: Rainy Season; X AUG: Schools Closed; X SEP: Schools Closed
8 | LIBERIA | Christianity | SCI | Dubai Cares | 390000 | 1-Sep-13 | 31-Aug-17 | SEP: GA; OCT: DSB 1-Oct; X MAR: PU 31-Mar; X APR: DR 15-Apr; X JUN: Rainy Season,Schools Closed; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed,Ebola Outbreak; X SEP: Rainy Season,Ebola Outbreak; X OCT: Rainy Season,Ebola Outbreak; X NOV: Rainy Season,Ebola Outbreak; X MAY: Rainy Season; X JUN: Rainy Season,Schools Closed; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season; X OCT: Rainy Season; X NOV: Rainy Season; X MAY: Rainy Season; X JUN: Rainy Season,Schools Closed; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season; X OCT: Rainy Season; X NOV: Rainy Season; X MAY: Rainy Season; X JUN: Rainy Season,Schools Closed; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed
9 | MALI | Islam | HKI | Al Ansari, Gates, Mining Cos | 1304566 | 2013-04-01 | 2014-06-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; NOV: DSB 13-Nov; JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DSB 15-MayDR (Ansari) 1-May
10 | NAMIBIA | Christianity | Synergos | DC, Gates, Legatum | 1,043,021 | 2014-06-01 | 2017-05-31 | X OCT: MDA 20-24; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy SeasonMDA; X APR: Rainy Season; X MAY: Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Schools Closed
11 | NIGER | 080202 | HKI | Al Ansari, Gates | 78000 | 2013-04-01 | 2013-09-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; DEC: DSB 20-Dec; X MAY: DR (Ansari) 1-May
12 | NIGERIA | 080201 | Sightsavers | Al Ansari, Gates | 500000 | 2013-05-01 | 2013-12-31 | MAY: DSB 3-May; JUN: PU 30-Jun; SEP: DSB 30-SepPU 30-Sep; JAN: PU 31-Jan; X MAY: DR (Ansari) 1-May
13 | RWANDA | Christianity | SCI | Gates, OUP, Legatum | 1643507 | 2012-02-13 | 2014-12-31 | JAN: DSB 9-Jan; FEB: GA OUP; MAR: PU 15-Mar; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; DEC: DR (OUP) 15-Dec; JAN: DSB 9-Jan PU 31-Jan; X MAR: MDA; X APR: PU 30-Apr; X MAY: DR (OUP) 15-May; X OCT: Rainy Season,MDA; X NOV: Rainy Season,Schools Closed; X DEC: Rainy Season,Schools Closed; X JAN: School Break; X FEB: Rainy Season; X MAR: Rainy Season; X APR: Rainy Season; X MAY: Rainy Season
| YEMEN | Islam | SCI | Al Ansari | 243343 | 2014-05-01 | 2015-03-31 | X JUN: School Break; X JUL: Rainy Season,Schools Closed; X AUG: Rainy Season,Schools Closed; X SEP: Rainy Season; X NOV: MDA; X MAR: Rainy Season; X APR: Rainy Season
16 | ZIMBABWE | Christianity | SCI | Zakharov, Masiyiwa | 146500 | 2012-09-01 | 2016-01-31 | FEB: DSB 1-Feb; MAY: PU 30-May; AUG: DSB 15-Aug; SEP: DR 15-Sept; JAN: PU 31-Jan; X MAR: DSB 15-Mar; X OCT: MDA 20-25; X NOV: Rainy Season; X DEC: Rainy Season,Schools Closed; X JAN: Rainy Season,Schools Closed; X FEB: Rainy Season; X MAR: Rainy Season

## Sheet1
[8 empty] | 2012 |  |  |  |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016
| Rainy Seasons, School Closures etc. | [24 empty] | X |  |  | X
| COUNTRY | GRANT NO. | IPI | DONORS | TOTAL GRANT $ | Start Date | End Date | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | ANGOLA | 080194 | Mentor Intiative | Helmsley, Dubai Cares, Legatum, JP Morgan | 7285315 | 25-March-13 | 1-Jan-18 | MAR: DSB 25-Mar; JUN: DSB 20-Jun; JUL: PU 31-Jul; OCT: PU 31-Oct; JAN: DSB 1-JanPU 31-Jan; X FEB: DR (DC); X APR: DSB 1-AprPU 30-Apr; X JUL: PU 31-JulDR (JP Morgan); X OCT: PU 31-OctMDA; X NOV: DR 14-Nov (Helms) DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: DSB 1-AprPU 30-Apr; X MAY: DR 31-May (DC); X JUN: DR 15-Jun (Helms); X JUL: PU 31-Jul; X OCT: PU 31-Oct; X NOV: DR 30-Nov (DC); X JAN: DSB 1-JanPU 31-Jan; X APR: DSB 1-JanPU 30-Apr; X MAY: DR 31-May (DC); X JUN: DR 15-Jun (Helms); X JUL: PU 31-Jul; X OCT: PU 31-Oct; X NOV: DR 30-Nov (DC)
2 | BURUNDI | 080139 | CBM | Legatum | 331500 | 9-Jan-12 | 31-Apr-14 | JAN: DSB 9-Jan; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; X APR: PU 31-Apr; X JUN: NCE
4 | DRC | 080217 | CNTD | Gates, SOCO Int. | 371020 | 15-Jul-13 | 31-Mar-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; JAN: PU 31-Jan; X FEB: DSB 1-Feb; X APR: PU 30-Apr; X MAY: DSB 1-May; X JUN: DR (Gates) 30-Jun
5 | ETHIOPIA | 080218 | CNTD | Gates, Melissa Murdoch | 362451 | 15-Jul-13 | 15-Dec-13 | JUL: GADSB 15-Jul; SEP: PU 30-Sep; OCT: DSB 30-Oct; DEC: PU 31-Dec; JAN: DSB 31-Jan; X MAY: DR 19-May (Murdoch); X JUN: DR (Gates) 30-Jun; X NOV: DR (Murdoch); X MAY: DR (Murdoch); X NOV: DR (Murdoch)
| ETHIOPIA |  | FMoH | Shefa | 750000 | 24-Mar-14 | 31-Dec-14 | X MAR: DSB; X JUL: PU 15-JulDR 31-JulDSB; X NOV: DR 19-Nov (Murdoch); X JAN: PU 30-Jan; X FEB: DR 15-Feb
| ETHIOPIA |  | SCI | Cargill | 1875000 | April-14 | Feb-17 | X OCT: PU 31-Oct; X MAR: PU 31-Mar; X APR: DR 30-Apr; X SEP: PU 30-Sep; X MAR: PU 31-Mar; X APR: DR 30-Apr; X AUG: PU 30-Sep
6 | INDIA | 080221 | DtW | Gates, GGI, Legatum, Scott Powell | 180000 | 15-Aug-13 | 15-July-13 | SEP: GA; OCT: DSB 3-Oct; X FEB: PU 28-Feb; X APR: PU 30-Apr; X JUN: DSB 1-JunDR (Gates) 30-Jun; X JUL: PU 31-Jul
7 | KENYA | 080179 | IPA/DTW | Campbell, Legatum | 1146473 | 31-Aug-12 | 30-Aug-17 | JUN: DSB 1-Jun; SEP: DSB 1-SeptPU 15-Sept; OCT: DR; JAN: PU 15-Jan; X FEB: MDA; X APR: PU 15-Apr; X JUN: DSB 1-JunDR 16-Jun (Campbell); X JUL: PU 15 Jul; X SEP: DSB 1-Sep; X JUN: DSB 1-Jun; X SEP: DSB 1-Sep; X JUN: DSB 1-Jun; X SEP: DSB 1-Sep
8 | LIBERIA | 080196 | SCI | Dubai Cares | 390000 | 1-Sep-13 | 31-Aug-17 | SEP: GA; OCT: DSB 1-Oct; X MAR: PU 31-Mar; X APR: DR 15-Apr; X OCT: DSB 15-OctPU 15-Oct; X NOV: DR 15-Nov; X APR: PU 15-Apr; X MAY: DR 15-May; X OCT: DSB 15-OctPU 15-Oct; X NOV: DR 15-Nov; X APR: PU 15-Apr; X MAY: DR 15-May; X OCT: DSB 15-OctPu 15-Oct; X NOV: DR 15-Nov
9 | MALI | 080206 | HKI | Al Ansari, Gates, Mining Cos | 1304566 | 2013-04-01 | 2014-06-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; NOV: DSB 13-Nov; JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DSB 15-MayDR (Ansari) 1-May; X JUN: DR (Gates) 30-JunPU 30-Jun
10 | NAMIBIA | 080193 | Synergos | DC, Gates, Legatum | 1,043,021 | 2014-06-01 | 2017-05-31 | X JUN: DSB; X OCT: DR 1-Oct DCPU 31-Oct; X JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DR 1-May Annual; X JUL: PU 31-Jul; X SEP: IP Annual Rep 30-Sep; X OCT: DR 1-Oct DC SAPU 31-Oct; X JAN: PU 31-Jan; X APR: PU 30-Apr; X MAY: DR 1-May Annual; X JUL: PU 31-Jul; X SEP: IP Annual Rep 30-Sep; X OCT: DR 1-Oct DC SAPU 31-Oct
11 | NIGER | 080202 | HKI | Al Ansari, Gates | 78000 | 2013-04-01 | 2013-09-30 | APR: DSB 1-Apr; JUL: PU 31-Jul; OCT: PU 31-Oct; DEC: DSB 20-Dec; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
12 | NIGERIA | 080201 | Sightsavers | Al Ansari, Gates | 500000 | 2013-05-01 | 2013-12-31 | MAY: DSB 3-May; JUN: PU 30-Jun; SEP: DSB 30-SepPU 30-Sep; JAN: PU 31-Jan; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
13 | RWANDA | 080140 | SCI | Gates, OUP, Legatum | 1643507 | 2012-02-13 | 2014-12-31 | JAN: DSB 9-Jan; FEB: GA OUP; MAR: PU 15-Mar; JUN: PU 15-Jun; SEP: DSB 9-SepPU 15-Sep; DEC: DR (OUP) 15-Dec; JAN: DSB 9-Jan PU 31-Jan; X MAR: MDA; X APR: PU 30-Apr; X MAY: DR (OUP) 15-May; X JUN: DR (Gates) 30-Jun; X JUL: PU 31-Jul; X SEP: DSB 9-Sep; X OCT: PU 31-Oct; X DEC: DR (OUP) 15-DecPU 15-Dec; X JAN: PU 31-Jan; X JUL: DR (OUP) 15-Jul; X AUG: DR (OUP) 1-Aug; X JUL: DR (OUP) 15-Jul
| YEMEN |  | SCI | Al Ansari | 243343 | 2014-05-01 | 2015-03-31 | X JUN: DSB; X AUG: PU 31-Aug; X SEP: DR 15-Sep; X NOV: PU 30-Nov; X MAR: PU 31-Mar; X APR: DR 15- Apr
14 | YEMEN | 080200 | SCI | Al Ansari, Gates | 150000 | 2013-03-01 | 2013-12-31 | FEB: GA; MAR: DSB 1-Mar; JUN: PU 30-Jun; SEP: DSB 30-SepPU 30-Sep; JAN: DSB 31-JanPU 31-Jan; X MAY: DR (Ansari) 1-May; X JUN: DR (Gates) 30-Jun
15 | ZAMBIA |  | GGI (St. Pauls, EHCZ) | Legatum | N/A |  | 2014-06-30 | X MAR: DR 31-Mar; X SEP: DR (SIFund) 30-Sep
16 | ZIMBABWE | 080180 | SCI | Zakharov, Masiyiwa | 146500 | 2012-09-01 | 2016-01-31 | FEB: DSB 1-Feb; MAY: PU 30-May; AUG: DSB 15-Aug; SEP: DR 15-Sept; JAN: PU 31-Jan; X MAR: DSB 15-Mar; X SEP: DR 31-Aug; X JAN: PU 31-Jan; X MAR: DSB 15-Mar; X JAN: PU 31-Jan