## Summary
PHC Qualitative Metrics
KEY INDICATORS | [5 empty] | Liberia | Rwanda | Burundi | Malawi | Zimbabwe | Sierra Leone
1. All identified industries producing fortified foods meet the designated national standard | [5 empty] | Yes | No | No | No | No | N/A
2. All identified importers importing fortified foods meet the designated national standard | [5 empty] | No | No | No | No | No | N/A
3. Samples are taken from industry, border, and market on a regular (quarterly) basis | [5 empty] | No | No | No | No | No | N/A
4. Non-compliance measures are taken as relevant for local industry and / or importers | [5 empty] | No | No | No | No | No | N/A
5. Surveillance mechanisms are put in place to ensure at least 80% of the target population is consuming fortified foods | [5 empty] | No | No | No | No | No | N/A
BENCHMARKS REQUIRED TO MEET INDICATORS
| Phase | Data | Status | Comments | Anticipated completion
LIB | Preparing for data collection
|  | Is the sampling plan in place? | Yes | Incorporated into national guidelines
|  | Has a clear data flow chart been decided upon and presented? | Yes | Agreed upon my relevant bodies and incorporated into national guidelines
|  | Have inspector trainings been held? | Yes | MoH and Port inspector trainings completed as of June 2015 | Still more trainings to occur starting Oct 2015
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes | All inspectors have been informed by their respective ministries, however, they are not yet inspecting.
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | Yes
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | 2015-08-01
Data collection
|  | Have all samples been taken? | No | Domestic facilities: yes. Imported: partial with emphasis only on salt | 2015-07-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2015-07-01
|  | Have all qualitative tests been complete? | No |  | 2015-07-01
|  | Have all quantitative tests been complete? | No |  | 2015-07-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2015-07-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2015-07-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2015-07-01
Data results
|  | Do all industry comply? | Yes
|  | Do all importers comply? | No |  | 2015-08-01
|  | Do all market samples comply? | No |  | 2015-09-01
|  | Have all non-complying importers / producers been identified? | No |  | 2015-09-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2015-09-01
|  | Do we understand contraints preventing compliance? | No |  | 2015-09-01
|  | Do all products meet designated logo requirements? | No |  | 2015-09-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-05-01
|  | Have surveillance mechanism discussions begun with stakeholders? | Yes |  | 2016-05-01
| Phase | Data | Status | Comments | Anticipated completion
RWA | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes | However, there will likely need to be refresher trainings
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | No | Pending RFMA | 2015-08-01
|  | Are all importers and local producers aware of their responsibilities? | No | Pending RFMA | 2015-08-01
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | No |  | 2015-08-01
|  | Have all data forms been harmonized? | No |  | 2015-08-01
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | 2015-01-01
Data collection
|  | Have all samples been taken? | No |  | 2015-10-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2015-10-01
|  | Have all qualitative tests been complete? | No |  | 2015-10-01
|  | Have all quantitative tests been complete? | No |  | 2015-10-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2015-11-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2015-11-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2015-11-01
Data results
|  | Do all industry comply? | No |  | 2015-12-01
|  | Do all importers comply? | No |  | 2015-12-01
|  | Do all market samples comply? | No |  | 2015-12-01
|  | Have all non-complying importers / producers been identified? | No |  | 2016-01-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2016-01-01
|  | Do we understand contraints preventing compliance? | No |  | 2016-01-01
|  | Do all products meet designated logo requirements? | No |  | 2015-12-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2015-12-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2015-12-01
| Phase | Data | Status | Comments | Anticipated completion
BUR | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | No | Local producers, yes; importers, no | 2015-07-01
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | No |  | 2015-08-01
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | TBD |  | 2015-08-01
Data collection
|  | Have all samples been taken? | No |  | 2015-09-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 407490
|  | Have all qualitative tests been complete? | No |  | 2015-10-01
|  | Have all quantitative tests been complete? | No |  | 2015-10-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2016-01-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2016-01-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2016-01-01
Data results
|  | Do all industry comply? | No |  | 2016-01-01
|  | Do all importers comply? | No |  | 2016-01-01
|  | Do all market samples comply? | No |  | 2016-01-01
|  | Have all non-complying importers / producers been identified? | No |  | 2016-02-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2016-03-01
|  | Do we understand constraints preventing compliance? | No |  | 2016-03-01
|  | Do all products meet designated logo requirements? | No |  | 2016-02-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-05-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2016-05-01
| Phase | Data | Status | Comments | Anticipated completion
MAL | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes | Refresher trainings are needed | 2015-08-01
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | No | Pending purchase from IA grant | 2015-08-01
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | 2015-09-01
Data collection
|  | Have all samples been taken? | No | Only sugar and salt | 2015-07-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2015-08-01
|  | Have all qualitative tests been complete? | No |  | 2015-08-01
|  | Have all quantitative tests been complete? | No |  | 2015-08-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2015-11-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2015-11-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2015-11-01
Data results
|  | Do all industry comply? | No |  | 2015-11-01
|  | Do all importers comply? | No |  | 2015-11-01
|  | Do all market samples comply? | No |  | 2015-11-01
|  | Have all non-complying importers / producers been identified? | No |  | 2015-12-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2015-12-01
|  | Do we understand constraints preventing compliance? | No |  | 2015-12-01
|  | Do all products meet designated logo requirements? | No |  | 2015-11-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2015-12-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2015-12-01
| Phase | Data | Status | Comments | Anticipated completion
ZIM | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | Yes
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | TBD |  | 2015-09-01
Data collection
|  | Have all samples been taken? | No |  | 2015-09-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2015-10-01
|  | Have all qualitative tests been complete? | No |  | 2015-10-01
|  | Have all quantitative tests been complete? | No |  | 2015-10-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2016-01-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2016-01-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2016-01-01
Data results
|  | Do all industry comply? | No |  | 2016-01-01
|  | Do all importers comply? | No |  | 2016-01-01
|  | Do all market samples comply? | No |  | 2016-01-01
|  | Have all non-complying importers / producers been identified? | No |  | 2016-03-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2016-03-01
|  | Do we understand constraints preventing compliance? | No |  | 2016-03-01
|  | Do all products meet designated logo requirements? | No |  | 2016-01-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-04-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2016-04-01
| Phase | Data | Status | Comments | Anticipated completion
SL | Preparing for data collection
*PENDING |  | Is the sampling plan in place?
Has a clear data flow chart been decided upon and presented?
Have inspector trainings been held?
Have trainings for major importers and industry been held?
Are all inspectors aware of their roles?
Have monitoring responsibilities been clarified?
Are al importers and local producers aware of their responsibilities?
Have all equipment and reagent needs been identified?
Have all equipment and reagent needs been procured?
Have all data forms been harmonized?
Have individual responsibilities for data collation and entry been identifed?
When will sample collection begin?
Data collection
Have all samples been taken?
Have all samples arrived at the appropriate lab on time?
Have all qualitative tests been complete?
Have all quantitative tests been complete?
Are reports generated on a quarterly basis for all imports?
Are reports generated on a quarterly basis for all industry?
Are reports generated on a quarterly basis for all markets?
Data results
Do all industry comply?
Do all importers comply?
Do all market samples comply?
Have all non-complying importers / producers been identified?
Have all non-complying importers / producers been contacted?
Do all products meet designated logo requirements?
| Reach | Have surveillance mechanisms been put into place to track coverage?
Have surveillance mechanism discussions begun with stakeholders?

## LIB status report
Obtaining adequate Monitoring Data
|  | STATUS | COMMENTS
1 | Is the sampling Plan in place? | Yes
1.1 | How many industries need to be sampled? | 3 - 5 random samples every quarter | Currently, Premier Milling Corporation as well as Fouani Brothers Inc. will be viewed as industries, since the first is producting locally and the second is the biggest importer of cooking oil. PMC: Samples to be taken from raw materia, premix and finished product.
1.2 | How many imporers need to be sampled? | 1 major importer for each commodity will be inspected in addition to 1 randomly selected importer from the rest. | 10% of the total sum of importers must be sampled each quarter. The major sugar importers will be confirmed during the training and passed on to the MoCI inspectors. Random samples will be done by inspectors, standard method for sampling preexists and inspectors will be taught to use it during training According to Trade Data, these are the major importers 2012 - 2013:
|  |  | Flour 1 Nouma Foods Limited 2 Supreme Food Service 3 J&R Enterprise Inc. 4 Massaffi General Trading Corporation 5 Supplying West Africa Traders Inc. 6 Trands-Mondial 7 Founani Brothers 8 Eid Brothers Inc. 9 Monoprix Supermarket 10 Missra Business center | Cooking Oil: 1 Fouani Brothers Corporation 2 Bridgeway Corporation 3 H.K. Enterprise 4 Supreme Food Service 5 Monoprix Supermarket 6 ERA Trade Corporation 7 Supreme Food Service 8 Habibi Enterprise 9 Logistics/Clearing & Forwarding 10 Liberian Trading Center | Salt: 1 Fouani Brothers Corporation 2 T. Choithram&Sons 3 A-Z Corporation 4 Eid Brothers Inc. 5 Bridgeway Corporation 6 Barbar Motors Corporation / ATCO 7 Abi Jaoudi & Azar Trading Corporation 8 Monoprix Supermarket 9 H&A Corporation 10 UN Drive Supermarket | Sugar: 1 A-Z Corporation 2 Fouani Brothers Corporation 3 Liberia Coca Cola Bottling Company 4 Alpha & Borhters Corporation 5 Supplying West Africa Traders Inc. 6 Bridgeway Corporation 7 Alpha & Brothers Corportaion 8 Euro-American Food Inc. 9 Mila Commoditites Ltd 10 H&A Corporation
1.3 | How many ports and border points need to be sampled? | 3 ports: Greenville, Freeport, buchanan 3 borderpoints each quarter / Cchosen by rotation in accordance with the M&E Tool | 3 ports total 12 borderpoints
1.4 | How many markets and households need to be sampled? | 1 market &10 households in 1 district per year | Evaluation once a year by the inspectors. For 15 counties, one major market will be focused on. Environmental and Occupational Health Inspectors choose a district on a random basis and test minimum of 10 households. In the 15 Counties there are a total of 68 Districts, listed on the right.
1.5 | Have the responsible agencies/ministries and departments for inspection been identified? | yes | MoHSW, MoF have handed in the names of the inspectors, MoCI pending.
1.6 | Have the roles been clearly distributed? | yes
1.7 | Is the frequency of inspections clear to all inspecting agencies/ministries? | yes
2 | Have trainings been planned? | yes | Training Manuals have been completed Pending: Equipment / BASF test kits on their way Trainings planned for June/July
2.1 | Have all inspecting agencies recveived a training plan? | No
2.2 | Have all inspecting agencies been trained on gathering samples? | No
2.3 | Has it been clearly defined and communicated which inspections will be done on which levels (e.g. markets, point of entry, households, commercial sites…) | yes
2.4 | Who will be responsible for the trainings? | yes
2.5 | How will it be ensured that every inspector is present at the training? | attendance list compared to list of inspectors. | We have received inspector listings from: MoF / MoHSW
2.6 | Has all the equipment needed arrived? If not, what is being done to ensure that it does? | no | we have: 1 iCheck oil / 1 iCheck flour / 28 BASF testing kits. we need: min 1 iCheck for lab: one for sugar, and salt. 1 iCheck for Founani, 1 for PMC UNICEF has agreed to procure salt test kits next year for us to use.
3 | Have trainings for major importers and industry been held? | no | after inspector training, we train the technical staff of major importers. Check importer list. Only major importers, responsible for more than 10% of imports will be trained
3.1 | Is the premix stored correctly? | no
3.2 | Are measures clear concerning the handling and storage of the fortificant(s)? | no
3.3 | Are Certificate of Analysis available from every delivery of the fortificant? | no
3.4 | Are quality assurance measures in place, including correct equipment, storage, etc.? | no
3.5 | Are analyses of the fortification levels of the proudcts being fortified routinely taken? | no
3.6 | Are routine in-house analysis of the micronutrient levels/ presence in the finished product being done? | no
3.7 | Are enough samples being taken during production , before the production and after the production? | no
3.8 | Are fortificant premix samples being taken regularly and being tested at the NSL? | no
4 | Are all inspectors aware of their roles? | no
4.1 | General QA practices and record keeping including sample collection, production procedures and equipment maintenance? | no
4.2 | Properly review the Certificates of Analysis and recognize appropriate fortificants and levels | no
4.3 | Number of samples that need to be taken is clear? | no
4.4 | Are they aware when to take the samples? | no
4.5 | Where are samples taken to? | samples taken to NSL by focal person, during training this person will be identified by name | Will be identified by name during the trainings
4.6 | Is everyone aware of the focal person responsible for taking the data and samples to the NSL? | samples taken to NSL by focal person, during training this person will be identified by name | Will be identified by name during the trainings
5 | Have monitoring responsibilities been clarified? | yes | Konah Okai (analyst) and Melvin Togbah (coordinator for chemical laboratory) of the NSL
5.1 | Has the monitoring tool been introduced to all to ensure that all realize WHY it is important to take proper samples? | no | part of training to ensure that all inspectors know why they are collecting what for which reason.
5.2 | Is it clear how data and samples will flow from the inspecting agency to the National Standards Laboratory? | yes
5.3 | Who will input results into tool | NSL - Konah Okai
5.4 | Who will communicate information from NSL to the MoHSW Secretariat? | NFA and secretariat will get information via email. | NSL keeps all originals
5.5 | Who will control the data at the MoHSW? | Helena
5.6 | Who will communicate the results to the industry and importers? | NSL - Konah Okai
5.7 | Who will be responsible for the signing of certificates for the National Fortificaiton Logo? | Stephen Mambu
6 | Are importers and local producers aware of their responsibilities? | yes | A second importer meeting was held May 2nd, 2015 covering the logo guideinlines, acquisition of the logo, fining procedures and inspection processes. All information were additionally sent to the importers and industry, including BIVAC who is fully aware of their responisiblities as well.
6.1 | Sample taking procedures? | yes
6.2 | Premix handling? | yes
6.3 | Storage? | yes
7 | When will the sample collection begin? | 01.07.2014
8 | Have all data collection forms been harmonized? |  | will be compared at trainings
PHC Qualitative Metrics
Qualitative: Measure program implementation and monitoring
|  | Information obtained | Timeframe |  | Tool / Who transfers data | [7 empty] | Average Values
[5 empty] | Liberia | Salone |  |  | Wheat flour | Salt | Cooking Oil | Sugar | NSL | MoHSW | Variance | % importers adhering to NS | % producers adhering to NS | Total % adhering to NS
1 | All identified industries and importers producing and importing foritified foods meet the designated national standards. | NSL | 2014-01-15 | 2014-12-31 | M&E Tool / NSL | / | LIBERIA | Total # of Importers complying
[5 empty] | NSL collaboration: As soon as inspections start and foods are tested, PHC will have to work with NSL to input data. MoHSW Secretariat should understand data as well and be present at all Technical Staff or Production and Distribution meetings, where results are discussed. All Inspectoing agencies MUST ATTEND THESE MEETINGS FROM NOW ON! Time Frame: all 2014: constant monitoring through PHC must be top priority to ensure a functioning tool from the beginning. | create a Production and Distribution Subcommittee to exchange information. Intorduce Tool. Find out who is collecting data at all. |  | Absolute #
Relative #
Average level of fortification
Market
Border
Household
Port
Total # of Importers complying
[7 empty] | SALONE | Absolute #
Relative #
Average level of fortification
Market
Border
Household
Port
2 | Samples are taken from industry, border and market on a regular (at least quarterly) vasis. | NSL | 2014-01-15 |  | Inspections / NSL | /
Respective inspector ministry meetings vs. NSL data: Once a quarter meetings with respective inspecting ministries necessary to find out how many inspections were undertaken. This data should then be compared to the data of the NSL. If there's a variance, we must correct and find out if potentially more trainings are necessary or other measures. Time Frame: All 2014, same as above, longer if required.
3 | Samples are tested and results are provided to industry / importers and the NFA (at least quarterly) | NSL / NFA | 2014-01-15 |  | Inspections / NSL | /
NSL collaboration: Required number of samples reach NSL - required number is CLEARLY DEFINED IN M&E TOOL Compare Nr. Of Samples with Nr. Of Importers. Also compare with trade data to ensure compatibility and correct mistakes
4 | Non-compliance measures are takes as relevant for local industry and / or importers. | Bureau of Standards | 2014-01-15 |  | Nr. Of non Compliance measures implemented /MoCI | /
NSL reports non-compliance to Standards Department of MoCI. Until the NSB is created, close collaboration with the Standards Department. DEFINE ONE PERSON RESPONSIBLE FOR ACCUMULATING NON-COMPLIANCE AND SENDING TO NFA NFA should discuss these accumulated measures at each meeting while all stakeholders are present
5 | Surveillance mechanisms are put in place to ensure that at least 80% of the target popultaion is consuming fortified foods. | Ministry of Health | 2014-01-15 |  | Nr. Of surveillance mechanisms out into place vs. % of population consuming fortified foods / Inspections (NSL) | /
???
Fiscal Monitoring
|  | PHC | 10/2013 - 12/2013 | Budget | 19131 | 12906
|  | PHC | 10/2013 - 12/2013 | Actual | 20628 | 5398
|  | PHC | 10/2013 - 12/2013 | Variance | 1497 | -7508
Green - Accomplished
Orange - Initiated and ongoing
Red - Pending
Bomi County
Dewoin District
Klay District
Mecca District
Senjeh District
Bong County
Fuamah District
Jorquelleh District
Kokoyah District
Panta-Kpa District
Salala District
Sanayea District
Suakoko District
Zota District
Gbarpolu County
Belleh District
Bopolu District
Bokomu District
Kongba District
Gbarma District
Grand Bassa County
District #1
District #2
District #3
District #4
Owensgrove District
St. John River District
Grand Cape Mount County
Commonwealth District
Garwula District
Gola Konneh District
Porkpa District
Tewor District
Grand Gedeh County
Gbarzon District
Konobo District
Tchien District
Grand Kru County
Buah District
Lower Kru Coast District
Sasstown District
Upper Kru Coast District
Lofa County
Foya District
Kolahun District
Salayea District
Vahun District
Voinjama District
Zorzor District
Margibi County
Firestone District
Gibi District
Kakata District
Mambah-Kaba District
Maryland County
Barrobo District
Pleebo/Sodeken District
Montserrado County
Careysburg District
Greater Monrovia District
St. Paul River District
Todee District
Nimba County
Gbehlageh District
Saclepea District
Sanniquelleh-Mahn District
Tappita District
Yarwein-Mehnsohnneh District
Zoegeh District
River Gee County
Gbeapo District
Webbo District
Rivercess County
Morweh District
Timbo District
Sinoe County
Butaw District
Dugbe River District
Greenville District
Jaedae Jaedepo District
Juarzon District
Kpayan District
Pyneston District

## LIB flow charts
_ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _
_ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _
Inspectors
Environmental Health Technicians (EHT), MoHSW
EHT responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits. Iodine spot test kits are used for salt.
3. Results are recorded in appropriate forms
EHT transfers samples and forms to Food Safety Coordinator (FSC)
The EHTs transfers completed forms and samples for quantitative testing to the CHT Food Safetey Coordinator each quarter via airplane or road. Transfer of samples must happen within 24 hrs of collection.
FSC transfers samples and forms to NSL
The FSC transfers completed forms and samples for quantitative testing to NSL each quarter. Transfer of samples must happen within 24 hrs of collection.
Market and HH inpections at County and District levels
Port and Border Level inspections
MoF Custom Officers
MoHSW Port Health Officers
Custom Officer Responsibilities
1. Every quarter, composite samples for each imported staple food brand (oil, sugar, flour, and salt) are collected at designated borders / ports.
2. Every quarter these samples are transfered to the Port Health Officer located at the respective port / border.
Port Health Officer Responsibilities
1. Qualitative tests are conducted by the Port Health Officer on oil and sugar brand samples using BASF test kits. Iodine spot test kits are used for salt.
2. Results are recorded in appropriate forms.
3. Results and samples for quantitative testing are provided to the Food Safety Coordinator, MoHSW
Food Safety Coordinator Responsibilities
1. The Food Safety Coordinator transfers samples for quantiative testing and qualitative results to NSL within 24 hours.
Food Safety Coordinator
BIVAC:
Responsible for pre-shippment inspections
Industry Level Inspections
Inspectors
Standards Officer, MoCI
Standards Offier Responsibilities
1. Every quarter, composite samples for each domestically produced staple food product are collected.
2. If a qualititave testing method exists, they are conducted.
3. Results are recorded in appropriate forms.
Standards Officer transfers samples and forms to Standards Director, MoCI
This happens each quarter via airplane or road. Transfer of samples must happen within 24 hrs of collection.
Standards Director tansfers forms to NSL
Samples and results are then transfered to the NSL for quantiative testing.
This happens each quarter via airplane or road. Transfer of samples must happen within 24 hrs of collection.
National Standards Laboratory
Receives samples every quarter from:
1. Food Safety Coordinator, MoHSW
2. Standards Director, MoCI
NSL Responsibilities:
1. Tests all composite samples quantitatively using iChecks
2. Inputs quantitative data and qualitative data from submitted forms into the Monitoring Tool
3. Reports results to NFA Secretariat and GAIN on a quarterly basis
4. Issues National Fortification Logo to importers and producers after application and conformity have been confirmed
5. Conducts refresher training for inspectors on sampling and monitoring procedures as needed
6. Follows outlined procedures in the case of non-compliance
7. After third warning to non-compliant producer or importer, NSL reports event to Ministry of Justice. MoJ

## MAL status report
Institution | Kind of Training | How many to be trained | Who will provide | Status
MBS | Inspector Training and Laboratory Training | All MBS inspectors and ALL lab personel (45 people) | Technical consultant | All MBS inspectors AND lab personel were trained on OIL fortification
MOH | Inspector Training and Laboratory Training | DEHOs at national level and EHOs at district level (28 DEHOs and 100+ EHOs) | Consultant on Lab, CHSU and MOH for DEHOs | DEHOs have been trained but problems of sending samples still remain - MOH trained on Monitoring Tool and CHSU just lab equipment constraints for oil, sugar, and flour
MRA | Sensitization for border inspectors | All inspectors at each border post (Need figure on number of inspectors) | Maybe MBS could do this? Inquiry to Sindani pending | No trainings to date for MRA
Vehicle | Salt | Oil | Sugar | Maize/Wheat Flour
MBS | Refresher training needed on proper inspection at borders | Training COMPLETE at factory level | Some training initiated at factory level but more needed for ALL inspectors - Lab needs icheck machine | Training needed for ALL inspectors - equipment needed at lab
MOH | Inspector Training and Laboratory Training | DEHOs at national level and EHOs at district level (28 DEHOs and 100+ EHOs) | Consultant on Lab, CHSU and MOH for DEHOs | DEHOs have been trained but problems of sending samples still remain - MOH trained on Monitoring Tool and CHSU just lab equipment constraints for oil, sugar, and flour
MRA* | Refresher training needed | N/A | N/A | Trainings needed for fortification of flour coming through borders
*No MRA inspectors at market level - need to see what imports are coming in for maize and wheat flour
Samples Collected From… | Institution Samples going to… | Contact Person | How often | Where and when will results go? | Cost
Border and Factory Samples | MBS | Sindani Wangawanga | Quarterly | back to factory and to MOH HQ; within 1-2 weeks | Border industries pay MBS, no cost to factories
Market samples | CHSU | Jelita Gondwe | Quarterly | back to MOH and district offices; within 1-2 weeks | No cost to districts, although some vendors request payment for samples
Contracted | Chancellor College | Samson Sajidu | As needed basis | back to MBS or MOH; within 1-2 weeks | Contractor's fee
Institution | Current Equipment | Needed Equipment | Status
| UV Spectrometer | icheck for sugar and one for oil | One icheck should be included in Bunda Proposal
MBS | UV Spectrometer | icheck for sugar | One icheck should be included in Bunda Proposal
MOH
Chancellor College

## MAL Martket and Factory Samples
| SALT | OIL | SUGAR | MAIZE | WHEAT
Industries | N/A | Unilever | Illovo | Rab Processors | Rab Processors
|  | CORI |  | Premier Foods | Bakhresa
|  | Oil and Protein |  | Kharti Brothers, Ltd. | Premier Foods
|  | Mulawe |  |  | Universal Industries
|  | Mapanga |  |  | Capital Foods
Importers | Agora | Shoprite | N/A | HMS Foods | HMS Foods
| Bharat Trading | Transglobe Produce Export |  | Game Stores | Game Stores
| Chimalira Enterprises | Spider Corporation? |  | Shoprite | Shoprite
| Eco Products | SANA |  | Chipiku | Chipiku
| Fadamz Rice Mill | Vega Foods
| Family Pride | Chipiku |  |  |  |  | *Percentages based on population of districts
Rab Processors
Rice Milling
Tambala Food Products
Markets* | Northern Region - 7 districts - 18.5 % country's markets | Northern Region - 7 districts - 18.5 % country's markets | Northern Region - 7 districts - 18.5 % country's markets | Northern Region - 7 districts - 18.5 % country's markets | Northern Region - 7 districts - 18.5 % country's markets
| Central Region - 7 districts - 35.7 % country's markets | Central Region - 7 districts - 35.7 % country's markets | Central Region - 7 districts - 35.7 % country's markets | Central Region - 7 districts - 35.7 % country's markets | Central Region - 7 districts - 35.7 % country's markets
| Southern Region - 12 distrcits, 45.6 % country's markets | Southern Region - 12 distrcits, 45.6 % country's markets | Southern Region - 12 distrcits, 45.6 % country's markets | Southern Region - 12 distrcits, 45.6 % country's markets | Southern Region - 12 distrcits, 45.6 % country's markets
DISTRICT* | SALT | OIL | SUGAR | MAIZE FLOUR | WHEAT FLOUR | WHO is testing | How Often
Chitipa | 6 | 2 | 2 | 1 | 2 | CHSU | Every Quarter | Northern District
Karonga | 8 | 3 | 3 | 2 | 3 | CHSU | Every Quarter
Nkhata Bay | 6 | 2 | 2 | 1 | 2 | CHSU | Every Quarter | Central District
Rumphi | 5 | 2 | 2 | 1 | 2 | CHSU | Every Quarter
Mzimba | 26 | 10 | 10 | 5 | 10 | CHSU | Every Quarter | Southern Distric
Likoma | 0 | 0 | 0 | 0 | 0 | CHSU | Every Quarter
Kasungu | 22 | 9 | 9 | 4 | 9 | CHSU | Every Quarter |  | *Sample number based on district population size
Nkhotakota | 10 | 4 | 4 | 2 | 4 | CHSU | Every Quarter
Ntchisi | 8 | 3 | 3 | 2 | 3 | CHSU | Every Quarter
Dowa | 17 | 7 | 7 | 3 | 7 | CHSU | Every Quarter
Salima | 12 | 5 | 5 | 2 | 5 | CHSU | Every Quarter
Lilongwe | 69 | 28 | 28 | 14 | 28 | CHSU | Every Quarter
Mchinji | 15 | 6 | 6 | 3 | 6 | CHSU | Every Quarter
Dedza | 22 | 9 | 9 | 4 | 9 | CHSU | Every Quarter
Ntcheu | 17 | 7 | 7 | 3 | 7 | CHSU | Every Quarter
Mangochi | 26 | 11 | 11 | 5 | 11 | CHSU | Every Quarter
Machinga | 14 | 5 | 5 | 3 | 5 | CHSU | Every Quarter
Zomba | 25 | 10 | 10 | 5 | 10 | CHSU | Every Quarter
Chiradzulu | 10 | 4 | 4 | 2 | 4 | CHSU | Every Quarter
Blantyre | 40 | 16 | 16 | 8 | 16 | CHSU | Every Quarter
Mwanza | 6 | 2 | 2 | 1 | 2 | CHSU | Every Quarter
Thyolo | 20 | 8 | 8 | 4 | 8 | CHSU | Every Quarter
Mulanje | 19 | 8 | 8 | 4 | 8 | CHSU | Every Quarter
Phalombe | 11 | 4 | 4 | 2 | 4 | CHSU | Every Quarter
Chikwawa | 16 | 6 | 6 | 3 | 6 | CHSU | Every Quarter
Nsanje | 8 | 3 | 3 | 2 | 3 | CHSU | Every Quarter
Balaka | 11 | 4 | 4 | 2 | 4 | CHSU | Every Quarter
| 450 | 180 | 180 | 90 | 180
Vehicle | Industry | Number of Samples (per Quarter) | Frequency | Total (per year) | Who is Testing
SALT (Packers) | Halima | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Rab Processors | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Rice Milling | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Tambala Food Products | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
Total Samples |  |  |  | 160 | Nationally per year
SALT (Borders) | Northern Region (5 entry points, 20%) | 9 | 1 x Quarter .: 4 x per year | 36 | MBS/MOH/MRA
| Central Region (4 entry points, 50%) | 21 | 1 x Quarter .: 4 x per year | 84 | MBS/MOH/MRA
| Southern Region (5 entry points, 30%) | 15 | 1 x Quarter .: 4 x per year | 60 | MBS/MOH/MRA
Total Samples |  |  |  | 180 | Nationally per year
OIL | Unilever | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| CORI | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Oil and Protein | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Mulawe | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Mapanga | 3 | 1 x Quarter .: 4 x per year | 12 | MBS
Total Samples |  |  |  | 172 | Nationally per year
SUGAR | Illovo (at Nchalo) | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Illovo (at Dwangwa) | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
Total Samples |  |  |  | 80 | Nationally per year
MAIZE FLOUR | Rabs Processors | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Premier Foods | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
Total Samples |  |  |  | 80 | Nationally per year
WHEAT FLOUR | Bakhresa | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Capital Foods | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
| Universal Industries | 10 | 1 x Quarter .: 4 x per year | 40 | MBS
Total Samples |  |  |  | 120 | Nationally per year

## MAL flow charts
_ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _
_ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _ _
GAPS: | Border level - MBS and MOH are not working together at the borders, samples results take long to get back, and equipment is not always available
Market level - Most inspectors at the districts claim of lack of resources (test kits, transport, etc) and samples are not sent on time
Household level - lack of consistent sampling due to lack of resources at village level
Overall: There needs to be better communication between MBS and MOH, and between MOH HQ, CHSU, and the districts
SOLUTIONS: | Equipment needs at the borders and labs need to be addressed (outside funding? Bunda proposal?)
Increased communication needs to happen between MBS and MOH (official document was shared in 2013 agreeing to share data)
Increased communication between MOH, districts, and CHSU (the Monitoring Tool is supposed to help with some of this)
Continued trainings of DEHOs and MBS inspectors with Appreciation/Recoginition rewards
Border and Factory Level inspections
MBS Inspectors
MoH EHO
MBS Inspector Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected at each borders point and at domestic factories.
2. Random qualitative tests are conducted on composite samples.
3. Results are recorded in appropriate forms and sent via transport to MBS with samples for quant testing within 24 hours of collection.
Inspectors
MBS and Environmental Health Officers (EHO)
MoH EHO Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected at each borders point.
2. Random qualitative tests are conducted on composite samples.
3. Results are recorded in appropriate forms and sent via transport to MBS with samples for quant testing.
4. Quant results are shared with MOH HQ for input into the Monitoring Tool
MBS Lab
1. Samples are tested quantitatively at importers expense. Routine factory samples are tested each quarter at no expense
2. MBS makes decision to allow or deny the stock into the country. At factory level, MBS returns the results within 14 days and noncompliance measures taken if necessary
3. MBS sends data to MoH for input into Monitoring Tool within two weeks.
MoH Monitoring Tool
1. Results are sent to MoH via e-mail in the Tool formatting to be inputted.
2. A decision is made regarding compliance measure within one week and results are reported quarterly.
Inspectors
District Environmental Health Officers (DEHOs), MoH
DEHO Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected from various markets in the country.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour.
3. 100g samples are collected and labeled according to CHSU standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
4. DEHOs transport samples to CHSU via hospital vehicle within 24 hrs of sample collection.
CHSU (MoH Lab)
1. Samples arrive at CHSU once a quarter for quant testing. Turn around time is 2 weeks.
MoH Monitoring Tool
1. Results are sent via e-mail by CHSU to MoH within 2 weeks for input into Monitoring Tool.
2. MoH adapts the data from the CHSU format into the Monitoring Tool format.
3. MoH produces report within one week for CHSU, DEHOs, and NFA.
Market Level Inspections
Results to MoH
1. DEHOs follow-up with CHSU for results by phone or e-mail after 1-2 weeks.
2. DEHOs must travel to CHSU to obtain results.
Inspectors
Health Surveillance Assistants (HSAs), MoH
HSA Responsibilities
1. Every quarter, conduct random sampling of fortified products within households
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour.
3. 100g samples are collected and labeled according to CHSU standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
4. HSAs send results and samples to DEHOs located at the District Hospital via vehicle or bicycle transport.
DEHOs
1. Transport samples to CHSU for quantitative testing via hospital ambulance.
MoH
1. MoH / EHo advise MBS when there are problems and MBS communicates with industry.
Household Level Inspections
CHSU
1. Tests HHs samples within 2 weeks of receiving samples (once a quarter)
2. DEHOs follow-up with CHSU after 2 weeks for results.
3. CHSU reports result to MoH within one week of generating results
Malawi Bureau of Standards
Receives samples every quarter from:
1. All border points via MBS inspectors
2. All fortifying industries via MBS inspectors
3. All markets via MoH DEHOs
NSL Responsibilities:
1. Tests all composite samples quantitatively using iChecks
2. Inputs quantitative data and qualitative data from submitted forms into the Monitoring Tool input form and sends to MoH once a quarter
3. Reports results to NFA quarterly
4. Issues National Fortification Logo to importers and producers who apply and have shown conformity through two rounds of sampling and testing by MBS inspectors
5. Conducts refresher training for inspectors on sampling and monitoring procedures as needed
6. Follows outlined procedures in the case of non-compliance based on FFL Guidelies

## RWA status report
Institution | Kind of Training | Who will be trained | Who will provide | Status
MOH | Training inspectors and Lab technicians | ALL new members of the Rwanda Food and Medicine Authority | PHC | Some of the inspectors were trained on sampling and testing of FF back in May 2013
Rwanda Bureau of Standards | Inspector Training and Laboratory Training | New recruited inspectors who will be posted at different entry posts. And those who will be at the district level like Rubavu regional lab | Those who attended the Sampling and testing training. | More than 15 inspectors from RBS attended the training in May 2013, but the challenge is the organization of the training of the new recruits due to Budget constraint
Vehicle | Salt | Oil | Sugar | Maize/Wheat Flour
MOH | Some of the hygiene inspecotrs were trained but a new training is need and equipment too. | All inspectors need to be trained and equipment needed. | All inspectors need to be trained, also equipment need like ichecks | All inspectors need to be trained and equipment needed
RBS | Some of the inspectors have been trained by ECSA and PHC. A new training is need for the new recruits. Reagents for the main Lab and field equipments needed. | Training is needed and reagents are also needed | All inspectors need to be trained | In 2010, ECSA trained some of the Lab technicians but inspectors need to be trained.
Samples Collected From… | Institution Samples going to… | Contact Person | How often | Where will results go?
Border and airport samples | RBS | ? | Quarterly | Back to importers then MOH
Market samples | MOH/RBS | Alphonsine Munana | Quarterly | MOH/ RBS
Factory samples | RBS | ? | Whenever possible/request from the client | Back to the client, then MOH
Institution | Current Equipment | Needed Equipment | Status
MOH | NONE | ichecks | The governemnt has started building a new Laboratory
RBS | UV Spectrometer | ichecks and reagents | Reagents are supposed to be in the country by end of March.

## RWA flow chart
GAPS: | More inspectors are needed at borders and factory levels (~10)
BASF equipment is needed for qual testing at borders
Ichecks and reagents are needed for quant testing at BBN laboratory
Logistics need to be improved to ensure appropriate transfer time to BBN Lab
A sampling plan needs to be put in place with appropriate training
Monitoring Tool needs to be adapted and training provided
Inspectors
RBS Inspectors
RBS Inspector Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected at each of Rwanda's X border points.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour. Resullts are recorded in appropriate forms.
3. 100g samples are collected and labeled according to RBS standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
4. Qual results (if relevant) and samples for quant testing are transported to RBS within 24 hrs of sample collection.
RBS Lab
1. Samples arrive at RBS once a quarter for quant testing using iChecks. Turn around time is 2 weeks.
2. If results are positive, products are allowed to enter market. If negative, they are denied entrance.
Border Level Inspections
Results Recorded
1. Results are recorded by appropriate RBS staff and sent to MoH / NFA for every quarter.
Inspectors
RBS Inspectors
BBN Inspector Responsibilities
1. Every quarter, RBS collects domestically produced samples.
2. Random samples are collected from production line and stock and composite samples are created and labeled according to RBS standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
3. Random qualitative tests are conducted using BASF test kits or iron-spot tests.
4. Results of the qual test and samples for quant testing using iChecks are taken to the RBS Lab.
5. Results are communicated to industry and sent to MoH quarterly.
Non-compliance
1. RBS identfies all domestic samples that do not comply with the standard.
2. RBS / MoIC send non-compliant letter within 2 weeks of obtaining results
Factory Level Inspections
Inspectors
Hygiene Inspectors, MoH
MoH Hygiene Inspector Responsibilities
1. Every quarter, conduct random sampling of fortified products in every district throughout the country.
2. Random qualitative tests are conducted on composite brand samples using BASF test kits, RTKs, and iron-spot tests as they are available.
4. Results are recorded in appropriate forms.
3. 100g samples are collected and labeled according to RBS standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
Results to RBS
1. Hygiene inspectors send results and samples to the RBS Lab within 24 - 48 hrs.
Market Level Inspections
RBS Laboratory and Non-compliance
1. Samples are analyzed using iChecks within X.
2. Appropriate step are taken based on non-compliance.
3. Results are shared with MoH and NFA quarterly.
Non-compliance
1. RBS identfies all imported samples that do not comply with the standard.
2. RBS / MoIC send non-compliant letter within 2 weeks of obtaining results.
Results Recorded
1. Results are communicated to industry and sent to MoH quarterly.
Rwanda Bureau of Standards
Receives samples every quarter from:
1. All border points via RBS inspectors
2. All fortifying industries via RBS inspectors
3. All markets via MoH Hygiene inspectors
RBS Responsibilities:
1. Tests all composite samples quantitatively using iChecks
2. Inputs quantitative data and qualitative data from submitted forms into appropriate monitoring form
3. Reports results to Alliance quarterly
4. Issues National Fortification Logo to importers and producers who apply and have shown conformity through two rounds of sampling and testing by RBS inspectors
5. Conducts refresher training for inspectors on sampling and monitoring procedures as needed
6. Follows outlined procedures in the case of non-compliance based on FFL Guidelies

## BUR status report
Institution | Kind of Training | Who will be trained | Who will provide | Status
MSPLS | Training inspectors and Lab technicians | All hygiene inspectors in the ministry and school of public health. | PHC | A sampling and testing training to be organized during the last quartet of the year 2014
Bureau Burundais de Normalisation | Inspector Training and Laboratory Training | All inspectors | PHC | A joint training of all inspectors to be held in the last quartet of 2014
Vehicle | Salt | Oil | Sugar | Maize/Wheat / CassavaFlour
MPSL | Some hyigiene inspectors were trained by unicef to use RTK. A new training and equipment are needed | All inspectors need to be trained and equipment needed. | All inspectors need to be trained, also equipment need like ichecks | All inspectors need to be trained and equipment needed
BBN | Some attended a UNICEF training 3 years ago. A new training and equipment are need. | All inspectors need to be trained and icheks needed. | All inspectors need to be trained | A training to all inspectors and ichecks are needed
Samples Collected From… | Institution Samples going to… | Contact Person | How often | Where will results go?
Border and airport samples | BBN | Eric Ruracenyeka | 3 months | Back to importers then MSPLS
Market samples | MSPLS/ SCHOOL OF PUBLIC HEALTH/ BBN | Aimee Nduwimana/ Eric Ruracenyaka | 3 months | MPSLS/SPB/BBN
Factory samples | BBN | Eric Ruracenyaka | Whenever it is required | Industry/ MSPLS
Institution | Current Equipment | Needed Equipment | Status
MSPLS | NONE | BASF/ichecks | The Burundi governemnt has no funds. They are going to talk to chinese to get a grant to build a new referal laboraroty. In the past they were using the CNTA and Facagro laboratories but are in very poor conditions .
BBN | UV Spectrometer | BASF equipment/Ichecks/Reagent | GIZ has shown interest to support the Bureau, but due to some politics, it is taking too long.

## BUR flow charts
GAPS: | More inspectors are needed at borders and factory levels (~10)
BASF equipment is needed for qual testing at borders
Ichecks and reagents are needed for quant testing at BBN laboratory
Logistics need to be improved to ensure appropriate transfer time to BBN Lab
Monitoring Tool needs to be adapted and training provided
Inspectors
BBN Inspectors
BBN Inspector Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected at each of Burundi's 7 border points.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour. Resullts are recorded in appropriate forms.
3. 100g samples are collected and labeled according to BBN standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
4. Qual results and samples for quant testing are transported to BBN within 24 hrs of sample collection.
BBN Lab
1. Samples arrive at BBN once a quarter for quant testing using iChecks. Turn around time is 2 weeks.
2. If results are positive, products are allowed to enter market. If negative, they are denied entrance.
Border Level Inspections
Results to MoH
1. Results are sent by BBN to the MoH PRONIANUT focal point person where they are recorded in the Monitoring Tool.
Inspectors
BBN Inspectors
BBN Inspector Responsibilities
1. Every quarter, BBN informs industry and / or industry requests inspection.
2. Random samples are collected from production line and stock and composite samples are created and labeled according to BBN standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
3. Random qualitative tests are conducted using BASF test kits or iron-spot tests.
4. Results of the qual test and samples for quant testing using iChecks are taken to the BBN Lab.
5. Results are communicated to industry and sent to MoH quarterly.
MoH Monitoring Tool
1. MoH-PRONIANUT adaptes the data from BBN into the Monitoring Tool format.
2. MoH shares results quarterly with the Alliance.
Factory Level Inspections
Inspectors
MSPLS / PSB Inspectors, MoH
MSPLS / PSB Inspector Responsibilities
1. Every quarter, conduct random sampling of fortified products with the X different districts throughout the country.
2. Random qualitative tests are conducted on composite brand samples using BASF test kits, RTKs, and iron-spot tests.
4. Results are recorded in appropriate forms.
3. 100g samples are collected and labeled according to BBN standards (coded by district abbreviation and sample # including brand name and site collected) and packed into black plastic papers.
Results to BBN
1. MSPLS / PSB's send results and samples to the BBN Lab within 24 - 48 hrs.
MoH Monitoring Tool
1. MoH focal point person inputs data into the Monitoring Tool.
2. Reports are shared with the Alliance quarterly.
Market Level Inspections
BBN Laboratory
1. Samples are analyzed using iChecks within X.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance.
MoH Monitoring Tool
1. MoH adapts the data from BBN into the Monitoring Tool format.
2. MoH shares results quarterly with the Alliance.
Results to MoH
1. Results are sent by BBN to the MoH- PRONIANUTperson where they are recorded in the Monitoring Tool.
Burundi Bureau of Standards
Receives samples every quarter from:
1. All border points via BBN inspectors
2. All fortifying industries via BBN inspectors
3. All markets via MoH MSPLS / PSB inspectors
BBN Responsibilities:
1. Tests all composite samples quantitatively using iChecks
2. Inputs quantitative data and qualitative data from submitted forms into the Monitoring Tool input form and sends to MoH once a quarter
3. Reports results to Alliance quarterly
4. Issues National Fortification Logo to importers and producers who apply and have shown conformity through two rounds of sampling and testing by MBS inspectors
5. Conducts refresher training for inspectors on sampling and monitoring procedures as needed
6. Follows outlined procedures in the case of non-compliance based on FFL Guidelies

## BUR market samples
| SALT | OIL | SUGAR | MAIZE | WHEAT | Cassava
Industries | All imported | SAVONOR | SOSUMO | MINOLAC | MINOTERIE DE MURAMVYA | MUSALAC
|  | MUKWANO |  | FARISANA | PEMBE | ETS TWUBAKANE
|  |  |  | PEMBE | AZAM | Ets EREST et Freres
Importers | ETS DIMITRI | Ets DIMITRI | OFFICIALLY NO SUGAR IS IMPORTED | ETS DIMITRI | ETS DIMITRI | ALL LOCALLY PRODUCED
| SIYOMVU | SIYOMVU |  | BURUNDI IMPEX | BURUNDI IMPEX
| BURUNDI IMPEX | BURUNDI IMPEX |  | PEMBE
| ETS DEWJI |  |  | MUKWANO FLOURS
Markets* | BUJUMBURA( All markets) | 4 Markets | 4 Markets | 4 Markets | 4 Markets | 4 Markets
| NGOZI( Ville Market) | 1 Market | 3 Markets( Buye,Mwumba,Ville) | 3 Markets | 4 major markets | 4 Markets
| GITEGA ( Ville Market) | 3 Markets( Giheta, Ville, Bukirasazi | 3 Market | 3 Major market | 3 Market
| BURURI( Ville Market) | 1 Market | 1 Market | 1 Market | 1 Market | 1 market
| MUYINGA( Ville Market) | 1 Major markets | 1 Major Markets | 1 Major Markets | 1Major Markets | 1 market

## ZIM status report
Institution | Kind of Training | How many to be trained | Who will provide | Status
GL | The GL will need capacity building in how to use new lab equipment and how to test for all nutrients in fortified products | ALL members of GL lab (approx 15) | UNICEF, outside consultant? | Budgeted for in proposal
EH Inspectors | EH Inspectors will need to be trained on spot test training in markets as well as factory level inspection and border level inspection, hopefully with iChecks | ALL EH inspectors* There are too many in the country to train every single person. MOH idea right now is to have a focal team within EH at National Level, they will take local authority teams to industries with them. Otherwise PEHOs and DEHOs will be trained on field inspections and expected to carry that training back to their EHOs. It is possible to train all Port Health Officers though. | UNICEF, donor partners, outside consultant? | Budgeted for in proposal
SAZ Inspectors | All SAZ inspectors to be trained on new lab equipment and factory level inspections | 6 full time personnel for inspections and 20 external personnel that can be subcontracted when there is more work | UNICEF, outside consultant? | Budgeted for in proposal
Vehicle | Salt | Oil | Sugar | Maize/Wheat Flour
GL | Already capacitated to test for iodine in salt | Training needed | Training needed | Training needed
EH | Already capacitated to test for iodine in salt - maybe refresher on RTKs and correct sample taking for quant sent to GL | Training needed | Training needed | Training needed
SAZ | Already capacitated for iodine in salt | Training needed | Training needed | Training needed
Institution | Current Equipment | Needed Equipment | Status
GL | UV Spectrometer | HPLC, iCheck for Vit A,iCheck Zinc, BASF Rapid for Vit A, reagents | Included in budget/proposal
SAZ | UV Spectrometer | HPLC, iCheck for Vit A,iCheck Zinc, BASF Rapid for Vit A, reagents | Included in budget/proposal
In the Field | RTKs | iChecks, BASF, WYD | to be shared from GL if reources allow
Laboratories | Samples Collected From… | Institution Samples going to… | Contact Person | How often | Where will results go? | When will results go? | Cost
GL | Border, Factory, and Market Level from PEHOs, DEHOs, EHOs | Government Analysis Lab | Bernard Samende | 3x a year | MOH HQ | Within 14 days | No cost
SAZ | Factory and Market level of Industries registered with SAZ | SAZ lab | Mrs. Marunda | Quarterly | MOIC/MOH? | Within 14 days | Cost to industry

## ZIM samples
| SALT | OIL | SUGAR | MAIZE | WHEAT
Industries | Netrade Marketing | National Foods | National Foods | National Foods | National Foods
| ProBrands | Pure Drop | ProBrands | Victoria Foods | Victoria Foods
| Grain Millers Board | United Refinements Ltd | Hulettes | Manyame Milling | UNI Products
| National Foods |  | Country Choice Foods | Grain Marketing Board | Baker's Inn
Importers | Pick N Pay Retailers | Pick N Pay Retailers | TM Industries | TM Industries | Premier Foods
| Cerebos Limited | Willowton Group | SPAR | SPAR | TM Industries
| TM Industries | TM Industries | OK Mart | OK Mart | SPAR
| SPAR | SPAR | Pick N Pay Retailers | Pick N Pay Retailers | OK Mart
| OK Mart | OK Mart | Bon Marche | Bon Marche | Pick N Pay Retailers
| Bon Marche | Bon Marche |  |  | Bon Marche
Markets* | 10 Provinces, 62 Districts, 1,200 Wards | 10 Provinces, 62 Districts, 1,200 Wards | 10 Provinces, 62 Districts, 1,200 Wards | 10 Provinces, 62 Districts, 1,200 Wards | 10 Provinces, 62 Districts, 1,200 Wards
Border Country | Border Post | Frequency | Inspectors | Who is Testing*
South Africa | Beit Bridge | 1 x every 4 months .: 3 x per year | Port Health | GL |  | *SAZ inspects at factory and market level for industries registered
| Mapungubwqe | 1 x every 4 months .: 3 x per year | Port Health | GL
| Chikwarakara | 1 x every 4 months .: 3 x per year | Port Health | GL
Botswana | Plumtree | 1 x every 4 months .: 3 x per year | Port Health | GL
| Kazungwa | 1 x every 4 months .: 3 x per year | Port Health | GL
Mozambique | Nyampanda | 1 x every 4 months .: 3 x per year | Port Health | GL
| Mutare | 1 x every 4 months .: 3 x per year | Port Health | GL
Zambia | Kariba | 1 x every 4 months .: 3 x per year | Port Health | GL
| Victoria Falls | 1 x every 4 months .: 3 x per year | Port Health | GL
| Chirundu | 1 x every 4 months .: 3 x per year | Port Health | GL
SAMPLE NUMBER | Salt | # | Number of Inspectors | GL
| Sugar | # | Number of Inspectors | GL
| Wheat Flour | # | Number of Inspectors | GL
| Maize Flour | # | Number of Inspectors | GL
| Cooking Oil | # | Number of Inspectors | GL
Total Samples
Vehicle | Industry | Number of Samples (per Quarter) | Frequency | Total (per year) | Who is Testing*
SALT | Netrade Marketing | 10 | 1 x every 4 months .: 3 x per year | 30 | GL |  | *SAZ inspects at factory and market level for industries registered
| ProBrands | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Grain Millers Board | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| National Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
Total Samples |  |  |  | 120 | Nationally per year
OIL | National Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Pure Drop | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| United Refinements Ltd | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
Total Samples |  |  |  | 90 | Nationally per year
90
SUGAR | National Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| ProBrands | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Hulettes | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Country Choice Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GK
Total Samples |  |  |  | 120 | Nationally per year
MAIZE FLOUR | National Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Victoria Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Manyame Milling | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Grain Marketing Board | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
Total Samples |  |  |  | 120 | Nationally per year
WHEAT FLOUR | National Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Victoria Foods | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Manyame Milling | 10 | 1 x every 4 months .: 3 x per year | 30 | GL
| Baker's Inn | 10 | 1x every 4 months .: 3 x per year | 30 | GL
Total Samples |  |  |  | 120 | Nationally per year
PROVINCE | POPULATION | DISTRICT* | SALT | OIL | SUGAR | MAIZE FLOUR | WHEAT FLOUR | WHO is testing | How Often
Bulawayo | 653337 | Bulawayo District | [5 empty] | GL | 3x a year
Matabeleland South | 683893 | Beitbridge | [5 empty] | GL | 3x a year
|  | Bulilima | [5 empty] | GL | 3x a year
|  | Mangwe | [5 empty] | GL | 3x a year
|  | Gwanda | [5 empty] | GL | 3x a year
|  | Insiza | [5 empty] | GL | 3x a year
|  | Matobo | [5 empty] | GL | 3x a year
|  | Umzingwane | [5 empty] | GL | 3x a year
Matabeleland North | 749017 | Binga | [5 empty] | GL | 3x a year
|  | Bubi | [5 empty] | GL | 3x a year
|  | Hwange | [5 empty] | GL | 3x a year
|  | Lupane | [5 empty] | GL | 3x a year
|  | Nkayi | [5 empty] | GL | 3x a year
|  | Tsholotsho | [5 empty] | GL | 3x a year
|  | Umguza | [5 empty] | GL | 3x a year
Mashonaland Central | 1152520 | Bindura | [5 empty] | GL | 3x a year
|  | Guruve | [5 empty] | GL | 3x a year
|  | Mazowe | [5 empty] | GL | 3x a year
|  | Mbire | [5 empty] | GL | 3x a year
|  | Mukumbura | [5 empty] | GL | 3x a year
|  | Muzarabani | [5 empty] | GL | 3x a year
|  | Rushinga | [5 empty] | GL | 3x a year
|  | Shamva | [5 empty] | GL | 3x a year
Mashonaland East | 1344955 | Goromonzi | [5 empty] | GL | 3x a year
|  | Hwedza | [5 empty] | GL | 3x a year
|  | Marondera | [5 empty] | GL | 3x a year
|  | Murehwa | [5 empty] | GL | 3x a year
|  | Mutoko | [5 empty] | GL | 3x a year
|  | Seke | [5 empty] | GL | 3x a year
Masvingo | 1485090 | Bikita | [5 empty] | GL | 3x a year
|  | Chiredzi | [5 empty] | GL | 3x a year
|  | Chivi | [5 empty] | GL | 3x a year
|  | Gutu | [5 empty] | GL | 3x a year
|  | Masvingo | [5 empty] | GL | 3x a year
|  | Mwenezi | [5 empty] | GL | 3x a year
|  | Zaka | [5 empty] | GL | 3x a year
Mashonaland West | 1501656 | Chegutu | [5 empty] | GL | 3x a year
|  | Hurungwe | [5 empty] | GL | 3x a year
|  | Kadoma | [5 empty] | GL | 3x a year
|  | Kariba | [5 empty] | GL | 3x a year
|  | Makonde | [5 empty] | GL | 3x a year
Zvimba
Midlands | 1614941 | Chirumhanzu | [5 empty] | GL | 3x a year
|  | Gokwe North | [5 empty] | GL | 3x a year
|  | Gokwe South | [5 empty] | GL | 3x a year
|  | Gweru | [5 empty] | GL | 3x a year
|  | Kwekwe | [5 empty] | GL | 3x a year
|  | Mberengwa | [5 empty] | GL | 3x a year
|  | Shurugwi | [5 empty] | GL | 3x a year
|  | Zvishavane | [5 empty] | GL | 3x a year
Manicaland | 1752698 | Buhera | [5 empty] | GL | 3x a year
|  | Chimanimani | [5 empty] | GL | 3x a year
|  | Chipinge | [5 empty] | GL | 3x a year
|  | Makoni | [5 empty] | GL | 3x a year
|  | Mutare | [5 empty] | GL | 3x a year
|  | Mutasa | [5 empty] | GL | 3x a year
|  | Nyanga | [5 empty] | GL | 3x a year
Harare | 2123132 | Harare | [5 empty] | GL | 3x a year

## ZIM flow charts
GAPS: | Border level - Port Health Officers are inspecting now but results take too long to come back. Equipment for testing fortificants is needed.
Market level - Most inspectors at the districts claim of lack of resources (test kits, transport, etc) and samples are not sent on time
Household level - lack of consistent sampling due to lack of resources at village level
Overall: There needs to be funding for resources and a better communication system between EH, SAZ, MOIC, and MOH
SOLUTIONS: | Equipment needs at the borders and labs need to be addressed through funding proposal
Increased communication needs to happen between MOH, MOIC, and SAZ (PHC can assist here)
Increased communication between MOH, districts, and GAL (the Monitoring Tool is supposed to help with some of this)
QUICK NOTE ON MONITORING: |  | The Government is hoping that each District Office and Provincial Office will be given a computer through the funding proposal.
They believe this will help with communication between the institutions and want to create a system of on site sampling where
results are recorded and shared in real time, live through the computer system.
Zimbabwe also has several Associations that monitor its members: There is a Baker's Association, a Grain Miller's Association,
and a Groceries Association that are all very active. They work to keep the playing field level and as a monitoring system for each other.
I think we can work with these groups and play off their already existing M&E systems as a further check on the program.
Inspectors
Ministry of Health, Port Health Officer for Environmental Health (EH)
EH Port Health Officer Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected from each of the X border points.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour. Resullts are recorded in appropriate forms.
3. If results are positive (or if importer certificate indicates compliance with standard), products are allowed to enter market. If negative, they are denied entrance.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection), packed into black plastic papers and transported to the GAL with the qualitative results within 24 hours.
Government Analysis Lab (GAL)
1. Samples arrive at GAL once a quarter for quant testing using iChecks. Turn around time is 2 weeks.
2. Importers pay for these tests. How?
3. GAL returns resuls to Port Health Officer within 14 days. Port Health Officer makes decision to allow or deny stock into country.
4. GAL sends data to MoH for Monitoring Tool within 2 weeks.
Border Level Inspections
Inspectors
Ministry of Health, Local Authority Environmental Health Officers
Local Authority EH Officer Responsibilities
1. Every 4 months, composite samples from production line and stock are colleced for each staple food brand from fortifying industries by Local Authorities for the city in which they reside.
3. Random qualitative tests are conducted using BASF test kits or iron-spot tests.
4. Results of the qual test and samples for quant testing are taken to the GAL Lab within 24 hours of collection.
MoH Monitoring Tool
1. MoH adapts the data from GAL into the Monitoring Tool format.
2. MoH shares results quarterly with the Task Force and GAL.
Factory Level Inspections
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every quarter, composite samples for each staple food brand are collected from the X of markets.
2. Random qualitative tests are conducted using BASF test kits, RTKs, and iron-spot tests.
3. Results are recorded in appropriate forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into black plastic papers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at Provincial Health Offices and sent together on behalf of several districts).
MoH Monitoring Tool
1.MoH focal point person inputs data into the Monitoring Tool.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Market Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
MoH Monitoring Tool
1. MoH adapts the data from GAZ into the Monitoring Tool format.
2. MoH shares results biannully with the Fortification Task Force.
Government Analysis Lab (GAL)
1. Samples arrive every 4 months for quantitative testing using iChecks.
2. After a decision regarding compliance or non-compliance is made by the Local Environmental Health Authority, results are sent back to the industry within 2 weeks.
3. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
Standards Association of Zimbabwe (SAZ)
Industry can choose to be SAZ certified
1. Has independent inspectors (less than 40)
2. Has its own logo and certification process
3. Registration with SAZ is not mandatory. Companies apply to use their logo as a marketing tool
4. SAZ inspectors only monitor SAZ registered companies at the factory and occasionally the market level
SAZ Responsibilities:
1. Tests all composite samples submitted to SAZ quantitatively in their own lab every 4 months
2. Shares results with MoIT (parent Ministry)
3. MoIT shares results with MoH for input into monitoring tool
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every 4 months, samples of staple food products are collected from the X of households at the village level.
2. Random qualitative tests are conducted if appropriate.
3. Results are recorded in designated forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into opaque containers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at X and sent together on behalf of several districts). How will tranport happen?
MoH Monitoring Tool
1.MoH focal point person inputs data into the Monitoring Tool.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Household Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks of arrival.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
Inspectors
Ministry of Health, Port Health Officer for Environmental Health (EH)
EH Port Health Officer Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected from each of the X border points.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour. Resullts are recorded in appropriate forms.
3. If results are positive (or if importer certificate indicates compliance with standard), products are allowed to enter market. If negative, they are denied entrance.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection), packed into black plastic papers and transported to the GAL with the qualitative results within 24 hours.
Government Analysis Lab (GAL)
1. Samples arrive at GAL once a quarter for quant testing using iChecks. Turn around time is 2 weeks.
2. Importers pay for these tests. How?
3. GAL returns resuls to Port Health Officer within 14 days. Port Health Officer makes decision to allow or deny stock into country.
4. GAL sends data to MoH for Monitoring Tool within 2 weeks.
Border Level Inspections
Inspectors
Ministry of Health, Local Authority Environmental Health Officers
Local Authority EH Officer Responsibilities
1. Every 4 months, composite samples from production line and stock are colleced for each staple food brand from fortifying industries by Local Authorities for the city in which they reside.
3. Random qualitative tests are conducted using BASF test kits or iron-spot tests.
4. Results of the qual test and samples for quant testing are taken to the GAL Lab within 24 hours of collection.
MoH Monitoring Tool
1. MoH adapts the data from GAL into the DHIS System.
2. MoH shares results quarterly with the Task Force and GAL.
Factory Level Inspections
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every quarter, composite samples for each staple food brand are collected from the X of markets.
2. Random qualitative tests are conducted using BASF test kits, RTKs, and iron-spot tests.
3. Results are recorded in appropriate forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into black plastic papers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at Provincial Health Offices and sent together on behalf of several districts).
MoH Monitoring Tool
1.MoH focal point person inputs data into the DHIS System.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Market Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
MoH Monitoring Tool
1. MoH adapts the data from GAZ into the DHIS System.
2. MoH shares results biannully with the Fortification Task Force.
Government Analysis Lab (GAL)
1. Samples arrive every 4 months for quantitative testing using iChecks.
2. After a decision regarding compliance or non-compliance is made by the Local Environmental Health Authority, results are sent back to the industry within 2 weeks.
3. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every 4 months, samples of staple food products are collected from the X of households at the village level.
2. Random qualitative tests are conducted if appropriate.
3. Results are recorded in designated forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into opaque containers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at X and sent together on behalf of several districts). How will tranport happen?
MoH Monitoring Tool
1.MoH focal point person inputs data into the DHIS System.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Household Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks of arrival.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
Inspectors
Ministry of Health, Port Health Officer for Environmental Health (EH)
EH Port Health Officer Responsibilities
1. Every quarter, composite samples for each staple food brand (oil, sugar, flour, and salt) are collected from each of the X border points.
2. Random qualitative tests are conducted on oil and sugar brand samples using BASF test kits, iodine spot test kits for salt, and iron-spot tests for flour. Resullts are recorded in appropriate forms.
3. If results are positive (or if importer certificate indicates compliance with standard), products are allowed to enter market. If negative, they are denied entrance.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection), packed into black plastic papers and transported to the GAL with the qualitative results within 24 hours.
Government Analysis Lab (GAL)
1. Samples arrive at GAL once a quarter for quant testing using iChecks. Turn around time is 2 weeks.
2. Importers pay for these tests. How?
3. GAL returns resuls to Port Health Officer within 14 days. Port Health Officer makes decision to allow or deny stock into country.
4. GAL sends data to MoH for Monitoring Tool within 2 weeks.
Border Level Inspections
Inspectors
Ministry of Health, Local Authority Environmental Health Officers
Local Authority EH Officer Responsibilities
1. Every 4 months, composite samples from production line and stock are colleced for each staple food brand from fortifying industries by Local Authorities for the city in which they reside.
3. Random qualitative tests are conducted using BASF test kits or iron-spot tests.
4. Results of the qual test and samples for quant testing are taken to the GAL Lab within 24 hours of collection.
MoH Monitoring Tool
1. MoH adapts the data from GAL into the DHIS System.
2. MoH shares results quarterly with the Task Force and GAL.
Factory Level Inspections
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every quarter, composite samples for each staple food brand are collected from the X of markets.
2. Random qualitative tests are conducted using BASF test kits, RTKs, and iron-spot tests.
3. Results are recorded in appropriate forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into black plastic papers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at Provincial Health Offices and sent together on behalf of several districts).
MoH Monitoring Tool
1.MoH focal point person inputs data into the DHIS System.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Market Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
MoH Monitoring Tool
1. MoH adapts the data from GAZ into the DHIS System.
2. MoH shares results biannully with the Fortification Task Force.
Government Analysis Lab (GAL)
1. Samples arrive every 4 months for quantitative testing using iChecks.
2. After a decision regarding compliance or non-compliance is made by the Local Environmental Health Authority, results are sent back to the industry within 2 weeks.
3. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.
Standards Association of Zimbabwe (SAZ)
Industry can choose to be SAZ certified
1. Has independent inspectors (less than 40)
2. Has its own logo and certification process
3. Registration with SAZ is not mandatory. Companies apply to use their logo as a marketing tool
4. SAZ inspectors only monitor SAZ registered companies at the factory and occasionally the market level
SAZ Responsibilities:
1. Tests all composite samples submitted to SAZ quantitatively in their own lab every quarter
2. Shares results with MoIT (parent Ministry) and back to person/industry who submitted the sample
3. MoIT shares results with MoH for input into DHIS System
Inspectors
Ministry of Health, District Environmental Health Officer Technicians
DEHO Technician Responsibilities
1. Every 4 months, samples of staple food products are collected from the X of households at the village level.
2. Random qualitative tests are conducted if appropriate.
3. Results are recorded in designated forms.
4. 100g samples are collected, labeled according to GAL standards (coded by district abbreviation, sample #, brand name, and site of collection) and packed into opaque containers.
5. DEHOs transport samples to GAL via hospital vehicle (where necessary, samples can be gathered at X and sent together on behalf of several districts). How will tranport happen?
MoH Monitoring Tool
1.MoH focal point person inputs data into the DHIS System.
2. MoH produces report within 1 week and distributes back to GAL and DEHOs. What is the purpose of this?
2. Reports are shared with the Task Force quarterly.
Household Level Inspections
Government Analysis Lab (GAZ)
1. Samples are analyzed using iChecks within 2 weeks of arrival.
2. Results are sent to MoH focal point person.
3. Appropriate step are taken based on non-compliance by DEHO. HOW? Do they have authority to pull a product from the market?
4. Results are sent via e-mail or in person by GAL to MoH within 2 weeks.