## General Status Report
Key:
Program Status Report | [6 empty] | Complete
KEY INDICATORS | Liberia | Rwanda | Burundi | Malawi | Zimbabwe | Sierra Leone | In-process
1. Standards drafted | Complete | Complete | Complete | Complete | Complete | Yes | Pending
2. Standards officially adopted | Complete | Complete | Complete | Complete | Complete | Yes
3. Standards circulated and communicated | Complete | Complete | Complete | Complete | Complete | No
4. MN / Fortification Strategy written, adopted, disseminated | In-process | In-process | In-process | Complete | Complete | No
5. Industry assessment complete / scale up begun | Complete | Complete | In-process | Complete | In-process | No
6. Fortification begun | Complete | Complete | Complete | Complete | Complete | No
7. Inspectors trained | In-process | Complete | Complete | Complete | In-process | No
8. Inspections begun | Complete | Pending | Complete | Complete | In-process | No
9. Advocacy measures initiated | Complete | In-process | In-process | Complete | In-process | No
10. Legislation drafted | Complete | Yes | Complete | Complete | Complete | No
11. Legislation passed / fortification is mandatory | In-process | In-process | Complete | Complete | In-process | No
12. Monitoring reports generated and shared | Complete | Pending | In-process | Complete | Pending | No
13. Representative sample of industry tested | Complete | Pending | In-process | Complete | Pending
14. Representative sample of importers tested | In-process | Pending | Pending | In-process | Pending
15. Most industries comply | Complete | Pending | In-process | In-process | Pending
16. Most importers comply | In-process | Pending | Pending | In-process | Pending
17. Non-compliance measures being taken | In-process | Pending | In-process | In-process | Pending
18. Quarterly reports provided to stakeholders | Complete | Pending | In-process | In-process | Pending

## Monitoring Snap Shot
PHC Qualitative Metrics
KEY INDICATORS | [5 empty] | Liberia | Rwanda | Burundi | Malawi | Zimbabwe | Sierra Leone
1. All identified industries producing fortified foods meet the designated national standard | [5 empty] | Yes | No | No | No | No | N/A
2. All identified importers importing fortified foods meet the designated national standard | [5 empty] | No | No | No | No | No | N/A
3. Samples are taken from industry, border, and market on a regular (quarterly) basis | [5 empty] | No | No | No | No | No | N/A
4. Non-compliance measures are taken as relevant for local industry and / or importers | [5 empty] | No | No | No | No | No | N/A
5. Surveillance mechanisms are put in place to ensure at least 80% of the target population is consuming fortified foods | [5 empty] | No | No | No | No | No | N/A
BENCHMARKS REQUIRED TO MEET INDICATORS
| Phase | Data | Status | Comments | Anticipated completion
LIB | Preparing for data collection
|  | Is the sampling plan in place? | Yes | Incorporated into national guidelines
|  | Has a clear data flow chart been decided upon and presented? | Yes | Agreed upon my relevant bodies and incorporated into national guidelines
|  | Have inspector trainings been held? | Yes | MoH inspector training completed as of June 2015 | Port Training Jan 2016
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes | All inspectors have been informed by their respective ministries, however, they are not yet inspecting.
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | Yes
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | Begun by NSL
Data collection
|  | Have all samples been taken? | No | Domestic facilities: yes. Imported: partial with emphasis only on salt | 2016-12-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2016-12-01
|  | Have all qualitative tests been complete? | No |  | 2017-02-01
|  | Have all quantitative tests been complete? | No |  | 2017-02-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2017-04-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2017-04-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2017-04-01
Data results
|  | Do all industry comply? | Yes
|  | Do all importers comply? | No |  | 2016-05-01
|  | Do all market samples comply? | No |  | 2017-05-01
|  | Have all non-complying importers / producers been identified? | No |  | 2017-06-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2017-07-01
|  | Do we understand contraints preventing compliance? | No |  | 2017-07-01
|  | Do all products meet designated logo requirements? | No |  | 2017-07-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2017-09-01
|  | Have surveillance mechanism discussions begun with stakeholders? | Yes |  | 2016-05-01
| Phase | Data | Status | Comments | Anticipated completion
RWA | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes | However, there will likely need to be refresher trainings
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes |  | 2016-07-01
|  | Are all importers and local producers aware of their responsibilities? | No | Local producers, yes; importers, no | 2016-10-01
|  | Have all equipment and reagent needs been identified? | Yes |  | 2016-04-01
|  | Have all equipment and reagent needs been procured? | No |  | 2016-12-01
|  | Have all data forms been harmonized? | No |  | 2016-12-01
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | TBD
Data collection
|  | Have all samples been taken? | No |  | 2017-01-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2017-01-01
|  | Have all qualitative tests been complete? | No |  | 2017-02-01
|  | Have all quantitative tests been complete? | No |  | 2017-02-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2017-04-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2017-04-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2017-04-01
Data results
|  | Do all industry comply? | No |  | 2017-06-01
|  | Do all importers comply? | No |  | 2017-06-01
|  | Do all market samples comply? | No |  | 2017-06-01
|  | Have all non-complying importers / producers been identified? | No |  | 2017-07-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2017-08-01
|  | Do we understand contraints preventing compliance? | No |  | 2017-08-01
|  | Do all products meet designated logo requirements? | No |  | 2017-08-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-12-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2016-12-01
| Phase | Data | Status | Comments | Anticipated completion
BUR | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | No |  | 2017-10-01
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | Begun |  | 2016-06-01
Data collection
|  | Have all samples been taken? | No | Doemstic yes; imported no | 2017-10-01
|  | Have all samples arrived at the appropriate lab on time? | Yes |  | 2016-07-01
|  | Have all qualitative tests been complete? | No |  | 2016-09-01
|  | Have all quantitative tests been complete? | No |  | 2016-09-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2016-12-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2016-10-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2016-12-01
Data results
|  | Do all industry comply? | No |  | 2016-09-01
|  | Do all importers comply? | No |  | 2017-02-01
|  | Do all market samples comply? | No |  | 2017-02-01
|  | Have all non-complying importers / producers been identified? | No |  | 2017-02-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2017-03-01
|  | Do we understand constraints preventing compliance? | No |  | 2017-03-01
|  | Do all products meet designated logo requirements? | No |  | 2017-03-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-12-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2016-12-01
| Phase | Data | Status | Comments | Anticipated completion
MAL | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes | Refresher trainings are needed
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | Yes
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | 2015-09-01
Data collection
|  | Have all samples been taken? | No | Only sugar and salt domestically; no imports | 2016-12-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2016-12-01
|  | Have all qualitative tests been complete? | No |  | 2016-12-01
|  | Have all quantitative tests been complete? | No |  | 2016-12-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2016-12-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2016-12-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2016-12-01
Data results
|  | Do all industry comply? | No |  | 2017-01-01
|  | Do all importers comply? | No |  | 2017-02-01
|  | Do all market samples comply? | No |  | 2017-03-01
|  | Have all non-complying importers / producers been identified? | No |  | 2017-04-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2017-05-01
|  | Do we understand constraints preventing compliance? | No |  | 2017-05-01
|  | Do all products meet designated logo requirements? | No |  | 2017-05-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2016-12-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2016-12-01
| Phase | Data | Status | Comments | Anticipated completion
ZIM | Preparing for data collection
|  | Is the sampling plan in place? | Yes
|  | Has a clear data flow chart been decided upon and presented? | Yes
|  | Have inspector trainings been held? | Yes
|  | Have trainings for major importers and industry been held? | Yes
|  | Are all inspectors aware of their roles? | Yes
|  | Have monitoring responsibilities been clarified? | Yes
|  | Are all importers and local producers aware of their responsibilities? | Yes
|  | Have all equipment and reagent needs been identified? | Yes
|  | Have all equipment and reagent needs been procured? | Yes
|  | Have all data forms been harmonized? | Yes
|  | Have individual responsibilities for data collation and entry been identifed? | Yes
|  | When will sample collection begin? | TBD
Data collection
|  | Have all samples been taken? | No |  | 2016-12-01
|  | Have all samples arrived at the appropriate lab on time? | No |  | 2017-01-01
|  | Have all qualitative tests been complete? | No |  | 2017-02-01
|  | Have all quantitative tests been complete? | No |  | 2017-02-01
|  | Are reports generated on a quarterly basis for all imports? | No |  | 2017-03-01
|  | Are reports generated on a quarterly basis for all industry? | No |  | 2017-03-01
|  | Are reports generated on a quarterly basis for all markets? | No |  | 2017-03-01
Data results
|  | Do all industry comply? | No |  | 2017-05-01
|  | Do all importers comply? | No |  | 2017-07-01
|  | Do all market samples comply? | No |  | 2017-09-01
|  | Have all non-complying importers / producers been identified? | No |  | 2017-08-01
|  | Have all non-complying importers / producers been contacted? | No |  | 2017-08-01
|  | Do we understand constraints preventing compliance? | No |  | 2017-08-01
|  | Do all products meet designated logo requirements? | No |  | 2017-08-01
| Reach | Have surveillance mechanisms been put into place to track coverage? | No |  | 2017-01-01
|  | Have surveillance mechanism discussions begun with stakeholders? | No |  | 2017-01-01