## Surveys_Sept-16
| Mapping |  |  |  |  | Coverage survey |  |  |  |  | Health impact
| Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report
Burundi | 2014-05-01 | Complete | Complete | Complete | 8-Sept-16 (KK/CCA survey) | [10 empty] | Reports in white = when sent to GiveWell
Cote d'Ivoire | Apr-13 and Mar-14 | Complete | Complete | Complete | Sep-15 (baseline mapping) | 2014-02-01 | Complete | Complete | Complete | Oct-14 | 2013-11-01 | Complete | Complete | Complete | (baseline) | Reports in orange = due to send to GiveWell 08-Sep-16
[6 empty] | May-16 | Complete | Complete | Complete | 21-Sep-16 | 2016-03-01 | Complete | Complete | wait for 2nd round of follow-up data | - | Reports in blue = intenal SCI deadlines
DRC | [5 empty] | Sep-16 | In progress | - | - | - | 2014-12-01 | Complete | Complete | Complete | 8-Aug-16 (baseline)
[11 empty] | Nov-15 | Complete | Complete | Awaiting in-country capacity building - Oct-16 | Dec-16 (F1 survey)
Ethiopia | 2014-03-01 | Complete | Complete | Complete | Sep-15 | Jul-15 | Complete | Complete | Complete | 8-Sep-16 | Apr-15; Nov-15; Apr-16 | Complete | Complete | In progress | 8-Sept-16 (baseline)
| 2015-04-01 | Complete | Complete | Complete | 8-Sep-16 | Jul-16 | Complete | In progress | - | - | Nov-15; Apr-16; Nov-16 | Complete | In progress | wait for 3rd round of follow-up data | -
Liberia | 2012; 2013 and 2015 | Complete | Complete | In progress with in-country statisticians | 7-Oct-16 | Sep-16 | In progress | - | - | - | Dec-12 | Complete | Complete | Complete | Oct-14 (baseline)
[11 empty] | Dec-13 | Complete | Complete | Complete | 8-Sept-16 (F1 survey)
Madagascar | 2014-11-01 | Complete | Complete | Complete | Sep-15 | Apr-16 | Complete | Complete | Complete | 8-Sep-16 | Oct-15 | Complete | Complete | Complete | 8-Sept-16 (baseline)
| 2015-06-01 | Complete | Complete | Complete | 8-Aug-16
Malawi | 2012-02-01 | Complete | Complete | Complete | Oct-14 | Nov-12 | Complete | Complete | Complete | Oct-14 | Jun-12 (baseline) & May-14 (F1) | Complete | Complete | Complete | Oct-14 (F1 Survey)
| 2013-06-01 | Complete | Complete | Complete | Oct-14 | Jul-14 | Complete | Complete | Complete | Sep-15 | Mar-15 | Complete | Complete | Complete | Sep-15 (F2 survey)
| 2015-12-01 | Complete | Complete | Complete | 8-Aug-16 (Likoma mapping) | Sep-16 | In progress | - | - | - | Mar-16 | Complete | Complete | Complete | 8-Sept-16 (F3 survey)
Mozambique | [5 empty] | Jul-15 | Complete | Complete | Complete | Sep-15 (2015 LQAS survey) | Nov-12; Aug-13; Sept-14 | - | Complete | Complete | Sep-15 (Garcia-Nunez report)
[6 empty] | Jul-16 | Complete | Complete | Complete | 8-Sept-16 (LQAS survey) | Sept-15 | - | Complete | Awaiting in-country analysis | 2016-10-01
Niger | 2012 and 2013 | Complete | Complete | Complete | 14-Oct-16 | Oct-16 | In progress | - | - | - | Data collected under SCORE programme 2011 (Y1) to 2015 (Y5) |  |  |  | PI on maternity leave, returns Apr-17
Rwanda | 2014-06-01 | Complete | Complete | Complete | 28-Oct-16 (KK/CCA survey)
Tanzania | [5 empty] | Oct-16 | In progress | - | - | - | May-13 | Complete | Complete | Complete | 8-Sept-16 (baseline)
[11 empty] | Jun-16 | Complete | Complete | Awaiting in-country analysis | -
Uganda | Feb-13 & Oct-14 | Complete | Complete | Complete | shared with GiveWell? | Mar-14 | Complete | Complete | Complete | Sep-15 | Nov-13 | Complete | Complete | Complete | Oct-14 (baseline)
| 2016-08-01 | Complete | - | - | - | Feb-16 | - | - | - | - | Sep-15 | Complete | Complete | mid-survey results only | -
Yemen | 2014-05-01 | Complete | Complete | Complete | Oct-14 | Feb-13 | Complete (Grant Thronton) | - | - | Not authorised for sharing
Zambia | 2012-11-01 | Complete | Complete | Complete | - | Jun-15 | copy with FPSU | Complete | Complete | Sep-15 | Aug-13 | Complete | Complete | Complete | Oct-14 (baseline)
[11 empty] | Jan-17 | - | - | - | -
Zanzibar | [5 empty] | Feb-15 | Complete | Complete | Complete | Sep-15
Note on P16: Author: Not complete in time for GW deadline
Note on K18: Author: Presentation only
Note on P21: Author: Not complete in time for GW deadline

## Surveys_Mar-17
| Mapping/Reassessment |  |  |  |  | Coverage survey |  |  |  |  | Health impact
| Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report
Burundi | 2014-05-01 | Complete | Complete | Complete | 01-Jun-17 (KK/CCA survey) | July/Aug-17 | - | - | - | Dec-17 | May-17 | In progress | - | - | - | Reports in white = when sent to GiveWell
Cote d'Ivoire | Apr-13 and Mar-14 | Complete | Complete | Complete | Sep-15 (pre-treat mapping) | 2014-02-01 | Complete | Complete | Complete | Oct-14 | 2013-11-01 | Complete | Complete | Complete | (baseline) | Reports in orange = due to send to GiveWell 01-Jun-17
[6 empty] | May-16 | Complete | Complete | Complete | 01-Jun-17 | 2016-03-01 | Complete | Complete | wait for 2nd round of follow-up data | 01-Jun-17 (F1 survey) | Reports in blue = intenal SCI deadlines
[6 empty] | Nov-17 | In progress | - | - | - | 2016-10-01 | Complete | In progress
[11 empty] | 2017-08-01 | - | - | - | -
DRC | [5 empty] | Jun-17 | In progress | - | - | - | 2014-12-01 | Complete | Complete | Complete | 8-Aug-16 (baseline)
[11 empty] | Nov-15 | Complete | Complete | Awaiting in-country capacity building - Oct-16 | TBC-17 (F1 survey)
[11 empty] | Apr-17 | Complete | - | -
Ethiopia | 2014-03-01 | Complete | Complete | Complete | Sep-15 | Jul-15 | Complete | Complete | Complete | 8-Sep-16 | Apr-15; Nov-15; Apr-16 | Complete | Complete | In progress | 8-Sept-16 (baseline)
| 2015-04-01 | Complete | Complete | Complete | 8-Sep-16 | Jul-16 | Complete | In progress | Complete | 01-Jun-17 | Nov-15; Apr-16; Nov-16 | Complete | In progress | - | TBC-17 (F1 survey)
[6 empty] | Jun-17 | - | - | - | - | Nov-16; Mar-17; Nov-17 | Complete | - | - | -
Liberia | 2012; 2013 and 2015 | Complete | Complete | Complete | 01-Jun-17 | Apr-17 | Complete | - | - | - | Dec-12 | Complete | Complete | Complete | Oct-14 (baseline)
[11 empty] | Dec-13 | Complete | Complete | Complete | 8-Sept-16 (F1 survey)
[11 empty] | Jan-18 | Complete | - | - | -
Madagascar | 2014-11-01 | Complete | Complete | Complete | Sep-15 | Apr-16 | Complete | Complete | Complete | 8-Sep-16 | Oct-15 | Complete | Complete | Complete | 8-Sept-16 (baseline)
| 2015-06-01 | Complete | Complete | Complete | 8-Aug-16 | May-17 | In progress | - | - | Sep-17 | Oct-17 | - | - | - | Dec-17 (F1 survey)
Malawi | 2012-02-01 | Complete | Complete | Complete | Oct-14 | Nov-12 | Complete | Complete | Complete | Oct-14 | Jun-12 (baseline) & May-14 (F1) | Complete | Complete | Complete | Oct-14 (F1 Survey)
| 2013-06-01 | Complete | Complete | Complete | Oct-14 | Jul-14 | Complete | Complete | Complete | Sep-15 | Mar-15 | Complete | Complete | Complete | Sep-15 (F2 survey)
| 2015-12-01 | Complete | Complete | Complete | 8-Aug-16 (Likoma mapping) | Sep-16 | Complete | Complete | Complete | 01-Jun-17 | Mar-16 | Complete | Complete | Complete | 01-Jun-17 (F3 survey)
| 2017-03-01 | Complete | - | - | - | June-17 | In progress | - | - | - | Mar-17 | Complete | - | - | Jul-17 (F4 survey)
Mozambique | 2017-10-01 | In progress | - | - | - | Jul-15 | Complete | Complete | Complete | Sep-15 (2015 LQAS survey) | Nov-12; Aug-13; Sept-14 | - | Complete | Complete | Sep-15 (Garcia-Nunez report)
[6 empty] | Jul-16 | Complete | Complete | Complete | 01-Jun-17 (LQAS survey) | Sept-15 | - | Complete | - | 2016-10-01
[11 empty] | Data collected under SCORE programme 2011 (Y1) to 2015 (Y5) |  |  |  | Jun-17 (draft manuscript)
Niger | 2012 and 2013 | Complete | Complete | Complete | TBC-17 | May-17 | In progress | - | - | Sep-17 | Data collected under SCORE programme 2011 (Y1) to 2015 (Y5) |  |  |  | Jun-17 (draft manuscript)
Rwanda | 2014-06-01 | Complete | Complete | Complete | Jun-17 (KK/CCA survey)
Tanzania | [5 empty] | Jun-17 | In progress | - | - | - | May-13 | Complete | Complete | Complete | 01-Jun-17 (baseline)
[11 empty] | Jun-16 | Complete | Complete | Complete | 01-Jun-17 (baseline)
[11 empty] | Apr-17 | Complete | - | - | -
Uganda | Feb-13 & Oct-14 | Complete | Complete | Complete | shared with GiveWell? | Mar-14 | Complete | Complete | Complete | Sep-15 | Nov-13 | Complete | Complete | Complete | Oct-14 (baseline)
| 2016-08-01 | Complete | Complete | Complete | 01-Jun-17 | Mar-17 | In progress | - | - | - | Sep-15 | Complete | Complete | mid-survey results only | -
| 2017-08-01 | - | - | - | - | [5 empty] | Sep-17 | Complete | - | - | -
Yemen | 2014-05-01 | Complete | Complete | Complete | Oct-14 | Feb-13 | Complete (Grant Thronton) | - | - | Not authorised for sharing | 2010 /12 - 2016 | Complete | Complete | Complete | 01-Jun-17 (baseline/mid/end)
Zambia | 2012-11-01 | Complete | Complete | Complete | - | Jun-15 | copy with FPSU | Complete | Complete | Sep-15 | Aug-13 | Complete | Complete | Complete | Oct-14 (baseline)
Zanzibar | [5 empty] | Feb-15 | Complete | Complete | Complete | Sep-15
Note on G8: Author: MDA was postponed due to elections at end of 2016 which thus had a knock-on effect on the coverage survey
Note on G14: Author: Was delayed due to contract issues
Note on G26: Author: Was postponed from Oct-16 due to change in treatment period
Note on G28: Author: Contract issues delayed 2016 plans for survey
Note on P32: Author: Mid-survey results discussed with country and will write a full report at the end-survey

## Surveys_Jun-17
| Mapping/Reassessment |  |  |  |  | Coverage survey |  |  |  |  | Health impact
| Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report | Date of survey | Protocol | Data entry | Data analysis | Report
Burundi | 2014-05-01 | Complete | Complete | Complete | 01-Jun-17 (KK/CCA survey) | Jan/Feb-18 | - | - | - | - | Nov-17 | Complete | - | - | - | Reports in white = when sent to GiveWell
Cote d'Ivoire | Apr-13 and Mar-14 | Complete | Complete | Complete | Sep-15 (pre-treat mapping) | 2014-02-01 | Complete | Complete | Complete | Oct-14 | 2013-11-01 | Complete | Complete | Complete | (baseline) | Reports in orange = OUSTANDING were due to send to GiveWell 01-Jun-17
[6 empty] | May-16 | Complete | Complete | Complete | 01-Jun-17 | 2016-03-01 | Complete | Complete | wait for 2nd round of follow-up data | 01-Jun-17 (F1 survey) | Reports in pink = sent to GiveWell 01-Jun-17
[6 empty] | Nov-17 | In progress | - | - | - | 2016-10-01 | Complete | In progress |  |  | Reports in blue = intenal SCI deadlines
[11 empty] | 2017-10-01 | - | - | - | -
DRC | [5 empty] | Jun-17 | Complete | - | - | - | 2014-12-01 | Complete | Complete | Complete | 8-Aug-16 (baseline)
[11 empty] | Nov-15 | Complete | Complete | Awaiting in-country capacity building - Oct-16 | TBC-17 (F1 survey)
[11 empty] | Apr-17 | Complete | In progress | To be analysed with Nov-15 data
Ethiopia | 2014-03-01 | Complete | Complete | Complete | Sep-15 | Jul-15 | Complete | Complete | Complete | 8-Sep-16 | Apr-15; Nov-15; Apr-16 | Complete | Complete | In progress | 8-Sept-16 (baseline)
| 2015-04-01 | Complete | Complete | Complete | 8-Sep-16 | Jul-16 | Complete | In progress | Complete | 01-Jun-17 | Nov-15; Apr-16; Nov-16 | Complete | In progress | - | TBC-17 (F1 survey)
[6 empty] | Jun-17 | In progress (WHO sampling) | - | - | - | Nov-16; Mar-17; Nov-17 | Complete | - | - | -
Liberia | 2012; 2013 and 2015 | Complete | Complete | Complete | 01-Jun-17 | Jun-17 | Complete | - | - | TBC-17 | Dec-12 | Complete | Complete | Complete | Oct-14 (baseline)
[11 empty] | Dec-13 | Complete | Complete | Complete | 8-Sept-16 (F1 survey)
[11 empty] | Jan-18 | Complete | - | - | -
Madagascar | 2014-11-01 | Complete | Complete | Complete | Sep-15 | Apr-16 | Complete | Complete | Complete | 8-Sep-16 | Oct-15 | Complete | Complete | Complete | 8-Sept-16 (baseline)
| 2015-06-01 | Complete | Complete | Complete | 8-Aug-16 | Jun-17 | Complete | - | - | Sep-17 | Oct-17 | - | - | - | Dec-17 (F1 survey)
Malawi | 2012-02-01 | Complete | Complete | Complete | Oct-14 | Nov-12 | Complete | Complete | Complete | Oct-14 | Jun-12 (baseline) & May-14 (F1) | Complete | Complete | Complete | Oct-14 (F1 Survey)
| 2013-06-01 | Complete | Complete | Complete | Oct-14 | Jul-14 | Complete | Complete | Complete | Sep-15 | Mar-15 | Complete | Complete | Complete | Sep-15 (F2 survey)
| 2015-12-01 | Complete | Complete | Complete | 8-Aug-16 (Likoma mapping) | Sep-16 | Complete | Complete | Complete | 01-Jun-17 | Mar-16 | Complete | Complete | Complete | 01-Jun-17 (F3 survey)
| 2017-03-01 | Complete | Ongoing | - | TBC-17 | June-17 | In progress | - | - | - | Mar-17 | Complete | In progress | - | Jul-17 (F4 survey)
Mozambique | 2017-10-01 | In progress | - | - | - | Jul-15 | Complete | Complete | Complete | Sep-15 (2015 LQAS survey) | Nov-12; Aug-13; Sept-14 | - | Complete | Complete | Sep-15 (Garcia-Nunez report)
[6 empty] | Jul-16 | Complete | Complete | Complete | 01-Jun-17 (LQAS survey) | Sept-15 | - | Complete | - | 2016-10-01
[11 empty] | Data collected under SCORE programme 2011 (Y1) to 2015 (Y5) |  |  |  | Jun-17 (draft manuscript)
Niger | 2012 and 2013 | Complete | Complete | Complete | TBC-17 | Jun-17 | Complete | - | - | Oct-17 | Data collected under SCORE programme 2011 (Y1) to 2015 (Y5) |  |  |  | Jun-17 (draft manuscript)
Rwanda | 2014-06-01 | Complete | Complete | Complete | Jul-17 (KK/CCA survey)
Tanzania | [5 empty] | Jun-17 | Complete (WHO sampling) | - | - | - | May-13 | Complete | Complete | Complete | 01-Jun-17 (baseline)
[11 empty] | Jun-16 | Complete | Complete | Complete | 01-Jun-17 (baseline)
[11 empty] | May-17 | Complete | - | - | -
Uganda | Feb-13 & Oct-14 | Complete | Complete | Complete | shared with GiveWell? | Mar-14 | Complete | Complete | Complete | Sep-15 | Nov-13 | Complete | Complete | Complete | Oct-14 (baseline)
| 2016-08-01 | Complete | Complete | Complete | 01-Jun-17 | Jun-17 | In progress (WHO sampling) | - | - | - | Sep-15 | Complete | Complete | mid-survey results only | -
| 2017-08-01 | - | - | - | - | [5 empty] | Sep-17 | Complete | - | - | -
Yemen | 2014-05-01 | Complete | Complete | Complete | Oct-14 | Feb-13 | Complete (Grant Thronton) | - | - | Not authorised for sharing | 2010 /12 - 2016 | Complete | Complete | Complete | 01-Jun-17 (baseline/mid/end)
Zambia | 2012-11-01 | Complete | Complete | Complete | - | Jun-15 | copy with FPSU | Complete | Complete | Sep-15 | Aug-13 | Complete | Complete | Complete | Oct-14 (baseline)
Zanzibar | [5 empty] | Feb-15 | Complete | Complete | Complete | Sep-15
Note on G3: MDA delayed from June to Dec as WHO PZQ donation not incountry in time. MDAs occur either during June Child Health Week or Dec Child Health Week
Note on L3: MDA delayed from June to Dec as WHO PZQ donation not incountry in time. MDAs occur either during June Child Health Week or Dec Child Health Week
Note on K5: Coverage Survey (May 2016) - SCI PM had concerns about team in Aboisso in terms of quality of data collection as one member of this team was not adhering to the survey protocol - Data was entered in country and some of the data sent to SCI were missing due to the fact that they were not collected properly by the Aboisso team - Aboisso district (randonly) selected had many camps and not villages to be surveyed and some camps only had a few households which was reported by the team. Again no supervision on field during that time.
Note on P5: Impact Survey (Feb and Oct2016) - Data entered in country and sent after several months delay - October data to be sent by w/c 5-Jun-17 so analysis of both survey can be finalised
Note on K12: Author: - Data analysis complete except for inclusion of reported coverage data. - Recommendations Report in near final draft.
Note on G18: Author: Delayed due to funds/contracts delays
Note on G26: Was postponed from Oct-16 due to change in treatment period Delyaed from May to Jun for contract delays
Note on G28: Author: Contract issues delayed 2016 plans for survey
Note on P28: SCI were only permitted to analyse data in-country and sites have never been revisted. No report was written on these results by Program Manager
Note on P29: MoH written report with FF comments, but havent received feedback since Dec-16 despite frequent contact.
Note on G32: MoH dictated delays due to competing priorities
Note on P32: Author: Mid-survey results discussed with country and will write a full report at the end-survey