## BVA
SCI Budget vs Actuals period 1 April 2015-31 March 2016 (all figures in GBP)
|  |  | Original Budget on 13 Aug. 2015 | Revised Budget (figures in the contract with the countries) |  |  | Actual expenditure from 1 April 2015 to 31 March 2016 |  |  |  | Notes
|  |  |  | Restricted | Unrestricted | Total | Restricted (DFID, END Fund, Score, Gates, CIFF) | Unrestricted |  | Total
[8 empty] | ICT | IC
| Total Central Expenditure |  | 1826215.3392 |  |  | 1826215.3392 | 787023.54 | 308486.95 | 189208.81 | 1284719.3 | Central programme costs include programme management, travel, monitoring &evaluation, payments to partners, and overhead costs. Previous figure Including 303K to LSTM related to Mozambique rolled from previous fiscal year.
Country Programmes Expenditure
|  | Burundi | 198414 |  |  | 0 | 4762.88 | 35179.82 | 18195.91 | 58138.61 | No implementation costs; only consultancies and travel
|  | Cote d'Ivoire | 172042 | 74199 | 94034 | 168233 | 48284.63 | 0 | 87042.04 | 135326.67 | Not all contract value was transferred; the balance to be rolled to next year budget
|  | Democratic Republic of the Congo | 375000 | 164657.7993 | 208993.1985 | 373650.9978 | 104025.97 | 0 | 124140.14 | 228166.11 | Not all contract value was transferred; the balance to be rolled to next year budget
|  | Ethiopia | 1805512 | 437169.2339 | 1136987 | 1574156.2339 | 511303.07 | 0 | 1410357.87 | 1921660.94 | Transfers were made in April 2015 relating to last year's contracts; including in-country costs and salaries not only implementation costs
|  | Liberia | 67273 | 127490 | 45616 | 173106 | 0 | 0 | 0 | 0 | Contract not signed yet; activities in Liberia delayed until April because of delay in contract & drugs availability in the country; budget will be rolled over; 45,616 is already in the country from 2013.
|  | Madagascar | 318011 |  | 490461 | 490461 | 0 | 54112.81 | 313414.23 | 367527.04
|  | Malawi | 591229 | 141602 | 449628 | 591230 | 476458.94 | 56422 | 0 | 532880.94 | Errors in book-keeping to be corrected; costs are booked as DFID while they are covered from unrestricted
|  | Mauritania | 0 | 0 | 43534 | 43534 | 0 | 0 | 43533.53 | 43533.53
|  | Mozambique | 743094 | 210294 | 267876 | 478170 | 380113.76 | 0 | 0 | 380113.76 | Transfer to LSTM in March didn't show on the accounts until April; will be rolled into next year budget; the costs include research costs and consultant costs
|  | Niger | 199060 | 193606 | 0 | 193606 | 362358.74 | 0 | 1094.44 | 363453.18
|  | Nigeria | 0 | 0 | 0 | 0 | 0 | 0 | 1079.11 | 1079.11
|  | Rwanda | 403189 | 188383 | 0 | 188383 | 0 | 250528.8 | 11303 | 261831.8
|  | Senegal | 0 | 0 | 0 | 0 | 0 | 0 | 8894.98 | 8894.98
|  | Sudan | 200000 | 0 | 0 | 0 | 0 | 0 | 1169.77 | 1169.77 | Money transferred Last fiscal year
|  | Tanzania | 751995 | 345018 | 406696 | 751714 | 480010.08 | 0 | 428912.59 | 908922.67 | In country bank account; expenses recorded relating to last year contract.
|  | Uganda | 186077 | 54576 | 131501 | 186077 | 250947.15 | 0 | 117005 | 367952.15 | In country bank account; expenses recorded relating to last year contract; expenses include costs of PHD student and research costs
|  | Yemen | 53264 | 246285.9669 | 0 | 246285.9669 | 229494.97 | 0 | 10299.11 | 239794.08 | Including Salary of program manager based in Egypt
|  | Zambia | 458000 | 117798 | 105653 | 223451 |  |  | 0 | 0 | Transfer to LSTM in March didn't show on the accounts until April; will be rolled into next year budget
|  | Zanzibar | 430907 | 99314 | 331393 | 430707 | 99731.21 |  | 331392.5 | 431123.71
| Total Country Programmes Expenditure |  | 6953067 | 2400393.0001 | 3712372.1985 | 6112765.1986 | 2947491.4 | 396243.43 | 2907834.22 | 6251569.05
| Total Expenditure |  | 8779282.3392 | 2400393.0001 | 3712372.1985 | 7938980.5378 | 3734514.94 | 704730.38 | 3097043.03 | 7536288.35
| Note: | The budget is only the implementation budget and doesn't include research costs and rolled budgets from previous years.
Note on E9: No contract is signed yet with Burundi
Note on E10: contract with MAP
Note on E11: contract with UFAR
Note on E13: End Fund & DFID
Note on E25: new agreement with End Fund