Department for International Development Tanzania

Project Completion Review of DFID's support for ApproTEC’s Micro Irrigation Promotion Project (MIPP)

PROJECT COMPLETION REVIEW OF DFID'S SUPPORT TO THE MICRO IRRIGATION PROMOTION PROJECT (MIPP)

## A report for the Department for International Development - Tanzania

## December 2003

Leon Tomesen

The views expressed in this report are those of the consultant alone and do not

necessarily reflect those of DFID

The Springfield Centre for Business in Development

Mountjoy Research Centre

Durham

DH1 3UZ

UK

Tel: +44 191 3831212

Fax: +44 191 3831616

E-mail: global@springfieldcentre.com

# TABLE OF CONTENTS

### EXECUTIVE SUMMARY

- INTRODUCTION									  1

- REVIEW OF OUTPUTS								  1

- PURPOSE AND GOAL								  6

  - Purpose										  6

  - Goal											  7

  - Purpose to goal									9

- SUSTAINABILITY									10

  - Approach and achievements							10

  - Findings										11

  - Challenges										12

- KEY LESSONS LEARNED								16

  - Project level lessons									16

  - Sector level lessons									16

  - General development lessons							18

  - Other issues										18

- RECOMMENDATIONS								19

ANNEXES

- DFID Project Progress Report

- Terms of Reference

- Wholesalers and dealers

- Executive Summary of Second Follow-up Survey Report

- Summary Report of Commercial Study

- ApproTEC Tanzania’s Approach to Market Development

EXECUTIVE SUMMARY

# OUTPUTS

- At the output level, the project has generally performed very well. A number of quantitative targets as defined in the logframe have been surpassed:

  - Twice as many retailers as targeted are now selling the pump (78 against 35);

  - Twice as many wholesalers as targeted distribute the pumps (8 instead of 4);

  - One manufacturer is profitably producing and distributing the pump;

  - The manufacturer has build a good track record with a financial institution;

  - The manufacturer supplies inventory credit to the wholesalers;

  - About 90% of the retailers receive a 30 day supplier credit from wholesalers;

  - An adequate system for measuring economic impact has been developed;

  - Livelihood security indicators have been identified and integrated into the monitoring system;

  - ApproTEC has systematised its approach to market development in Tanzania.

- However, in some areas the project has not achieved its targets fully, or there are areas of concern:

  - No additional new irrigation technology has been successfully introduced;

  - The results of the different monitoring surveys have to be treated with caution since the sample size and geographical coverage were limited.  ApproTEC’s monitoring system covers the whole country but second year impact surveys remained to be carried out in the south

  - The lessons learned on the market development approach have not yet been shared with donors, government and NGOs (planned for March 2004)

# PURPOSE AND GOAL

- ApproTEC is likely to surpass the target of selling 8,000 pumps in Tanzania and to have 85% of these in active use by farmers;

- There are very few technical problems with the pumps (less than 1% of end-users reported flaws);

- ApproTEC has provided facilitation and incentives to the manufacturer, wholesalers, retailers and end-users that have made them aware of the benefits a well functioning market mechanism offers them. It is highly unlikely that without the project support the market would have developed in the manner it now has.

- Notwithstanding the very positive achievements with respect to the purpose level indicators, there are more complicated issues associated with the development of a “sustainable mass market”. ApproTEC has chosen to work with a single, highly capable manufacturer and a high proportion of sales are through a single wholesaler.   This is a strategy that maximises efficiency, but may leave the product vulnerable to the changing priorities of the manufacturer and the largest wholesaler.

- The rationale for subsidising the development of an irrigation technology is generally justifiable. It will be interesting to see if this leads in the long run to a more entrepreneurial and self-reliant “supply-side” in the pump industry.

- At the goal level, evidence suggests that the increase of the area under irrigated cropping has not increased significantly (only by about 20%);

- Survey results show that the family/household income of farmers has dramatically increased (on average by 367% or an increase in net profit per household of Tzs. 777,012 per annum);

- While most pump owners are men, there has been a notable increase (54%) in the number of women that manage the pumps. Only a small percentage (9%) of women felt more financially independent as a result of this but they do report a notable reduction in time spent in the field.

SUSTAINABILITY

- ApproTEC/MIPP has facilitated the development of the market by reducing the perceived levels of risk for the manufacturer, the wholesalers and the retailers. This has implied a temporary distortion of the pricing structure. It has yet to be seen if without the comfort of risk reduction by the project the market will eventually operate in a fully sustainable manner. Evidence from the last six months in which ApproTEC has withdrawn from the market chain suggests that it will.

- The technology transfer process has been partly subsidised by the project, but all direct costs and capital investment in new production (and some training investments) has been contributed by the selected manufacturer. However, it will be useful to measure the extent to which the manufacturer will invest in further product development or whether wholesalers and retailers will invest in promotion, extension, and after sales services after the project finishes.

- Formal sector financial services are now available to the manufacturer, who passes on 60 days supplier credit to wholesalers.  More than 90% of retailers receive 30 days wholesaler credit and about half of all retailers provide informal credit to some of their customers.  It is probable that the manufacturer and wholesaler  end of the chain will continue to receive credit for the long term, but it remains unclear how this will play out at the retailer and customer levels.  The analysis of the PCR indicates a basic truth: “making markets work for the poor” with respect to irrigation technologies and the many services contained within this sub-sector requires also that financial services work effectively.

- ApproTEC’s wish for improved competition is laudable.  It is, then, unfortunate that the time available did not allow them to encourage more competition locally. Sustainable supplies of irrigation technology requires a competitive industry but this was not a priority in ApproTEC’s intervention approach, because building the market to a scale that justified a second manufacturer took all of the time allotted; emphasis rather (and very successfully) has been given to delivery.

### KEY LESSONS LEARNED

- Good operational, financial and administrative systems have been put in place, including measurable benchmarks for staff and partner performance. Such rigorous supervision is essential to ensure good project performance.

- For the measurement of national economic and social impact of the introduction of this irrigation technology appropriate resources need to be allocated to monitoring and evaluation.

- Development agency interventions should focus on addressing the underlying systemic causes of poverty – and in particular, of why markets are not working effectively for the poor. This should be their core focus. The essential logic and analytical framework for the pump sub-sector in Tanzania is the same as that which should be used for other private sector interventions. “The problem” is not over the benefits of irrigation technology for users; it is why the market system is not developing and delivering such technologies!

- While there is a case for public investment in basic R & D, care must be taken that this stimulates rather than displaces innovation among private sector companies. The state’s role in R & D should defray risk – but it shouldn’t remove it.

- There appear to be opportunities for wider impact through low-cost, mass market technologies. External support, in the form of facilitation and temporary incentives, can be crucial to change the mind-set of mostly traditionally operating companies to allow them to exploit these opportunities. However, these cannot be considered in isolation from the wider market system of which they are a part.

- Assessing “final” impacts in economic development is difficult and expensive but rigorous approaches can be used to give a detailed insight into change. Suitable provision must be made in project budgets to allow this to take place. However, assessing market level change - the means to final ends – is also a critical measurement challenge.

- Globalisation and free market mechanisms necessitate thinking beyond national boundaries. This reality applies to manufacturers and wholesalers of low-cost technologies and to development agencies.

RECOMMENDATIONS

- The PCR makes the following recommendations:

- To systematise the experiences and lessons learned and disseminate these through a national workshop in Tanzania and through publication in an international development journal;

- To roll over any budget left to a budget-neutral extension of maximum two months;

- To utilise the above lessons learned in debates over market development intervention approaches, the cost-benefit ratio, contribution to poverty alleviation and the need for an appropriate balance between project aid and budget support;

- To undertake a post project evaluation of how private sector market mechanisms have developed after project completion.

- INTRODUCTION

In October 2003, the Department for International Development (DFID) Tanzania commissioned the Springfield Centre for Business in Development to  undertake a Project Completion Review (PCR) of the DFID funded Micro-Irrigation Promotion Project (MIPP). The purpose of this project is ‘to improve access by small-scale farmers to manually operated water-pump technologies on a sustainable basis’’. It was assumed that the successful implementation of this would contribute to the realisation of the project goal which is ‘to reduce the incidence of poverty through sustainable and substantial improvements in the incomes and livelihoods of small-scale farmers’.

The project is implemented by ApproTEC Tanzania, an offspring of ApproTEC Kenya, an NGO that has been promoting the design, development, local manufacture and marketing of low cost technologies to promote enterprise development and income and employment generation for the last thirteen years.

Full terms of reference for this review are presented in Annex 2, but in brief the four main objectives of this review were to:

- Assess the extent to which the project outputs and purpose have been achieved;

- Assess the extent to which project achievements are likely to contribute to the goal of the project, ie the extent to which the incomes and livelihoods of small scale farmers have been or are likely to improve as a result of project action;

- Assess the extent to which the achievements of the project are sustainable;

- Provide lessons learnt from the project with respect to

- Project/Programme Level Lessons

ii)	Sector Level or Thematic Lessons, and

iii)	General Development Lessons.

In preparing this report, background documents, strategy papers, progress reports, and procedural documents were reviewed, meetings were held with project staff and various stakeholders in the distribution chain (the manufacturer, wholesalers, retailers and end-users).

- REVIEW OF OUTPUTS

Output 1:	At least two types of manually operated irrigation pumps available

in the marketplace without continuing project support

  - 35 retailers sell the pump with no project support (progress rating: 1)

At the time of the PCR, 78 retailers were selling the pump all over the country. Some of these retailers are very small outlets in remote areas. It is unlikely that after withdrawal of ApproTEC support this number will remain at this high level.

  - At least 4 wholesalers distribute the pump to at least 30 retailers using their own networks and capital (progress rating: 1)

There are 8 wholesalers, at least one in every zone of the country. Three of these belong to the Mukpar group, so one may argue that there are six wholesale companies involved in pump sales. All these wholesalers now operate without ApproTEC/MIPP support and have built their own network with the manufacturer and the retailers.

  - At least one manufacturer is profitably producing the irrigation pumps and distributing them to wholesalers, retailers and private customers (progress rating: 1)

There is one manufacturer (KARAM Industries) producing one irrigation pump and distributing them, without ApproTEC support. Attempts to introduce a second (hand) pump have not been successful so far. The manufacturer only sells to wholesalers, who sell to retailers, who in turn sell to end-users. This is a system based on existing transaction practices in Tanzania and elsewhere, where manufacturers usually sell exclusively to a network of wholesalers, who in turn sell to their individual networks of retailers. MIPP has addressed that various imperfections in the whole manufacturing-marketing-distribution-servicing chain, leaving behind a better functioning system in the private sector.

Apart from selling pumps in Tanzania, the manufacturer also exports pumps to Malawi, Mozambique and Haiti. Most of these contacts with foreign importers have been facilitated by ApproTEC. However there is evidence that both the manufacturer and some of the bigger wholesalers are, by themselves, trying to explore these and other export markets.

The manufacturer is making a net post-tax profit of Tzs. 34.4 million. The return on capital employed is 19%, while the return on equity is 22%. These figures compare very favourably to the return on investment and equity of other manufactured products in the engineering industry in Tanzania. It is probably for this reason that there are signs that one of the wholesalers is considering setting up its own manufacturing facility. This is an interesting indication that the market now recognises the importance of the technology and starts to act on its own in a healthy competitive environment.

At the time of the PCR the manufacturer had increased his production capacity to 750 pumps per month, although actual production is at 500 pumps per month.

  - New irrigation technology with mass market potential identified and market tested (progress rating: 3)

Experiments have been carried out with two new irrigation technologies (the Money Maker Plus and the Hand Pump). After market testing these technologies had to be withdrawn from the market due to lack of market potential and design flaws. The Hand Pump is presently being further developed and tested by ApproTEC. These developments are in an advanced stage and it is likely that the newly developed hand pump will be market tested within a few months.

## Output 2:	Financial services are available, tailored to the needs of at least 3

wholesalers to support inventory and to at least 40% of retailers

  - National Microfinance Bank supplies fixed asset credit to the designated manufacturer (progress rating: 2)

The designated manufacturer has received a US$ 10,000 loan from the National Microfinance Bank, for the purchase of a truck. This loan is being repaid promptly by the manufacturer (will be fully repaid by April 2004). The manufacturer is thus building-up a track record with a financial institution. In addition the manufacturer has received a US$ 20,000 working capital finance from IFC, guaranteed by ApproTEC at an interest rate of 25% per annum on a declining basis. This loan will be taken over by NMB when the loan for the truck has been repaid.

  - Inventory credit supplied by manufacturer to wholesalers (progress rating: 1)

The manufacturer now provides 60 days supplier credit to wholesalers without any project support. Amounts are based on pre-set credit limits depending on capacity, history, etc. The credit portfolio of the manufacturer is well managed and of good quality compared to standards of financial institutions in Tanzania. The question is whether or not this quality can be maintained without the follow-up support of MIPP staff.

  - At least 15 retailers continue to receive 30 day supplier credit after project support is withdrawn (progress rating: 1)

About 90% of the present 78 retailers receive a 30 days supplier credit from the wholesalers without any project support. However, without the MIPP guarantee, it is likely that wholesalers will increasingly demand cash payment for the pumps.

## Output 3:	Economic, social and business impact monitoring system

provides credible impact information and reliable insight

into business investment criteria

Within the possibilities and constraints of the project, MIPP has done a remarkably sound job in collecting and analysing economic and business impact data that appear both credible and reliable. The more complicated measurement of social impact at the national level requires more resources than are available in the MIPP project.

  - Economic impact measurement system accurately reports on income changes directly related to the use of irrigation technologies and indirectly arising out of new investments made with profits from irrigation activities (progress rating: 2)

MIPP has developed an economic impact measurement system that provides detailed information on:

- income changes at the farm household level directly related to the use of irrigation technologies;

- income changes at the farm level indirectly arising out of new investments made with profits from irrigation activities;

- economic impact of project activities on the manufacturer, the wholesalers and the retailers.

- The system has been qualified by the Harvard Institute for International Development as a groundbreaking way of measuring economic impact.  The PCR finds that MIPP has been very prudent in their claims with respect to impact and that the results of the surveys may be very indicative for national impact. However, the PCR finds that:

- The problem of attribution of economic impact could have been more adequately tackled. Especially in the absence of a control group it remains questionnable to what extent economic impact can be wholly and solely attributed to MIPP interventions;

- The economic impact measurement system are really indicators of delivery. It does not measure the degree to which ApproTEC’s interventions have facilitated a more competitive, innovative and sustainable pump supply industry.

ApproTEC/MIPP has devoped a ‘Bang for the Buck’ system for measuing return on (donor) investment. The formula used for this indicator is:

New profits generated by entrepreneurs + new wages paid to employees

## Donor’s intervention costs

This indicator has been endorsed by the Harvard School of Business. The PCR finds that the manner in which new profits generated are measured may not be 100% acurate, but it is certainly credible. New wages paid to employees do not include the opportunity costs of family farm labour, since it is argued that these workers would otherwise be idle anyway. Donor’s intervention costs include total project costs, including TA, R&D and institution building costs without discounting.The project’s current estimate of net direct financial benefit per pump is $1,904 over a 3-year pump life ($350+777+777) per pump user. These are actual figures based on their impact studies amongst more than 130 farmers, studied over a two-year period. MIPP's impact, then, can be equated to $17,132,192. While one can of course debate the precise figures or the accuracy of cost-benefit analysis, there is no doubt that the project has caused profits and wages (value added) to rise considerably through the increased use of irrigation technologies. The more contentious issues on project impact relate to its impact on the market for water pumps.

  - Livelihood Security indicators identified and integrated into monitoring system (progress rating: 2)

MIPP is using a system to measure livelihood security indicators and have integrated this into its monitoring system. The tool used for follow-up surveys on livelihood security indicators comprises of the following major sections:

- Pump-user bio data

- Farm size, layout with irrigated and potential area for irrigation activities

- Household level impacts, including sources of income for household expenditure

- Pump use specifications

- Enterprise level impact, which measures net income from irrigated crops, and labour allocation

- Individual level impact, comprising social capital

- Marketing information for the irrigated crops

- Other information in relation to future expectations of the client.

The PCR is impressed with the manner in which MIPP measures impact on livelihood security indicators. However, as observed in the OPR, the system could have been less elaborate and still would have served DFID's purposes.

  - 2 impact surveys available for assessment of national impact, with one long-term follow-up (progress rating: 1)

The project has conducted a base-line survey of a sample of 64 farmers (called Zero Age Survey) in two regions in the Lake Zone (Mwanza and Mara) and three regions in the Northern Zone (Arusha, Kilimanjaro and Tanga) two months after pump purchase (i.e. from June to September 2001). This was followed-up by a First Follow-up Survey of the same sample after 9 months in April/May 2002. In May/June 2003 (one year after the first follow-up survey).  Base-lines were also conducted in the central Zone (Dar, Morogoro and Dodoma) and the south west (Iringa and Mbeya) and Follow-up impact surveys 9 months later.  This covered an additional 67 farmers.  a Second Follow-up Impact Survey has been conducted, again with the sample of 64 farmers in the northern zones, while second impact follow-up surveys remain to be completed in the south. All three second follow-up surveys took place in the same geographical areas.The data emerging from these surveys have to be treated with some caution for two reasons: (i) the geographical coverage was not national; and (ii) the sample constitutes less than one percent of pump users.

However, these surveys provide a wealth of information on economic and social impact at the farmers' level and may be highly indicative for national impact. The PCR is of the opinion that MIPP could not have possibly carried out scientifically fully up to standard surveys within its resource constraints.

A summary of the Second Follow-up Survey Report is presented in annex 4.

## Output 4:	General strategies articulated for market development approaches

in Tanzania, related to technology and service dissemination

4.1	Results shared with broad coalition of donors, Government and NGOs (progress rating: 2)

Approaches, lessons learned and best practices in this type of technology and market development activities have to a large extent been systematised and articulated. This process will be completed before the project ends. MIPP has made commendable efforts to systematise their experiences and lessons learned. ApproTEC is really in a transitional phase to translate the experiences and lessons learned in MIPP and elsewhere in an innovative and contemporary approach to technology and market development.

So far, not much effort has been put into sharing results. It is understandable that MIPP has been cautious not to share results before they could be substantiated. Towards the end of 2003 or in the beginning of 2004 a workshop will be held to share experiences with a broad coalition of private sector representatives, donors, NGOs and Government Officials.

Overall progress assessment at the output level: 1 (Likely to be completely achieved).

- The quantitative targets for the number of pumps manufactured by a local producer and the distribution network of wholesalers and retailers and end-users involved have been substantially surpassed. New irrigation technologies with mass market potential have been identified, but did not prove to be successful in reality.

- A system of financial service provision for the manufacturer, wholesalers and retailers has been established and is likely to continue to function without project support.

- A system for monitoring economic, social and business impact has been established and is exemplary within the constraints of the available resources.

- Important lessons have been learned about feasible market development strategies related to technology and service dissemination. The systematisation of these lessons is nearly complete and will be disseminated among private sector stakeholders, donors, the Government of Tanzania and NGOs.

- PURPOSE AND GOAL

  - Purpose

The project’s purpose is: To develop sustainable mass markets for manually operated water pump technology suitable for use by small-scale farmers

- 8,000 manually operated pumps sold in Tanzania, with 85% in active use by first-time users, by the end of project (progress rating: 1)

Till September 2003 a total of 7,345 pumps have been sold in Tanzania. Nearly all of these are first time users of irrigation technology. A total of 8,955 pumps have been sold if exports are included. Based on projections from previous years and quarters, the target of 8,000 pumps sold in Tanzania will easily be achieved. A net figure of 8,350 pumps sold in Tanzania at project completion is a realistic estimate.

Close to 100% of the pumps sold in Tanzania are in active use. The surveys suggest that 94% of the pumps work well. Less than 1% of the responding farmers reported a few mechanical problems such as losing prime and failing to push water properly. Different measures have been undertaken to solve these problems. Two pumps were returned and maintained at their dealer shops and another two have been replaced by the manufacturer under the one year guarantee scheme.

- At least one new water pumping technology suitable for mass manufacture and marketing identified and market-tested (progress rating: 3)

MIPP has attempted to adapt the design of a very low cost hand pump from ApproTEC Kenya. This technology has been market tested and proven to show design flaws. This technology has, for the time being, been declared unfit for mass manufacturing and marketing. There is evidence that the design flaws may be addressed in the near future and that this technology may still have a potential for mass marketing.

Overall progress assessment at the purpose level: 2 (Likely to be largely achieved).

The progress made to achieve the project purpose is excellent. The project is an innovative example of a possible approach how to develop sustainable mass markets for a technology that substantially increases income of small-scale farmers, improves their livelihoods, makes a local manufacturer more competitive and establishes a well functioning manufacturing, marketing and distribution chain for irrigation pumps in Tanzania.

ApproTEC/MIPP has provided facilitation and incentives to the manufacturer, wholesalers, retailers and end-users that have made them aware of the benefits that a well functioning market mechanism offers them. It is highly unlikely that without the project support the market would have developed in the manner it now has. Notwithstanding the very positive achievements with respect to the purpose level indicators, there are more complicated issues associated with the development of a “sustainable mass market” that are not really identified by the given indicators. We discuss these below (in section 4) in more depth. However, one can certainly question the sustainability of a market in which one manufacturer has been given prominence (what appears to be a monopoly); a high proportion of sales are through one wholesaler; and technical innovation – essential in any market environment - has been undertaken primarily by the project.  ApproTEC argues that the manufacturer is highly capable and that starting up a second manufacturer at current rates of demand would have been premature and would, potentially, have de-motivated the existing producer.

  - Goal

The project’s goal is: To reduce the incidence of poverty in Tanzania through sustainable and substantial improvements in incomes and livelihoods of small-scale farmers

Figures quoted in this section are based on surveys of a sample of 65 farmers and other end-users undertaken in May/June 2003 in the Mwanza and Northeast Zones of Tanzania. As observed before, the PCR is confident that these figures are surely indicative for national impact.

  - 50% of farmers using micro-irrigation pumps increase the area under irrigated cropping by at least 100% within 1 year following acquisition of a pump (progress rating:4)

The irrigated land has, on average, increased only by 20% (from 0.96 acres to 1.15 acres) over a two year period after pump purchase. However, productivity of land under irrigation has increased by more that 300%, among others because the cropping cycle has changed from two to three cycles per annum. The survey did not observe significant changes in the type of crops grown.

It is noteworthy to observe that 34% of respondents to the survey had increased the land that they owned, while 33% decreased the land that they rented. Although this was not measured by the survey, this suggests a significant capital accumulation in land assets.

  - Family/household incomes of 3,000 farmers increased by 100% within 24 months following acquisition of micro-irrigation pumps (progress rating: 1)

Surveys suggest that the average gross income after using the pump for about two years has increased by 267%. This amounts to an increase from Tzs. 313,510/- to Tzs. 1,150,279/- or an additional income of Tzs. 836,769 per annum. The average production costs, including input costs (seeds, fertilizers and insecticides) and labour costs, may be estimated at Tzs. 142,381 per annum (72 %more than before pump purchase). Thus, the average net profit per household from pump activities has increased by Tzs. 777,012/- per annum (337%). See table 1 below for a summary of survey data.

#### Table 1: Summary Of The Income and Expenditure

| Item | At zero age | 9 Months | 23 Months | % Increase / decrease |
| --- | --- | --- | --- | --- |
| Average gross Income | 313,510 | 670,534 | 1,150,279 | 267% |
| Average input costs (TZS) | 46,373 | 53,440 | 86,515 | 87% |
| Average labour costs (TZS) | 36,427 | 38,608 | 55,866 | 53% |
| Average total production costs (TZS) | 82,800 | 92,048 | 142,381 | 72% |
| Average net profit (TZS) | 230,886 | 578,486 | 1,007,898 | 337% |

Since the PCR had to base its analysis predominantly on available secondary data, it could not establish the changes in overall income structures. What is evident, however, is that the main beneficiaries of the project are not the poorest of the poor. They are the slightly better off farmers that are in a position to purchase the irrigation pump. That those with the most resources, capacity and motivation take up market opportunities first is, of course, to be expected and is natural in an approach that stimulates market mechanisms.

  - At least 33% of those using or managing irrigation pumps are women (progress rating: 2)

In Tanzanian traditions, a man is usually the controller of family assets. This has also been the case for pump ownership. The percentage of women owners who came from groups or women headed households was 5% of the total survey sample while the remaining 95% were men.

In most cases women became daily supervisors of field operations (here termed as managers). Managers were not necessarily the pump operators but sometimes they could be so.

Over a period of one year there has been a 54% increase in the number of women managers (see figure 1). The changes in the number of women managers have been brought about by job displacement, where the former manager is now responsible for other businesses that resulted from the income generated from the pump use. Because irrigation work has become less labour intensive, women can now more easily manage irrigation activities. The surveys reveal that 22% of respondents feel more respected and trusted by the community and family members than before they had the pump. A small percentage (9%) of farmers, mostly women, felt more financially independent. This appeared to be appreciated by men who are normally responsible for financial support to the family.

Pump users, particularly women, reported a notable reduction in time spend in the field. They are now using this saved time to undertake other productive activities.

Figure 1. Changes in the Gender Composition of Pump Owners and Managers

  - Purpose to goal

The surveys conducted by the project convincingly suggest that the improved access to micro-irrigation technologies has substantially improved incomes and livelihoods of small-scale farmers, thus contributing to poverty alleviation. ApproTEC/MIPP has clearly made widespread and significant impact through its interventions. However, one single technology cannot possibly have a dramatic impact on the incidence of poverty in Tanzania. What is more significant is that ApproTEC/MIPP has demonstrated that its approach to technology dissemination through market development may have substantially more impact than conventional approaches. The methodology has a high potential for replication for other technologies that contribute to poverty alleviation.

- SUSTAINABILITY

  - Approach and achievements

Since its inception in 2001, ApproTEC/MIPP has pursued a policy of facilitating private sector involvement in the manufacture, distribution and sale of its treadle pump. For the pump to become established in the market place ApproTEC/MIPP has adopted a deliberate strategy in which it took responsibility for technology transfer and engaged in market development activities. The project has been conscious of the need to create sustainable production, distribution and sale of its products through private sector channels. It has successfully applied strategies that were designed to target subsidy only where there would be no effect on long-term pricing and the natural sustainability of the commercial relationships that support production and distribution. The rationale for this approach, with temporary development subsidies, includes that neither the manufacturer nor wholesalers and retailers were ready to invest in making or selling the pump because it was an unproven product. Wholesalers also needed to develop trust relationships with retailers and develop client tracking and credit recovery systems. ApproTEC/MIPP has facilitated the development of the market by reducing the perceived levels of risk for the manufacturer, the wholesalers and the retailers. This has implied a temporary distortion of the pricing structure. It has yet to be seen if without the comfort of risk reduction by the project the market will eventually operate in a fully sustainable manner.

Subsidies have been aimed solely at:

- Technology R&D

The project has focuses on an irrigation technology that:

- is self-targeting the poor because the technology is affordable; easy to operate and simple and cheap to maintain; and they relate to the most common forms of economic activity;

- has made a significant contribution to household income;

- pays for itself in less than 3 months;

- could be produced and sold in very large numbers;

- has been appropriate for centralised mass manufacture and mass market distribution through existing wholesale and retail channels;

- is durable enough to repay investment costs by a factor of 10 and has predictable wear and breakdown characteristics

The essence of market economies is, of course, that businesses are encouraged to innovate and reap the rewards or losses of their risk-taking endeavours. Sustainable markets are not static – rather they are continually changing as competitive businesses seek to improve their product offerings. Public/donor investment in this context may still be justified. R & D to generate basic/public knowledge and defray risk for private business takes place in most industrialised countries. Similarly, in many countries there is debate over this public – private interface, especially the extent to which public investment in R & D stimulates (“crowds in”) or discourages (“crowds out”) private business product development innovation; the extent to which it develops or distorts capacities (incentives, skills and knowledge) for innovation. This debate is equally relevant in relation to ApproTEC’s work in Tanzania.

This PCR finds therefore that the rationale for subsidising the development of an irrigation technology that fulfils the above criteria is generally justifiable. However, it is less clear that this investment has facilitated a more entrepreneurial, innovative and self-reliant “supply-side” in the pump industry – a different but related objective to developing a market that delivers high volumes of pumps. And while it might be claimed that this was not the objective of this project there can be little doubt that, for the Tanzanian economy, this is the more important developmental issue.

- Technology transfer to a local manufacturer

The technology transfer process has been partly subsidised by the project, but all direct costs and capital investment in new production has been contributed by the selected manufacturer. This manufacturer has also made a substantial investment in the training of his staff, covering approximately 1/3 of the training costs. At the time of the PCR the manufacturer operated in a fully sustainable manner without support from the project.

- Promotion and market development

Initial support for promotion and market development has been provided by the project through mass media, storefront and marketplace demonstrations, billboards etc. The rationale for this investment is that it speeds up the rate at which a new technology is inserted into the market and the rate at which the market for the product expands. It is assumed that once there is a critical mass of users, further promotion become less necessary and can be provided at much lower cost (and thus can be paid for by the private sector) as the technology is creating its own demonstration effect.

  - Findings

- The OPR appreciates the validity of the project’s rationale, particularly in the Tanzanian context. The fear, as expressed in the OPR, that this approach could move both ApproTEC staff and other stakeholders into a ‘comfort zone’ where the available donor funds actually slow down the evolution or transition process, has proven to be unwarranted.

- During project implementation ApproTEC/MIPP has gradually withdrawn from nearly all areas of support and is very likely to leave a sustainable commercial market behind at project completion. In annex 3 some schematics show the evolution of the process by which a technology is introduced and inserted into the marketplace, with subsidies aimed at market development, but not at subsidising at the transaction levels between manufacturers, wholesalers, retailers and end-users. ApproTEC intends to identify new technologies and apply the same methodology again.

  - Challenges

In spite of the commendable achievements of the project there remain a few largely unpredictable issues with respect to sustainability. These issues are less related to ApproTEC/MIPP’s approach but more to how private sector market mechanisms will develop in an ever-changing market environment.

##### Finance

A very critical condition for further development of the market for irrigation pumps is the development of formal financing arrangements between financial institutions and, particularly, the manufacturer. The limited capital available to manufacturers, wholesalers and retailers is usually insufficient to maintain supply at projected rates of demand and, to ensure sustainability, it is essential to inject liquidity to the tune of about 3-months turnover at all levels. Without the project’s guarantee arrangements with different stakeholders in the supply, marketing and distribution chain, there would certainly have been a serious deficit of private investment capital available to finance inventory, stocks of raw material and work in progress. The project has determined that the most practical point at which ApproTEC/MIPP should facilitate investment is neither through retailers nor wholesalers. Retailers are too many and the costs of managing a large, geographically diverse portfolio would be too high, and financially unsustainable. Wholesalers are unsuitable recipients of formal debt finance because they already receive it in the form of supplier credit and are averse to paying the high cost of commercial capital. Instead it is more practical to ensure that the manufacturer has access to sufficient working capital - as long-term commercial debt. This is mainly because the costs of programming and managing a single loan to a manufacturer are much less – and much less risky – than doing so across a swathe of more than 78 retailers and 8 wholesalers. By doing this the manufacturer is able to provide 60 days credit to wholesalers, who themselves can maintain credit relationships to approved retailers. Such arrangements are also simpler in terms of brokering and guaranteeing commercial credit. Such arrangements have been put in place through the facilitation of the project. However, there are a few areas where only the future will tell how sustainable the intervention has been:

- It has yet to be seen if the manufacturer will be able to establish a sustainable relationship with financial institutions after ApproTEC’s withdrawal.  Indications are, however, positive.;

- There is, as yet, no guarantee that wholesalers will invest sufficiently in marketing, promotion and financing export orders to ensure sustainable operations and growth.

The above analysis indicates a basic but inescapable truth: “making markets work for the poor” with respect to irrigation technologies and the many services contained within this sub-sector requires also that financial services work effectively. And while these may be different areas of focus for donor-supported interventions, they are entirely complementary and synergistic objectives.

###### Inter-Firm Relationships and Embedded BDS

ApproTEC Tanzania is at present in the final stages of terminating all relationships with wholesalers and retailers by the end of November 2003. A relationship with the manufacturer will remain until March/April 2004 in order to complete the transition to NMB finance. A further longer-term relationship will then emerge as ApproTEC introduces new products, such as the re-designed hand pump and the Xtra-cycle.

With respect to the MoneyMaker Plus treadle pump the types of inter-institutional/firm BDS that are expected to remain embedded after project completion are presented in table 2 below.

Table 2: Inter-Firm Relationships and Embedded BDS

| Institution/Firm Receiving BDS | BDS | Supplier of BDS | Role |
| --- | --- | --- | --- |
| Manufacturer | Product quality and acceptability feedback Quality control Business planning and financial services (credit) support New product development and transfer | Wholesaler Private consultant National Microfinance Bank Manufacturer and ApproTEC | Provider Provider Provider Provider Facilitator |
| Wholesalers | Delivery of products Manufacturer credit Guarantee support | Manufacturer Manufacturer Manufacturer | Provider Provider Provider |
| Retailer | Delivery of Products Credit Promotion Guarantee support Feedback via guarantees | Wholesaler Wholesaler Wholesaler Wholesaler/ manufacturer End user | Provider Provider Provider Provider Provider |
| End Users/MSEs | Provision of products/pumps Guarantee support Advice Informal credit | Retailer Retailer Retailer/wholesaler/ manufacturer Retailer Retailer | Provider Provider Provider Provider Provider |

The PCR observes the following risk factors in the sustainability of these relationships:

- The manufacturer may not be able to develop and transfer new technologies without ApproTEC support;

- In principle, it has been agreed that the presently highly appreciated guarantee for end-users will continue to exist after project completion. However there is a risk that one or more participants in the chain may cease to honour their obligations as laid down in their inter-firm contracts.

- Retailers may not invest sufficiently in promotion of the pump. Although the pump is now a well known phenomenon in Tanzania, some form of promotion remains necessary for continued profitability and sustainability;

- Not all retailers will be able or willing to provide advisory and after-sales services to end-users. It is likely that only the more developed retailers will allocate resources to this;

- For the main wholesaler pump sales contribute only 5% to their total turn-over. Although the return on investment for the pump is higher than that of most other products, it would not hurt this (and probably other) wholesalers to stop selling pumps.

- The manufacturer sells about 50% of his production sold in Tanzania to one single wholesaler (Mukpar).  Although ApproTEC sees this as being positive because it contributes to efficiency it may lead to an unhealthy dependency

##### Competitiveness

As part of its strategy, ApproTEC/MIPP initially established generous margins to ensure the rapid market uptake by wholesalers and retailers. The PCR finds that acceptable. However, now the increased competition has the potential to lead to a 10% or better price reduction over time. If the ex-factory price of the pump dropped to $45, with $3 for transport added on and 15% commission was added by wholesalers and 25% commission added by retailers, the market price could drop to about US$ 69 from its present US$77. The generous retailer margins could permit a further 5% discount, which would make it feasible for the pump to sell at $66 – a total compounded price reduction of 11.6%. Such a reduction could only be achieved by increasing competition and while it is not being suggested that these changes be made, this does indicate the scope for significant price reductions.

It needs to be mentioned, however, that even at its present price the pump is generally considered cheap and that much higher prices are paid to middle men who procure the pump for remote locations. The point is not that the pump should become cheaper, but that it can survive in a more globally competitive business environment.

This is a very relevant observation because ApproTEC is contemplating turning their attention to the world market and outsourcing manufacture to the cheapest location. A preliminary study, commissioned by ApproTEC, suggests that the landed price of the Money Maker Pump from China would be US$45. While this does imply that manufacture in Tanzania is close to being globally competitive, there are a number of more fundamental questions raised by this proposal:

- ApproTEC have developed “their” products through their own endeavours but – in the main – with support from development agencies. They are still of the opinion that they are the “owners” of the design. It is questionable if any of ApproTEC’s support was ever sanctioned to give a competitive edge to already very efficient and competitive Asian manufacturers. Moreover, the experience from other developing economies (such as Bangladesh) is that Chinese pump producers (with their own designs) need little encouragement to find new markets. Thus far, as a matter of policy ApproTEC has decided not to import Chinese pumps into East Africa, but to rely on a cluster of manufacturers in Kenya and Tanzania to cover westwards and southern expansion.

- While ApproTEC’s wish for improved competition is laudable, it is slightly puzzling that their approach did not therefore seek to encourage more competition locally. As we have argued above, sustainable supplies of irrigation technology requires a competitive industry but this does not appear to have been a priority in ApproTEC’s intervention approach here; emphasis rather (and very successfully) has been given to delivery.   ApproTEC argues that the scale of the market at the present time does not justify the initiation of production through another manufacturer and indeed that the current manufacturer is able also to supply other countries to the south.

- Underlying these debates there appears to be a diversion of views. One view might be that the developmental benefits of technology arise only in its use; the view of this PCR (and of ApproTEC) is that while, undoubtedly this is the case, where appropriate, interventions should address systemic constraints that undermine the competitiveness of local industries to allow Tanzania (and Africa) to be more than consumers.

There is also an inherent risk for the sustainability of pump manufacturing if the manufacturer focuses more on exports. Although the demand presently appears to be strong and growing, this could be a short-term market development. Global markets tend to fluctuate and this may affect (positively or negatively) investments for expansion made by the manufacturer and, thus, his sustainable operation.

Finally, in relation to the competitiveness of the manufacturer, product development (of existing and new technologies) is essential for his continued operations. Although some capacity for innovation has been demonstrated, the PCR is not convinced that he has sufficient expertise, resources or incentives to undertake the necessary continued innovation.

- KEY LESSONS LEARNED

  - Project Level Lessons

It is crucial to have a clear strategy right from the start. The project has been of an innovative nature and a clear strategy has been developed over the years. The country director of ApproTEC has kept a tight control over his staff and the manufacturer, wholesalers and retailers (especially where it concerns the tracking of stocks and credit facilities). Good operational, financial and administrative systems have been put in place, including measurable benchmarks for staff and partner performance. Such rigorous supervision is essential to ensure good project performance.

For a pilot project it is essential to allocate sufficient resources to monitoring and evaluation to enable systematisation of the methodology and lessons learned. Within the budget constraints the project has performed satisfactorily where it concerns monitoring and evaluation. However, for the measurement of national economic and social impact of the introduction of this irrigation technology more resources should have been allocated to monitoring and evaluation.

  - Sector/Thematic Level Lessons

(a) Successful against given delivery indicators (but these may mislead)

ApproTEC has successfully delivered against the targets set out in the logframe-and this is to their credit. However, the PCR is concerned that the indicators that are given in the logframe are mainly indicators of delivery and less about sustainability.

(b) The underlying system – the market context

The experience from Bangladesh where huge donor resources were invested (using the same approach as ApproTEC) in pump design and wholesaler and retailer systems was initially a huge success in selling literally millions of pumps. However, when the Chinese developed new diesel pumps this whole infrastructure of delivery – of manufacturers and retailers etc. – found it difficult to respond. It remains questionable whether or not the system set-up by ApproTEC in Tanzania will be able to respond to serious external threats. The question of the wisdom of working with only one manufacturer in Tanzania remains valid, although it is to be noted that ApproTEC’s ‘cluster’ of manufacturers in East Africa ( 3 in Kenya) does allow for some degree of assurance that continuity of supply can be maintained..

Ultimately ApproTEC see local business development essentially as a means to an end – the logical conclusion of their current thinking may be to send all their designs to Asian manufacturers and allow them to export directly to a wholesaler and retailer system that has been made ready by ApproTEC! ApproTEC’s approach poses a challenge for development agencies – and especially for DFID in a context of its commitment to “making markets work for the poor” and to address underlying systemic causes of poverty. What is the market system that is “the problem” to be addressed and what are the constraints that prevent it from working effectively currently?

From initial conception through design and implementation to final evaluation, projects need to be shaped by a clear analytical understanding of (a) why markets “aren’t working” – the capacities, incentives, services and relationships that underpin the market (ie critical constraints), (b) how they could work more effectively and sustainably in the future, and (c) what interventions are required to facilitate this happening. This basic logic and analytical framework should apply for interventions related to all dimensions of private sector development (including financial services).

(c) Basic R & D

ApproTEC’s contention is that product development is a public good and that subsidies should therefore always be provided to support innovation. While one can certainly make the case that basic R & D and the generation of basic knowledge is a public good, we run into trouble if it is implied that private sector manufacturers should not innovate – the essence of business is of course that people take risks and reap the rewards or losses of this in their business performance. Public investment in R & D might defray risk – but it shouldn’t remove it. The underlying development issue here is: what is the state’s role in basic R & D and how should agencies help them play this role?

(d) Low cost technology development

The paradigm of "small is beautiful" applies in the first place to the contribution that a low-cost technology can make to alleviating poverty for the poor and not so much to the manner in which the technology is being manufactured, marketed and distributed. The mass-market development of such technologies may require sophisticated production techniques, taking into consideration economies of scale and considerations of cost-price reductions through improved product design and manufacturing technologies.

Manufacturers with low overheads and high volume production capacity (like the manufacturer of the MIPP irrigation pump) are likely to be more successful than sophisticated manufacturers with high overheads and low volume production (like the large manufacturing companies in Tanzania).

External support, in the form of facilitation and temporary incentives, are crucial to change the mind-set of mostly traditionally operating manufacturers, wholesalers and retailers in Tanzania. The pay-off of such support has proven to be very high in the case of MIPP in terms of delivery. There are selected pro-poor technologies where local Tanzanian manufacturers have the potential to become globally competitive with limited and temporary support only.

However, as with (b) above, technologies should not be considered in isolation from the wider market system of which they are a part. In this instance, the focus on one manufacturer only and one dominant wholesaler raises the question to what extent the project has really helped to stimulate a local competitive market.

  - General Development Lessons

(a) Measurement at different levels

Measurement of “final” impacts in economic development projects at the upper reaches of logframes is inherently difficult and expensive. While one can question aspects of ApproTEC’s methodology here – and claims of specific quantitative impact should be accompanied by appropriate caveats – relatively speaking, this is an exhaustive and rigorous approach from which others should learn. DFID interventions, if they require measurement at this level, must make appropriate provision in project budgets to allow this to take place.

Using their methodology, the cost-benefit ratio of project activities related to mass-market development of pro-poor technologies can be very high. However, in some ways, this misses the point; there never has been much doubt that irrigation technologies are useful per se. The more pressing measurement issue is how to assess change in the pump sub-sector, in particular the extent to which interventions have facilitated systemic, market change. It is development here that is the means to final ends.

(b) Beyond national boundaries

Globalisation and free market mechanisms necessitate thinking beyond national boundaries. Eventually, global competitiveness can only be achieved if manufacturers of low-cost technologies and wholesalers operate in a transnational manner. For Tanzania this implies considering markets in the East African Community (EAC) and the South African Development Community (SADC). The reality of the aforementioned globalisation may require DFID and other donors to revisit the predominantly national focus of their development cooperation efforts.

Lessons at the General Development Level may be discussed within DFID Tanzania and DFID as a whole.

  - Other issues

- The decision of DFID not to extend the project with one year, as recommended by the OPR, came rather late, has created some confusion and frustration in the project and necessitated another revision of the Logical Framework and the Budget.

- An extension of 6 to 12 months would have provided room for a more stable exit of MIPP from the market and would have thus better ensured long-term sustainabilty.

- So far a total of 1,650 pumps have been exported to Malawi, Mozambique and Kenya. Firm and pre-paid orders for another 600 pumps have been received from Mozambique and Haiti. Although exports go beyond the scope of the project, there is a persuasive logic to manufacture irrigation pumps for exports as well. It is a healthy sign of the move towards global competitiveness of local manufacturing.

- Nearly 20% of the end-users use the pump for more than one purpose, including household water provision, selling water, construction, brick-making, and livestock. There is evidence that some of these alternative utilisations are even more profitable than the use for irrigation.

- It is unlikely that the project will be able to fully wind-up before the end of December 2003. Especially for dissemination of the results some more time (say one to two months) may be needed.

- RECOMMENDATIONS

The PCR wishes to make the following recommendations to DFID:

- To systematise the experiences and lessons learned and disseminate these through a national workshop in Tanzania. Additionally these experiences and lessons could be disseminated through a publication in an international development journal;

- To roll over any budget left to a budget-neutral extension of maximum two months;

- To utilise the above lessons learned in debates over market development intervention approaches, the cost-benefit ratio, contribution to poverty alleviation and the need for an appropriate balance between project aid and budget support;

- To undertake a post project evaluation of how private sector market mechanisms have developed after project completion.

# Type of Report:

For quarterly monitoring, complete Part A and C; for annual review complete Parts A, B and C

For Project Completion Reports complete Parts A, B and C but it is not necessary to complete the Outputs/OVI field in Part A.

# PART A.

| Country: | Tanzania | Project: | Approtec MIPP |
| --- | --- | --- | --- |
| Project Officer Date of Visit: Date of Report: | Arif Salehmohamed 06/10/03 14/11/2003 | Start Date: End Date: MIS Code: Risk Category: | 09/03/1998 01/03/2003 063540037 |

| Project Budget | Spend in period under review | Cumulative spend | Forecast for current financial year |
| --- | --- | --- | --- |
| £1,450,000 | £228,170 | £1233,235 | £216,765 |

| Goal Statement | OVIs |
| --- | --- |
| To reduce the incidence of poverty in Tanzania through sustainable and substantial improvements in incomes and livelihoods of small-scale farmers | 1.1 50% of farmers using micro-irrigation pumps increase the area under irrigated cropping by at least 100% within 1 year following acquisition of a pump 1.2 Family/household incomes of 3,000 farmers increased by 100% within 24 months following acquisition of micro-irrigation pumps 1.3 At least 33% of those using or managing irrigation pumps are women |

| Purpose Statement | OVIs |
| --- | --- |
| To develop sustainable mass markets for manually operated water pump technology suitable for use by small-scale farmers. | 8,000 manually operated pumps sold in Tanzania, with 85% in active use by first-time users, by the end of project. At least one new water pumping technology suitable for mass manufacture and marketing identified and market-tested |

| Outputs /OVIs | Progress | Comments |
| --- | --- | --- |
|  | Planned (period under review) | Actual (including comments if required) | Planned for next period |
| 1. At least two types of manually operated irrigation pumps available in the market place without continuing project support. OVIs 1.1 35 retailers sell the pump with no project support. 1.2 At least 4 wholesalers distribute the pump to at least 30 retailers using their own networks and capital. 1.3 At least one manufacturer is profitably producing the irrigation pumps and distributing them to wholesalers, retailers and private customers. 1.4 New irrigation technology with mass market potential identified and market tested. | Planned is identical to OVIs in first column. | 1. There is one irrigation pump (the Super Money Maker Plus) available in the market. 1.1 78 retailers sell the pump with no project support. 1.2 8 wholesalers distribute the pump to 78 retailers without project support, using their own network and capital. 1.3 One manufacturer is very profitably producing high volumes and high quality irrigation pumps and distributing them to wholesalers. 1.4 One new irrigation technology (the Super Money Maker Plus) has proven to be mass marketable and profitable for the manufacturer, wholesalers and retailers. | 2. See 1.4 below. 1.1 Actual progress is 223% beyond target. However, it is likely that after withdrawal of ApproTEC support a number of smaller retailers based in smaller towns and villages will no longer we able or willing to sell the pump. A limited number of larger urban-based retailers (say 40) are likely to dominate the market in the future. 1.2 Actual is more than double of target. 1.3 The manufacturer only sells to wholesalers, who sell to retailers, who in turn sell to end-users. This is a system based on existing transaction practices in Tanzania. MIPP has achieved that various imperfections in the whole manufacturing-marketing-distribution-servicing chain have been taken away, leaving behind a well functioning and sustainable system in the private sector. 1.4 Experiments have been carried out with two new irrigation technologies (the Money Maker Plus and the Hand Pump). After market testing these technologies had to be withdrawn from the market due to lack of market potential and design flaws. The Hand Pump will be further developed by ApproTEC after MIPP ends. |
| 2. Financial services are available, tailored to the needs of at least 3 wholesalers to support inventory and to at least 40% of retailers. OVIs 2.1 National Microfinance Bank supplies fixed asset credit to the designated manufacturer. 2.2 Inventory credit supplied by manufacturer to wholesalers. 2.3 At least 15 retailers continue to receive 30 day supplier credit after project support is withdrawn. | Planned is identical to OVIs in first column | 2.1 The designated manufacturer has not received fixed asset credit from the National Microfinance Bank, but did receive a US$ 10,000 loan from them for the purchase of a truck. In addition the manufacturer has received a US$ 20,000 working capital finance from IFC, guaranteed by ApproTEC. 2.2 The manufacturer now provides 60 days supplier credit to wholesalers without any project support. Amounts are based on pre-set credit limits depending on capacity, history, etc. 2.3 About 90% of the present 78 retailers receive a 30 days supplier credit from the wholesalers without any project support. | 2.1 This loan is being repaid promptly by the manufacturer (will be fully repaid by April 2004). The manufacturer is thus building-up a track record with financial institutions. However, is has yet to be seen if this relationship will be sustainable. This loan will be taken over by NMB when the loan for the truck has been repaid. 2.2 The credit portfolio of the manufacturer is well managed and of good quality compared to standards of financial institutions in Tanzania. The question is whether or not this quality can be maintained without the folow-up support of MIPP staff. 2.3 Without the MIPP guarantee, it is likely that the majority of retailers will increasingly demand cash payment for the pumps. |
| 3. Economic, social and business impact monitoring system provides credible impact information and reliable insight into business investment criteria. OVIs 3.1 Economic impact measurement system accurately reports on income changes directly related to the use of irrigation technologies and indirectly arising out of new investments made with profits from irrigation activities. 3.2 Livelihoods security indicators identified and integrated into monitoring system 3.3 2 impact surveys available for assessment of national impact with one long-term follow-up | Planned is identical to OVIs in first column | 3.1 MIPP has developed an economic impact measurement system that provides detailed information on: - income changes at the farm household level directly related to the use of irrigation technologies - income changes at the farm level indirectly arising out of new investments made with profits from irrigation activities - economic impact of project activities on the mnaufacturer, the wholesalers and the retailers. 3.2 MIPP is using a system to measure livelihood security indicators and have integrated this into its monitoring system. 3.3 For a sample of 64 farmers in the Lake Zone and the North Eastern Zone one base-line survey or "Zero Age Survey" (two months after pump purchase) and two follow-up impact surveys (after a little less than one and two years after pump purchase respectively) are available. | 3. Within the possibilities and constraints of the project, MIPP has done a remarkable sound job in collecting and analysing economic and business impact data that appear both credible and reliable. The more complicated measurement of social impact at the national level requires more resources than are available in MIPP. 3.1 The system has been qualified by the Harvard Institute for International Development as a groundbreaking way of measuring economic impact. However, the PCR finds that: - the problem of attribution of economic impact could have been more adequately tackled. Especially in the absence of a control group it remains questionnable to what extent economic impact can be wholly and solely attributed to MIPP interventions; - The sample survey covered only Mwanza and North East Zones of Tanzania and represents only 0.8% of all pumps sold in Tanzania; - On the other hand, the PCR finds that MIPP has been very prudent in their claims with respect to impact and that the results of the surveys may be very indicative of national impact.. 3.2 The PCR is impressed with the manner in which MIPP measures impact on livelihood security indicators. However, as observed in the OPR, the system could have been less elaborate and still would have served DFID's purposes. 3.3 These surveys provide a wealth of information on economic and social impact at the farmers' level. However, MIPP could not have possibly carried out scientifically fully up to standard surveys within its resource constraints. |
| 4. General strategies articulated for market development approaches in Tanzania, related to technology and service dissemination. 4.1 Results shared with broad coalition of donors, government and NGOs | Planned is identical to OVIs in first column | 4. Approaches, lessons learned and best practices in this type of technology and market development activities have to a large extent been systematised and articulated. This process will be completed before the project ends. 4.1 So far, not much effort has been put into sharing results. | 4. MIPP has made commendable efforts to systematise their experiences and lessons learned. ApproTEC is really in a transitional phase to translate the experiences and lessons learned in MIPP and elsewhere in an innovative and contemporary approach to technology and market development. 4.1 It is understandable that MIPP has been cautious not to share results before they could be substantiated. Towards the end of 2003 or in the beginning of 2004 a workshop will be held to share experiences with a broad coalition of private sector representatives, donors, NGOs and Government Officials. |
| 5. |  |  |  |
| 6. |  |  |  |
| 7. |  |  |  |
| 8. |  |  |  |
| 9. |  |  |  |
| 10. |  |  |  |
| 11. |  |  |  |
| 12. |  |  |  |
| 13. |  |  |  |
| 14. |  |  |  |
| 15. |  |  |  |

| General /Overall progress assessment - Project Purpose |  |
| --- | --- |
| Justification |
| The progress made to achieve the project purpose is excellent. The project is an innovative example of how to develop sustainable mass markets for a technology that substantially increases income of small-scale farmers, improves their livelihoods, makes a local manufacturer more competitive and establishes a well functioning manufacturing, marketing and distribution chain for irrigation pumps in Tanzania. |
| General /Overall progress assessment - Project Outputs |  |
| Justification |
| 1. The quantitative targets for the number of pumps manufactured by a local producer and the distribution network of wholesalers and retailers and end-users involved have been substantially surpassed. New irrigation technologies with mass market potential have been identified, but did not prove to be succesful in reality. 2. A system of financial service provision for the manufacturer, wholesalers and retailers has been established and is likely to continue to function without project support. 3. A system for monitoring economic, social and business impact has been establsihed and is exemplary within the constraints of the available resources. 4. Important lessons have been learned about feasible market development strategies related to technology and service dissemination. The systematisation of these lessons is nearly complete and will be disseminated among private sector stakeholders, donors, the Government of Tanzania and NGOs. |

| Log Frame Level |  |  |  |
| --- | --- | --- | --- |
| Inputs/Activities |  | Performance Rating | Comments |
| (a) Appropriateness (quality): | (a) DFID |  |  |
|  | (b) Partner |  |  |
| (b) Efficiency (quantity): | (a) DFID |  |  |
|  | (b) Partner |  |  |
| (c) Sufficiency (timeliness): | (a) DFID |  |  |
|  | (b) Partner |  |  |
| overall assessment*: |  |  |  |

(*) Including conditionality aspects where relevant

PART B.

| Purpose /OVIs | Progress | Comments |
| --- | --- | --- |
| To develop sustainable mass markets for manually operated water pump technology suitable for use by small-scale farmers. OVIs 8,000 manually operated pumps sold in Tanzania, with 85% in active use by first-time users, by the end of project. At least one new water pumping technology suitable for mass manufacture and marketing identified and market-tested. | Till September 2003 a total of 7,345 pumps have been sold in Tanzania. MIPP has attempted to adapt the design of a very low cost hand pump from ApproTEC Kenya. This technology has been market tested and proven to show design flaws. This technology has, for the time being, been declared unfit for mass manufacturing and marketing. | A total of 8,955 pumps have been sold if exports are included. Based on projections from previous years and quarters, the target of 8,000 pumps sold in Tanzania will easily be achieved. A net figure of 8,350 pumps sold in Tanzania at project completion is a realistic estimate. There is evidence that the design flaws may be addressed in the near future and that this technology may still have a potential for mass marketing. |

Attribution

ApproTEC/MIPP has provided facilitation and incentives to the manufacturer, wholesalers, retailers and end-users that have made them aware of the benefits that a well functioning market mechanism offers them. It is higly unlikely that without the project support the market would have developed in the manner it now has.

Purpose to Goal

The improved access to micro-irrigation technologies has evidently substantially improved incomes and livelihoods of small-scale farmers, thus contributing to poverty alleviation. ApproTEC/MIPP has clearly made widespread and significant impact through its interventions. However, one single technology cannot possibly have a dramatic impact on the incidence of poverty in Tanzania. What is more significant is that ApproTEC/MIPP has demonstrated that its approach to technology dissemination through market development may have substantially more impact than conventional approaches. The methodology has a high potential for replication for other technologies that contribute to poverty alleviation. The return on investment of the approach is impressive.

DOES LOGFRAME REQUIRE REVISION?

Not applicable.

DO PIMS MARKERS REQUIRE REVISION [ Mandatory for projects approved prior to 1.4.98 ]

Not applicable.

Quality of Scoring

High.

Lessons learned, and suggested dissemination. For PCRs please comment on (i) Project/Programme Level Lessons, (ii) Sector Level or Thematic Lessons, and (iii) General Development Lessons

(i) Project Level Lessons - It is crucial to have a clear strategy right from the start; - Good operational and financial and administrative systems need to be in place, including measurable benchmarks for staff and partner performance; - Sufficient resources should be allocated to monitoring and evaluation to enable systematisation of the lessons learned; - Rigorous supervision is essential to ensure good project performance. (ii) Sector Level or Thematic Lessons - The paradigm of "small is beautiful" applies in the first place to the contribution that a low-cost technology can make to alleviating poverty for the poor and not so much to the manner in which the technology is being manufactured, marketed and distributed. The mass market development of such technologies may require sophisticated production techniques, taking into consideration economies of scale and considerations of cost-price reductions through improved product design and manufacturing technologies; - Manufacturers with low overheads and high volume production capacity (like the manufacturer of the MIPP irrigation pump) are likely to be more successfull than sophisticated manufacturers with high overheads and low volume production (like the large manufacturing companies in Tanzania); - External support, in the form of facilitation and temporary incentives, are crucial to change the mind-set of mostly traditionally operating manufacturers, wholesalers and retailers in Tanzania. The pay-off of such support has proven to be very high in the case of MIPP. - There are selected pro-poor technologies where local Tanzanian manufacturers have the potential to become globally competitive with limited and temporary support only. These Sector/Thematic lessons may be disseminated through a national workshop in Tanzania and through a publication in a reputable international development journal. (iii) General Development Lessons - The cost-benefit ratio of project activities related to mass market development of pro-poor technologies is very high; - Globalisation and free market mechanisms neccesitate thinking beyond national boundaries. Eventually, global competitiveness can only be achieved if manufacturers of low-cost technologies and wholesalers operate in a transnational manner. For Tanzania this implies considering markets in the East African Community and the South African Development Community. - The reality of the aforementioned globalisation may require DFID and other donors to revisit the predominantly national focus of their development cooperation efforts. Lesons at the General Development Level may be discussed within DFID Tanzania and DFID as a whole.

# Part C

Key Issues / Points of information. For PCRs please comment on Sustainability

1. The decision of DFID not to extend the project with one year, as recommended by the OPR, came rather late, has created some confusion and frustration in the project and necessitated another erevision of the Logical Framework and the Budget. 2. An extension of 6 to 12 months would have provided room for a more stable exit of MIPP from the market and would have thus better ensured long-term sustainabilty. 3. A long-term risk for the manufacturing of irrigation pumps in Tanzania is the import of low-cost mass produced pumps from low-production cost countries (e.g. China). However, there is evidence that the manufacturing and distribution system for irrigation pumps in Tanzania may rapidly become globally competitive, especially if policies become more conducive to local production. 4. So far a total of 1,650 pumps have been exported to Malawi, Mozambique and Kenya. Firm and pre-paid orders for another 600 pumps have been received from Mozambique and Haiti. Although exports go beyond thw scope of the project, there is a persuasive logic to manufacture irrigation pumps for exports as well. It is a healthy sign of the move towards global competitiveness of local manufacturing. 5. Once the market has been completely liberalised after MIPP's withdrawal, it is likely that there will be a downward pressure on prices. There appear to exist a substantial price elasticity of the irrigation pump at the manufacturer, wholesalers and retailers levels. 6. Nearly 20% of the end-users use the pump for more than one purpose, including household water provision, selling water, construction, brick-making, and livestock. There is some evidence that some of these alternative utilisations are very profitable. 7. It is unlikely that the project will be able to fully wind-up before the end of December 2003. Especially for dissemination of the results some more time (say one to two months) may be needed.

| Recommendations | Responsibility | Date for completion |
| --- | --- | --- |
| To systematise the experiences and lessons learned and diiseminate these through a national workshop in Tanzania and a publication in an international development journal. | ApproTEC/MIPP | End of February 2004 |
| To roll over any budget left to a budget-neutral extension of maximum two months | DFID Tanzania | November 2003 |
| To utilise the General Developmental Lessons learned in the debate about the cost-benefit ratio, contribution to poverty alleviation and the need for an appropriate balance between project aid and budget support | DFID | Ongoing |
| To undertake a post project evaluation of how private sector market mechanism have developed after project completion | DFID | December 2004 |

| Review team: | Leon Tomesen, The Springfield Centre for Business Development |
| --- | --- |
| People met: | Liz Ditchburn, DFID Tanzania, Private Sector Development and Rural Livelihoods Adviser Iain Jones, DFID Tanzania, Economist Arif Salehmohamed, DFID Tanzania, Assistant Programme Officer Hugh Alan, ApproTEC/MIPP, Country Director Hillary Shiboni, ApproTEC/MIPP, Marketing Manager Monica Minja, ApproTEC/MIPP, Monitoring and Evaluation Officer Walter Massamu, Finance and Administrative Officer Aloyce Dinho, Consultant Aloys Kahinga, Director Karam Engineering Works, Pump manufacturer Ram Singh Panesar, Director Karam Engineering Works, Pump manufacturer Ajay Shah, Director Mukpar Tanzania Ltd., Wholesale dealer Mr. Patel, Manager Mukpar Moshi, retailer. Tanzania Farmers' Association, Moshi, retailer Rafiki Kilimo, Moshi, retailer. Kimangoro Enterprises, Himo, retailer Unnamed group of youths making bricks, Moshi, non-irrigation end-users Farmer, Arusha, end-user |

Scoring system:

1 = likely to be completely achieved           4 = only likely to be achieved to a very limited extent

2 = likely to be largely achieved                 5 = unlikely to be realised

3 = likely to be partially achieved               x = too early to judge extent of achievement

Annex 2: TERMS OF REFERENCE FOR THE PROJECT COMPLETION REVIEW OF THE APPROTEC MICRO- IRRIGATION PROMOTION PROJECT.

# 1. Background

1.1 ApproTEC, a Kenyan and a Tanzanian NGO, has been promoting the design, development, local manufacture and marketing of low cost technologies to promote enterprise development and income and employment generation for the last fifteen years. Their track record has been impressive and a number of ApproTEC technologies have become sustainable and profitable in the private sector. Notable successes have been a manual oil seed press, various low cost building technologies and the micro-irrigation pedal pump. ApproTEC has developed three models of the pedal pump, designed specifically for use by small-scale farmers, which have proven extremely popular in the Kenyan market.

1.2 DFIDEA provided funding to ApproTEC to assist the organisation undertake a market-test of the pedal pumps in Tanzania in the year 2000. The market test was intended to assess market potential for the pedal pump and assist ApproTEC gather sufficient information and experience upon which to base a cogent strategic plan for the marketing of the pumps. Following a review of the market test which endorsed a demand for pedal-pumps in Tanzania, DFIDEA(Tanzania), in August 2000, provided £1,360,000 funding for the implementation of the Micro-irrigation promotion project (MIPP).

1.3 The purpose of MIPP is ‘to improve access by small-scale farmers to manually operated water-pump technologies on a sustainable basis’. It is assumed that the successful implementation of this will lead to the project goal which is ‘to reduce the incidence of poverty through sustainable and substantial improvements in the incomes and livelihoods of small-scale farmers’.

1.4 The MIPP project has been operational for just over three years. Due to the changing nature of DFID’s Tanzania country programme, the project will not be extended beyond its current completion date of 31 December 2003. As the project has spent over 80% of its total budget, a Project Completion Report (PCR) is now due.

# 2. Objective

2.1 There are four main objectives underlying this assignment. These are to:

- Assess the extent to which the project outputs and purpose have been achieved;

- Assess the extent to which project achievements are likely to contribute to the goal of the project, ie the extent to which the incomes and livelihoods of small scale farmers have been or are likely to improve as a result of project action.;

- Assess the extent to which the achievements of the project are sustainable;

- Provide lessons learnt from the project with respect to

- Project/Programme Level Lessons

- Sector Level or Thematic Lessons, and

- General Development Lessons. .

In pursuing the assignment, and given the timescale of the task and the resources available, the consultant will draw principally on available secondary data and on discussions with key stakeholders. Given that more information is available on project outputs and purpose – the immediate essence of the project – the analysis will be more detailed at these levels.

# 3. Terms of Reference

3.1 During the visit the consultant will:

- Assess progress against the project purpose and outputs as

indicated in the logical framework (attached 1) in the project memorandum. This will involve determining the status of the objectively verifiable indicators (OVIs) specified in the project logical framework and wider evidence pertinent to progress against the outputs and purpose. Progress should be scored according to DFID’s standard project scoring approach (as outlined in PCR form) with an explanation provided for the scores. The scoring scheme is:

1 = likely to be completely achieved,

2 = likely to be largely achieved,

3 = likely to be partially achieved,

4 = only likely to be achieved to a very limited extent,

5 = unlikely to be achieved,

x = too early to judge the extent of achievement.

Ascertain impact of the project on small scale farmers incomes and livelihoods.

Assess the effectiveness of the project’s approach to facilitating the making of mass markets for technology. This should include an assessment of the functioning of the market chain in its entirety from manufacturer to retailer, including financing, profitability and sustainability of market development.

- Assess the types of relationships that have been established outside the market chain to ensure sustainability and effective utilisation of the pump e.g. with post-purchase maintenance, organisations providing irrigation advice, extension workers, rural financial services etc.

Carry out, using available data, an economic assessment of the benefits attributable to the project. In doing so, an examination of the impact on incomes and livelihoods of farmers using the pump compared to the incomes and livelihoods of farmers that do not have access to the pumps would be useful. However, an important focus for this economic analysis should be on underlying changes in the immediate market environment for farmers (users and non-users) that have been caused by the project’s intervention.

# 4. Management and Duration

4.1 DFID’s Corporate Team comprising of Julia Knowlton, Cuthbert Maendaenda and Arif Salehmohamed, will manage the assignment and be responsible for selecting the consultant and reviewing reports submitted. Liz Ditchburn (Private Sector Development and Rural Livelihoods Adviser) and Iain Jones (Economist) will provide any specialist inputs.

4.2 The project input for the study is a maximum of 24 days and is scheduled to commence October 6 and finish by Nov 14, 2003.

# 5. Reporting

5.1 The consultant is required to submit a review report (maximum of 20 pages for the main body of the report) with an executive summary and relevant annexes covering the objectives of the assignment.

5.2 The consultant will also submit a completed Project Completion Report form (template attached) summarising the findings and utilising the DFID scoring system.

5.2 Two reports will be required for each document, a draft report for comment and a final report following receipt of comments. The consultant should submit to Julia Knowlton, Deputy Programme Manager, DFID Tanzania:

- 2 bound copies of the final report;

- An electronic version sent to Julia Knowlton (j-knowlton@dfid.gov.uk) copied to Arif Salehmohamed (a-salehmohamed@dfid.gov.uk) and Cuthbert Maendaenda (c-maendaenda@dfid.gov.uk ).

Annex 3:

# Annex 4: EXECUTIVE SUMMARY SECOND FOLLOW-UP SURVEY

The Micro-Irrigation Promotion Project (MIPP) promotes the use of MoneyMaker pressure irrigation pump in Tanzania. This report contains the economic and social impact findings for end users of the pump in North and Northeast parts of Tanzania. It covers 14 districts, 9 in Mwanza and Mara regions and 5 districts from Arusha, Kilimanjaro and Tanga.

# Objective .The survey aimed to assess if there were significant economic benefits that could be reasonably attributed to the use of pumps at individual, household and farm enterprise levels after one-year’s utilisation.

# FINDINGS

# Gender and Age Composition of End-users. 95% of men owned the pump. But the number of male managers has dropped from 62% to 39% after 14 months utilisation. The number of female managers increased from 38% to 61%. 73% of pump managers were between 20-40 years old. Women perform 42% of the work in the Lake Zone while in the Northern Zone women perform 38%.

Shelter . There was a 38% increase in the number of farmers living in houses made from burnt bricks and roofed by iron sheets and an11% increase for those living in houses made from cement bricks and roofed by iron sheets. 48% of respondents were engaged in home improvements

# Economic Impact

Irrigation enterprise. The survey did not observe changes in the type of crops grown. But the cropping cycles changed from 2 to 3 cycles per year.

Household Income and Expenditure .  The gross income per household from irrigation shows a 336% increase from TZS 230,886/- to 1,007,898. The net was TZS 777,006.

# There was also an increase in household income from other economic activities of 145%, from TZS.361,326/-p.a. to TZS.886,809/-. Thus total family income changed from TZS.592,212/-per year to TZS.1,894,707/-p.a., 53% of which was contributed by irrigation activities. Most ‘other’ economic activities were financed by income from irrigation.

Employment. Total jobs from irrigation activities in the Lake Zone have increased from 1.098 jobs per household to 1.44 jobs after 14 months.

# Land ownership. The land owned by an average household had increased from 7.25 acres to 7.60 acres. 34% of respondents had increased the land that they owned, while 33% decreased the land that they rented. This implies significant capital accumulation in land assets, which were not measured by the survey. The irrigated land increased from 0.96 acres before using the pump to 1.15 acres per household. Land under irrigation had increased productivity by more than 300%

# Livestock. Livestock numbers increased by 156%, an average of 4.72 improved animals per household. The average livestock numbers (traditional and improved) increased from 8.55 to 16.64 per family.

Individual Social Status. Most participants confirmed improved social status in terms of recognition, respect and their participation in associations. Within associations they tended to rise to leadership positions.

## Annex 5: SUMMARY REPORT OF COMMERCIAL STUDY

ApproTEC’s strategy is to identify small-scale enterprise opportunities, find a technology gap (if one exists) and then design and develop technologies that fill the gap and provide enterprise opportunities for small-scale entrepreneurs. This is followed by the development of private sector relationships with manufacturers, wholesalers and retailers to disseminate the technology through market channels. ApproTEC then monitors the impact of the whole process.

Over the years, ApproTEC has enabled tens of thousands of people in Africa to create wealth, improve their standard of living and contribute positively to the economic growth of their countries.

## Objective of the study

The objective of this survey was to make an assessment of economic impact amongst the following:

- manufacturer

- selected wholesalers

- selected retailers

The approach taken was to compare the commercial attractiveness of the treadle pump compared to the top 5 competing products, using the following measures:

#### The return on capital employed in making, distributing and selling the treadle pump;

#### The return on capital related to the pump compared to the total capital employed;

#### The pump sales income contribution to gross margin;

#### Employment created

## FINANCIAL BENEFITS TO THE MANUFACTURER

Pro-forma financial statements, based on actual sales and production figures for the last 12 months, show the following:

- Increase of net cash of 19.0 million

- Net post-tax profit of 34.4 million TZS on sales of 209 million

- Return on capital employed of 19%

- Return on equity of 22%

These are competitive figures. Most light manufacturing enterprises in Arusha are suffering from the effects of globalisation and the opening of domestic markets for foreign manufactured goods. Many of these are zero rated for import duty and sales tax, while imported steel used by industries to make the same goods attracts both duty and tax, putting local producers at a serious competitive disadvantage. We estimate, for example, that steel in China costs approximately half the landed price in Tanzania. As a result most light engineering companies in Arusha limp along with either zero or negative returns on capital, producing similar products. Karam is able to charge higher margins because his pumps cannot easily be copied and have a high market demand.

22 staff are employed full time in the manufacture of the pumps, which account for 90% + of gross income.

## TREADLE PUMPS FINANCIAL IMPACT ON  WHOLESALERS AND RETAILERS

Treadle pumps have been a seasonal and slow moving product but have made a significant contribution to the business gross margin of 63% to wholesalers with only 27% of the total business capital investment. Also the return on capital invested in buying pumps is 49% while five other items recorded had an average of 40% return.

Also, it has a contribution of 21% to retailers' business gross margins, and a return on capital of 53% with only 11% capital investment. Other products have 49% return on capital.

The above results imply that pump margins are attractive to wholesalers and retailers and encourage them to continue with this business. The pump promotion and advertisement that have been taking places in different parts of the country, either by wholesalers and retailers themselves or by project, creates awareness amongst suppliers and end users. It is our conclusion that retail and wholesale margins have potential for significant reduction given increased competition.

Table 1: National Wholesalers Annualized Ratios

| Wholesaler | Return On Capital (Pump) | Return On Capital (Other Products) | Pump Contribution per period | % Capital Invested in Pumps |
| --- | --- | --- | --- | --- |
| Tanza Water & Wells | 33% | 95% | 24% | 48% |
| R. H. Patel | 77% | 71% | 39% | 37% |
| Mukpar Tz Limited Mwanza | 96% | 24% | 31% | 10% |
| KONARK Associates | 51% |  | 100% | 100% |
| BCS Kariakoo | 64% | 40% | 69% | 58% |
| Average | 49% | 40% | 63% | 27% |

. Table 2:  National Retailers Annualized Ratios

| Retailer | Return On Capital (Pump) | Return on Capital (Other Products) | Pump Contribution To gross Margin | % Of Capital Invested in Pump |
| --- | --- | --- | --- | --- |
| Mukpar Tz Limited Moshi Branch | 77% | 25% | 62% | 34% |
| BCS Super market | 63% |  | 100% | 100% |
| VETEX Korogwe | 97% | 62% | 77% | 68% |
| SOS Investments | 44% | 89% | 17% | 29% |
| Nzega Agrovet | 39% | 21% | 43% | 29% |
| Ndekimo Agrovet | 37% | 74% | 57% | 72% |
| Mausa AgroVet | 80% | 56% | 5% | 18% |
| Mamba Agrovet | 57% | 10% | 30% | 7% |
| Mahelasa Investments | 19% | 23% | 38% | 43% |
| Kilimanjaro Hardware | 44% | 6% | 57% | 16% |
| K.V Animal Health | 52% | 95% | 35% | 50% |
| Ilula Investments | 51% | 14% | 4% | 10% |
| Igunga District Council | 25% | 1% | 87% | 27% |
| G. G Investments | 76% | 18 | 47% | 17% |
| Cosmos Agro Seeds | 76% | 71% | 1% | 1% |
| Average | 53% | 49% | 21% | 11% |

PUMP SALES TREND

Wholesalers

The treadle pumps sales trend for wholesalers shows high sales in July to December and low sales in January to April. Most wholesalers started handling the pump from January 2002. This makes it difficult to get a clear comparison between years. In most part of the country, the dry season runs from June to November and is a peak period for pumps sales. (refer table 3 and figure 1 below).

Table 3: National Wholesalers Treadle Pumps Sales Trend

| Wholesaler | Jan-01 to Mar-01 | Apr-01 to Jun-01 | Jul-01 to Sept-01 | Oct-01 to Dec-01 | Jan-02 to Mar-02 | Apr-02 to Jun-02 | Jul-02 to Sept-02 | Oct-02 to Dec-02 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mukpar Tanzania Ltd Mwanza Branch | 0 | 80 | 100 | 50 | 0 | 30 | 100 | 0 |
| R. H. Patel | 0 | 15 | 70 | 25 | 40 | 50 | 100 | 39 |
| BCS Kariakoo | 0 | 0 | 40 | 10 | 40 | 50 | 50 | 50 |
| KONARK Associates | 0 | 0 | 35 | 0 | 45 | 50 | 50 | 32 |
| Tanza water & Wells | 0 | 0 | 40 | 36 | 10 | 150 | 170 | 30 |
| Total | 0 | 95 | 285 | 121 | 131 | 326 | 470 | 151 |
| Average | 0 | 19 | 57 | 24.2 | 27 | 63 | 94 | 30.2 |

Figure 1: National Wholesalers Sales Seasonal Fluctuation

## Retailers

The highest season for sales at the retailer level is April to September, with the highest peak attained in July. This is the season when farmers have already harvested the rain fed crops. Thus are able to use their revenues to buy pumps.

Table 4: National Retailers Treadle Pumps Trend Sales Trend

| Retailer | Jan-01 to Mar-01 | Apr-01 to Jun-01 | Jul-01 to Sept-01 | Oct-01 to Dec-01 | Jan-02 to Mar-02 | Apr-02 to Jun-02 | Jul-02 to Sept-02 | Oct-02 to Dec-02 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mausa Agro vet | 2 | 7 | 19 | 4 | 2 | 5 | 7 | 1 |
| Ndekimo Agro vet | 0 | 0 | 0 | 0 | 10 | 11 | 25 | 0 |
| Nzega Agro Vet | 0 | 0 | 2 | 4 | 4 | 6 | 7 | 0 |
| Igunga District Council | 0 | 5 | 10 | 5 | 0 | 6 | 9 | 5 |
| Mukpar Tz Ltd Moshi | 0 | 0 | 2 | 14 | 7 | 25 | 25 | 0 |
| Kilimanjaro Hardware | 0 | 0 | 0 | 0 | 10 | 37 | 37 | 34 |
| Mamba Agro Vet | 3 | 8 | 18 | 0 | 7 | 14 | 5 | 2 |
| VETEX Korogwe | 0 | 20 | 7 | 10 | 7 | 3 | 5 | 7 |
| SOS Investments | 0 | 4 | 6 | 0 | 3 | 1 | 0 | 0 |
| BCS Supermarket | 0 | 0 | 150 | 40 | 0 | 50 | 100 | 10 |
| Cosmos Agro Vet | 0 | 0 | 2 | 7 | 7 | 8 | 8 | 8 |
| G. G Investments | 0 | 0 | 1 | 8 | 2 | 7 | 9 | 5 |
| K.V. Animal Health Center | 0 | 0 | 6 | 8 | 5 | 14 | 12 | 22 |
| Mahelasa Investments | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 |
| Ilula Investments | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 1 |
| Total | 5 | 44 | 223 | 100 | 66 | 192 | 252 | 95 |
| Average | 2.5 | 22 | 111.5 | 50 | 33 | 96 | 126 | 47.5 |

Figure 2: national retailers sales Seasonal Fluctuation

Thus it will be seen that there is a high degree of compatibility between wholesaler and retailer sales. This is hardly surprising. But most retailing and wholesaling enterprises sell very few pumps for 4-5 months of the year, which poses special challenges for the manufacturer who must use the down season to stock for the high season. This implies significant working capital requirements.

## EMPLOYMENT

Wholesalers and Retailers

The treadle pump created 44% of total jobs at wholesaler level and 32% of jobs at retailer level.

Although treadle pumps have made a greater financial impact on both wholesalers and retailers, there is less effort made in selling the products. If 44% of the wholesaler employees and 32% of the retailer employees can sell the product with 49% and 53% returns respectively. Then, allocating more labour may positively affect the sales.

Table 5: The Percentage Contribution Of Pumps To Employment at Wholesalers Level

| Wholesaler | Other Products | Pump related | Percent |
| --- | --- | --- | --- |
| Mukpar Tanzania Ltd Mwanza Branch | 5 | 1 | 20% |
| R. H. Patel | 3 | 1 | 33% |
| BCS Kariakoo | 2 | 1 | 50% |
| KONARK Associates | 3 | 3 | 100% |
| Tanza water & Wells | 3 | 1 | 33% |
| Total | 16 | 7 | 44% |

Table 2: The Percentage Contribution Of Pumps To Employment At Retailers Level

| Retailer | Other Products | Pump related | Percent |
| --- | --- | --- | --- |
| Mausa Agro vet | 2 | 0 | 0% |
| Ndekimo Agro vet | 2 | 2 | 100% |
| Nzega Agro Vet | 3 | 1 | 33% |
| Igunga District Council | 0 | 0 | 0% |
| Mukpar Tanzania Ltd Moshi | 3 | 1 | 33% |
| Kilimanjaro Hardware | 2 | 0 | 0% |
| Mamba Agro Vet | 5 | 1 | 20% |
| VETEX Korogwe | 1 | 1 | 100% |
| SOS Investments | 1 | 0 | 0% |
| BCS Supermarket | 5 | 1 | 20% |
| Cosmos Agro Vet | 5 | 1 | 20% |
| G. G Investments | 1 | 1 | 100% |
| K.V. Animal Health Center | 4 | 1 | 25% |
| Mahelasa Investments | 1 | 1 | 100% |
| Ilula Investments | 3 | 1 | 33% |
| Total | 38 | 12 | 32% |

## CONCLUSIONS

- Manufacturer. The manufacturer is running a highly profitable business with an excellent return on capital and equity. This is in a business environment where light engineering is severely depressed and uncompetitive in the face of global competition. There appears to be a number of reasons for this. The first is that the pump is hard to copy and is linked to a sophisticated marketing network. Most manufacturers make to order and do not manage a market. The second is that the pump is hard to copy, but this is less important. Where the pump has been copied it has failed to make an impression on the market because the preferred strategy of the competition has been to maximize net margins and make little or no investment in extensive market development. More than anything else this contributes to the manufacturer’s competitive edge. Additional analysis indicates that the price of the pump could be reduced from TZS 50,000 to TZS 47,000 ($45) and still provide a return on capital of 19% and 22% on equity. Thus, it is likely that price will at least remain stable for the next few years and could, in principle, be reduced in the face of serious competition. The appended analysis shows how this is feasible: it is not the current situation, but a pro-forma analysis that could apply in a more competitive business environment.

- Wholesalers. Wholesalers are making an approximate 9% better return on capital from the pump than from other products and, with only 27% of their capital invested in pumps are deriving 63% of their gross income from pump sales during the irrigation season. This indicates that wholesaler margins are generous and could probably be reduced from 20% per pump down to 15%.

- Retailers. The return on capital employed is, at 53%, only slightly higher for pumps than for the top 5 other products (49%). But with only 11% of their capital invested in the pump, 21% of returns are generated by pump sales during the season. Even though their margins are greater (at 25%) than for wholesalers, there is little likelihood of a formal reduction in margins, except, as is already happening, through discounts. The evidence of price elasticity and adequacy of returns is that a large proportion of retailers have made provision for the replacement of ApproTEC’s demonstration staff with their own and a number of dealers are offering discounts.

- Pricing. If the ex-factory price of the pump dropped to $45, with $3 for transport added on and 15% was added by wholesalers and 25% added by retailers, the market price could drop to about 69$ from its present $77. The generous retailer margins could further permit a 5% discount, which would make it feasible for the pump to sell at $66 – a total compounded price reduction of 11.6%. Such a reduction could only be achieved by increasing competition and it is not proposed that ApproTEC suggests such changes. This merely indicates potential price elasticity. It needs to be mentioned, however, that even at its present price the pump is generally considered cheap and that much higher prices are paid to middle men who procure the pump for remote locations. The point is not that the pump should become cheaper, but that it can survive in a more competitive business environment. Thus, if cheap imports start to arrive, there is considerable scope for continued local manufacture and distribution.

The basic conclusion of the study, therefore, is that ApproTEC’s establishment of generous margins is a key factor in the rapid market uptake by wholesalers and retailers, but that increased competition can lead to a 10% or better price reduction over time.

# Annex 6: ApproTEC TANZANIA’S APPROACH TO MARKET DEVELOPMENT

Background

Since its inception in 2001, ApproTEC Tanzania has pursued a policy of facilitating private sector involvement in the manufacture, distribution and sale of its treadle pumps. For the pump to become established in the market place it has been necessary to adopt a deliberate strategy in which ApproTEC took responsibility for technology transfer and engaged in market development activities that, over time, substituted ApproTEC investment for private sector investment.

Process

ApproTEC is conscious of the need to create sustainable production, distribution and sale of its products through private sector channels. Its strategies are designed to target subsidy only where there will be no effect on long-term pricing and the natural sustainability of the commercial relationships that support production and distribution. Subsidies are aimed solely at:

- technology R&D

- technology transfer to manufacturers

- promotion and market development

The process is as follows:

Technology Choice ApproTEC focuses on technologies that fulfill the following criteria:

- they must self-target the poor because:

- they are affordable; costing less than 3 months disposable income to buy

- they are easy to operate and simple and cheap to maintain

- they relate to the most common forms of economic activity

- they must make a significant contribution to household income (at least double)

- they pay for themselves in less than 3 months

- they must have the potential to be produced and sold in very large numbers

- they must be capable of centralised mass manufacture and mass market distribution through existing wholesale and retail channels

- they are durable enough to repay investment costs by a factor of 10 and must have predictable wear and breakdown characteristics

R&D In the case of R&D ApproTEC’s rational for subsidy is that new product development requires it and that public subsidy through universities and research institutions is a normal part of the industrial experience in developed countries. In developing countries this public subsidy does not exist and without the evidence of market demand the private sector is unlikely to make substantial investment in R&D. Thus it falls to organizations like ApproTEC to engage in new product development to substitute for this deficiency.

Technology Transfer The technology transfer process is partly subsidized, but with all direct costs and capital investment in new production contributed by selected industrial partners. Industrial partners must also make a substantial investment in the training, covering approximately 1/3 of the costs.

Promotion and Market Development This involves mass media, storefront and marketplace demonstrations, billboards etc. The rationale for this investment is that it speeds up the rate at which a new technology is inserted into the market and the rate at which the market for the product expands. It is assumed that once there is a critical mass of users further promotion become less necessary and much lower cost (and thus can be paid by the private sector) as the technologies create their own demonstration effect.

Key Steps

The following schematics show the evolution of the process by which a technology is introduced and inserted into the marketplace, with subsidies aimed at technology transfer and market development, but not at production costs, or recurrent costs required to sustain supply under free market conditions.

In Step 1, which lasts about a year, it is assumed that neither manufacturers nor retailers are ready to invest in making or selling the pump because it is an unproven product. ApproTEC’s interventions are, then, principally designed to reduce perceived levels of risk without distorting the pricing structure that is needed for long-term sustainability. Mark-ups are substantial, totaling 50% or more ex-factory to end-user. ApproTEC works directly with Manufacturers and Retailers and indirectly with end-users, who benefit from the ApproTEC-backed guarantees and are made aware of the pump through publicity. At the end of this stage it can be expected that consumers are aware of the pump and its benefits, while manufacturers and retailers should be convinced of the pump’s potential to provide a competitive return on investment. It is appropriate at this point to create more direct linkages between the manufacturer and retailers.

In Step 2 ApproTEC continues to work with retailers and manufacturers, but starts to work with wholesalers.

Wholesalers can be convinced to work with ApproTEC because sales figures from Step 1 show that handling the pump provides a competitive return on capital invested, with significant growth potential. Wholesalers receive market intelligence (where the pump is selling well and who are the high-quality retailers who pay up in full and on time) from ApproTEC and financial assistance to invest in low-cost publicity instruments (calendars and the like). ApproTEC no longer provides credit to the retailer who now receives it from the wholesaler. The credit is no longer open-ended consignment credit but 30 days on presentation of invoice. ApproTEC backs this credit with guarantees: if the retailer doesn’t pay up, after 60 days the wholesaler can get his money from ApproTEC to whom the debt reverts. The retailer is cut off from wholesaler credit.

In Step 3, which lasts about a year, ApproTEC’s principal relationship is with the manufacturer.

In this stage, which lasts about a year, the manufacturer is financed with an ApproTEC-guaranteed commercial loan (see below) to manage the credit chain through wholesalers and retailers. ApproTEC’s operational involvement is to assist the manufacturer manage his credit chain by using marketing staff to make follow-up visits to delinquent wholesalers and retailers, but only for a limited period of six to nine months, while the relationships establish themselves and stabilise.

During this stage the manufacturers purchase tools and equipment and take over quality control responsibilities. The operating assumption here is that manufacturers accept the commercial benefits of maintaining a reputation for high product quality through investments in quality control. Ultimately this function has to become embedded in market relationships rather than remaining driven by contractual obligations to ApproTEC. It is essential for the sustainability of production, distribution and supply that there is a steady increase in investment amongst all the players in the pump.

# Finance

By far the most critical part of this stage is the development of formal financing arrangements. The limited stock of capital available to manufacturers, wholesalers and retailers is usually insufficient to maintain supply at projected rates of demand and, to ensure sustainability, it is essential to inject liquidity to the tune of about 3-months turnover at all levels. In short, there

is certain to be a deficit of private investment capital available to finance inventory, stocks of raw material and work in progress. ApproTEC has determined that he most practical point at which ApproTEC should facilitate investment is neither through retailers nor wholesalers. Retailers are too many and the costs of managing a large, geographically diverse portfolio would be too high, and financially unsustainable. Wholesalers are unsuitable recipients of formal debt finance because they already receive it in the form of supplier credit and are averse to paying the high cost of commercial capital.  Instead it is more practical to provide manufacturers with sufficient working capital - as long-term commercial debt. This is mainly because the costs of programming and managing a single loan to a manufacturer is much less – and much less risky – than doing so across a swathe of 100+ retailers and wholesalers. By doing this manufacturers are then able to provide 60 days credit to wholesalers, who themselves can be expected to maintain credit relationships to approved retailers. Such arrangements are also simpler in terms of brokering and guaranteeing commercial credit.

Final Inter-Firm Relationships and Embedded BDS

ApproTEC Tanzania is at present in the final stages of Step 3 and will terminate all relationships with wholesalers and retailers by the end of November 2003. A relationship with the manufacturer will remain until March/April 2004 in order to complete the transition to NMB finance. A further longer-term relationship will then emerge as ApproTEC introduces new products, such as the re-designed hand pump and the Xtra-cycle.

With respect to the MoneyMaker Plus treadle pump the following types of inter-institutional/firm BDS will remain embedded.

| Institution/FirmReceiving BDS | BDS | Supplier of BDS | Role |
| --- | --- | --- | --- |
| Manufacturer | Product quality and acceptability feedback Quality control Business planning and financial services (credit) support New product development and transfer | Wholesaler Private consultant National Microfinance Bank Manufacturer and ApproTEC | Provider Provider Provider Provider Facilitator |
| Wholesalers | Delivery of products Manufacturer credit Guarantee support | Manufacturer Manufacturer Manufacturer | Provider Provider Provider |
| Retailer | Delivery of Products Credit Promotion Guarantee support Feedback via guarantees | Wholesaler Wholesaler Wholesaler Wholesaler/ manufacturer End user | Provider Provider Provider Provider Provider |
| End Users/MSEs | Provision of products/pumps Guarantee support Advice Informal credit | Retailer Retailer Retailer/wholesaler/ manufacturer Retailer Retailer | Provider Provider Provider Provider Provider |

Results

Table 1:	Total Sales to Date by Region/by Month

| Place | Summary of Pump Movement by Region, 2003 |
| --- | --- |
|  | Cumulative | July | August | Sept. | Total |
| Market Test | 438 |  |  |  | 438 |
| Zone 1 (Lake Zone) | 2,070 | 150 | 210 | 190 | 2,620 |
| Zone 2 (Arusha/Tanga) | 1,999 | 90 | 35 | 47 | 2,171 |
| Zone 3 (Dar, Morogoro, Dodoma) | 1,163 | 150 | 95 | 130 | 1,538 |
| Zone 4 (Iringa, Mbeya) | 767 | 62 | 137 | 50 | 1016 |
| Exports | 1,050 | 300 |  | 300 | 1,650 |
| Total | 7,487 | 752 | 477 | 717 | 9,433 |

Table 2:	Detailed Breakdown of Sales in Preceding Year

Table 3 on the following page is a summary of impact at the levels of:

- Jobs created

- Gender Analysis

- Financial Benefits

- Sales summary

The benefit cost figures are based on a projected 3-year life for the pump. Prior estimates were based on $350 annual net benefits to pump buyers, since this was our measure for users after one year. After 2 years, however, the average net benefit has risen to $777. Our global figures, based on a 3 year pump life, thus assume a total benefit of $1,904 per user ($350+777+777).

### Impact

The acquisition of micro-irrigation technologies increases income from horticulture by 337% (an average net income increase of $777 from $230 to $1,007). Table 7 below indicates net financial benefits to date (as of June 2003).

Table 3:	Estimated Impact re. Labour, Gender, and Financial Benefits for Pump Owners, Manufacturers, Wholesalers and Retailers

The increases in production implied by these figures have proven to be readily absorbed by local and regional markets for vegetables, which are growing. Populations have doubled over the last 20 years, with urban populations expanding faster than the national average. This has given rise to a large and growing cash market for fresh vegetables. In particular demand still outstrips supply by a large margin during seasons when only irrigated vegetables are available.

ApproTEC’s facilitation of BDS, through guarantees to wholesalers (for retailer credit), to the manufacturer (for wholesaler credit) and to banks (for manufacturer credit), has been crucial to creating a system that sustains production and distribution while expanding retail demand. It will also be crucial to ensure expansion of demand and the induction of new players. ApproTEC has been following this path in Tanzania for the past 18 months but on-going facilitation of these services for the next few years is crucial to creating a system that will continue to sustain production, distribution and retail activities while at the same time ensuring expansion of demand and the induction of new wholesale, retail and credit players.

In terms of results in Tanzania we expect sales to increase by decreasing percentages: 45% in 2004, 35% in 2005 and 25% in 2006. This decrease will reflect both the decrease in ApproTEC facilitated marketing activities over the project period and a possible saturation of pumps in key high potential market areas of the country. Life of Project targets are projected as follows:

Table 4: Current and Projected Sales: Tanzania

| Country | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tanzania | 1,217 | 2,364 | 4,250 | 6,162 | 8,318 | 5,200 | 27,511 |
| % Annual Increase |  | 94% | 68% | 45% | 35% | 25% |  |

Table 5:	Direct Financial Benefits to Pump Users and Workers for the Next Three Years

| Item | Projected Sales | Annual Benefit | Aggregate Benefit |
| --- | --- | --- | --- |
| Pump Buyers Year 1 | 5,756 | $777 | 13,417,236 |
| Pump Buyers Year 2 | 7,770 |  | 18,111,870 |
| Pump Buyers Year 3 | 5,000 |  | 11,655,000 |
| Totals | 18,526 |  | 43,184,106 |

With a total project cost (ApproTEC contribution and USAID input) of $ 1,486,792, a ‘Bang-for-Buck’ figure of 29:1 may be anticipated. This figure will rise as pump sales continue on a sustainable basis long after the end of the project. The current Bang-for-Buck figure is 8.8:1, with the total monetary impact imputed to date is estimated at $9.65 million

Future Expansion

ApproTEC Tanzania has facilitated the development of export markets that are now entirely served by a Tanzanian wholesaler who exports mainly to Mozambique and Malawi, with occasional sales to places further afield such as Haiti. In all, 1,650 pumps have been exported to date. This will continue.

The future plans of ApproTEC Tanzania are as follows:

- facilitate continuing growth of the local market by entirely embedding marketing staff in wholesaler operations. Their work will focus on:

- expansion of the existing network

- continuing facilitation of credit relationships between retailers and wholesalers

- low-cost media promotion

- develope export markets in the region through the establishment of wholesaler relationships and facilitation of the development of a retail chain. This will be based on Tanzanian production

- introduce a new mass-marketable product. The main candidates at this time are the new hand-pump and an extension frame for bicycles allowing much greater and more stabe load-carrying.

These initiatives will be carried out with non-DFID funding.

Sales Summary

# Footnotes

There are seven wholesalers.  One, with 6 national outlets handles more than 45% of national sales

If NMB takes over this loan, the interest rate will be 2% per month flat, which computes to about 44% per annum on a declining basis.

Typically a cycle for the introduction of a particular technology takes three to four years.

For example, the NMB presently does not, as a matter of policy, provide working capital to SMEs. Although ApproTEC’s discussions with senior NMB management indicate that they are willing to be flexible in this respect.

For example, the PCR already found indications that not all retailers are willing to stock spare parts for the pump.

An internal audit of ApproTEC Tanzania over the period July 2002 to June 2003 was carried out by the internal auditor of ApproTEC Headquarters in Kenya. The overall conclusions of the internal audit reads as follows: “..in my opinion proper accounting procedures are in place and the existing procedures are adequate to generate accurate and reliable financial records and reports that explain all the financial transactions of the project”.

Similar technologies are, after all, used in many different countries

This is because training costs vary from place to place.  It is relatively cheap to train manufacturers in Nairobi, but as technologies are transferred to countries as far away as Mozambique the costs rise considerably and may well be beyond the capacity of local industrialists to pay.

In Tanzania, year-on-year sales growth runs currently at  67%

25% flat through NMB.  Wholesalers recognize that inventory credit has an imputed interest cost (the pumps cost more) but there is no time-value interest penalty should pumps take longer to sell than anticipated.

Pump life is estimated conservatively.  In normal conditions a pump may be expected to last for 5 years, given regular annual replacement of the rubber piston washers.  Where the water is salty and the pump left with water inside, it can be expected to fail after 4 years.  We have used a 3 year pump life as a worst case estimate.

For Tanzania, results of a 5 field surveys since April 2001 of over 150 pump users: approximately 35 in each of 4 zones.  This involved baseline surveys (Zero-age) plus follow-up at 9 months and at 14 months following pump acquisition

For calculation purposes only, years are computed to begin in September and end in August

Does not include pre-MIPP sales and extrapolates from end September to December.

6 Months

This does not include future stream of benefits.  If these are included the figure rises to $18.941 million

# Text boxes

ANNEX 1: DFID PROJECT PROGRESS REPORT