The Children’s Agenda: Community Action Plan

Programs and policies that work for children and youth:

- Are evidence-based and effective: proven to work

- Get to the root of the problems

- Are integrated and coordinated into a system of support and care

- Cover a continuum of growth from before birth to adulthood

CGR & TCA completed a report commissioned by the City of Rochester, Monroe County, RCSD, UW, and RACF to create 	baseline estimates of children served and dollars spent in each of the areas covered.

| Best Solution: 2015 Goal | Short-Term Goal | Progress |
| --- | --- | --- |
| Expand the Nurse-Family Partnership Program to meet our local need: 1,000 families per year. | Expansion of NFP program capacity to serve 500 families by 2011 | Current Status: 300 families; anticipate 400 families Jan 2011 Medicaid reimbursement for NFP has been approved by the Federal Center for Medicaid Services and billing has begun. Will cover ~1/3 of program costs. $510k from State budget NFP line item designated for Monroe County in 2010; ~$205K in 2011. Federal Health Care Reform includes money for evidence-based home visiting programs, $100M in 2010 ($1.5B over the next 5 years). NYS will receive $4M in 2010. County share unknown NYS COPS funding and UW support continued for NFP. NFP national site visit to Rochester November 4 |
| Increase the number of children in quality child care and early learning settings by 20% through achieving three long-term policy changes. | Increase the number of children receiving child care subsidies by at least 500 by March 2010 to maximize current capacity of ~8,000 slots. | County has enrolled an additional 1,246 children this budget year. Of these 658 children are a direct increase due to the increased dollars and eligibility level. Total NYS child care allocation for Monroe County decreased $2.2 Million in 2011. Eligibility, enrollment, accreditation differential held stable by using Child Care Dollars funding received locally. Policy letter sent to gubernatorial candidates. (REVIEW) |
| Provide high-quality, effective after-school programming for 25% of Rochester children. | Provide after-school programming to at least 300 more Rochester students in 2010. | Increased percentage allocation for Rochester and other Big 4 cities for Extended Day NYS State Grants from 10% to 15%: potential additional ~$1.3 Million dollars available to our community on an annual basis. Additional unused NYS Advantage Afterschool dollars allocated to support Rochester after-school programming $170,000 x 3 years Consulted on project to create new after-school program for ~50 students through Project Hope. New programming through help and partnership with RCSD and Encompass: 110 additional students being served at School #33. Expansion to School #39 to serve ~110 students underway. |
| Take Coping Power Program to full capacity for all children who need it in the Rochester City School District. | Expand Coping Power Program to 4 schools in 2010 as part of a comprehensive approach to violence prevention | Funding available for delivery of Coping Power plus PAThS, Primary Project at 3 RCSD schools Fall 2010: #35, #28, #17. TCA secured $50K in support from City of Rochester that will leverage private match of $50K raised by RACF. UW new Blueprint funding for Coping Power ~$70K. Significant RCSD funding for programming and transportation. NYS Extended Day application submitted for 2 additional schools pending: #2 and #12. Encompass will begin Coping Power at one of its 2 afterschool programs (#33 or #39) this year. Working with Wilson Commencement Park to bring Coping Power to afterschool program there. |